SUNDAYS RIVER VALLEY MUNCIPALITY

(EC 106)

Section 52

Quarterly report

30 September 2012

SEC 52(d) QUARTERLY REPOR ON IMPLEMENTATION OF BUDGET & FINANCIAL AFFAIRS

### INTRODUCTION

Section 52(d) of the Municipal Finance Management Act, 2003 (Act No 56 of 2003) stipulates that the Mayor must within 30 days of the end of each quarter, submit a report to the council

on the implementation of the budget and the financial state of affairs of the municipality;

Section 54 of the Municipal Finance Management Act, 2003 (Act No. 56 of 2003) stipulates as follows:-

Budgetary control and early identification of financial problems

54. (1)	On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must-

(a)	consider the statement or report;

(2)	If the municipality faces any serious financial problems, the mayor must-

(a)	promptly respond to and initiate any remedial or corrective steps proposed by the accounting officer to deal with such problems, which may include-

(i)	steps to reduce spending when revenue is anticipated to be less than projected in the municipality’s approved budget;

(ii)	the tabling of an adjustments budget; or

(iii)	steps in terms of Chapter 13; and

(b)	alert the council and the MEC for local government in the province to those problems.

### PURPOSE OF THIS REPORT

The purpose of this report is to submit the quarterly financial figures for the quarter ending

30 September 2012.

### OPERATING BUDGET PERFORMANCE

Table 1: Operating Budget performance for quarter ending 30 September 2012

|  | APPROVED BUDGET R’000 | PRO-RATA FOR PERIOD R’000 | ACTUAL FOR THE PERIOD R’000 | VARIANCE ACTUAL TO PRO-RATA BUDGET R’000 | % OF PRO-RATA BUDGET R’000 | % OF TOTAL BUDGET R’000 |
| --- | --- | --- | --- | --- | --- | --- |
| EXPENDITURE | 110 302 | 27 575 | 17 739 | (9 836) | 64% | 16% |
| REVENUE | 146 691 | 36 673 | 26 733 | (9 940) | 73% | 18% |
| SURPLUS (DEFICIT) | 36 389 | 9 098 | 8 994 | (104) | 99% | 25% |

### DISCUSSION OF REVENUE BY SOURCE

Table 2:  Operating Revenue vs Budget per service type for the period ending

30 Sept 2012

4.1	Property Rates & Service charges

- Annual rates were charged during July 2012, therefore actual is R3 million more than year to date budget.

- The billing for August and September has not been finalized as at 30 September 2012.  A meeting was held with Pastel on 19 September 2012 to discuss the problems that the municipality has been experiencing with the billing as well as other system related problems which was not resolved even after a number of previous meetings and engagements with them.  Consultants were on site during the week of 25 September 2012 to try and resolve matters.  It was found that the database was corrupt and that was the cause of the billing problems.  The database were send to Johannesburg to be fixed and municipal staff are now busy catching up on the billing for August and September 2012.

# 4.2	Finance Income

- Interest on outstanding debtors will be charged with the August and September billing run.

# 4.3	Fines

- Traffic fines did not realize as anticipated.

# 4.4	Licenses and Permits

- Drivers license fees are 64% under recovered and according to the Traffic department the main reason is shortage of staff to perform the function.

4.5	Agency Fees

- Agency fees indicate no revenue as at 30 September 2012. The allocation of agency fee still needs to be recorded and it is foreseen that the budget will realize by 30 June 2013.

4.6	Government grants and subsidies - capital

- Conditional grants still need to be recorded for the quarter.  This was normally recorded at year end when conditions have been met in total.  A project management functionality has been activated on Pastel to ensure expenditure and revenue associated with conditional grants are recorded as and when transactions take place and not at year end.  This will reflect during the 2nd quarter.

### DISCUSSION OF EXPENDITURE BY ITEM

Table 3:  Operating Expenditure vs budget per expenditure item for period ending

30 Sept 2012

5.1	Employee Related Costs & Social contributions

- A moratorium was placed on new appointments whilst salary increase negotiations were still ongoing.  The appointments of new staff will be revisited once the salary increase and the financial effect thereof have been determined.

5.2	Repair and Maintenance

- The main focus for this quarter was on resealing of roads and repairs to buildings and structure.

- Repairs on infrastructure will commence during 2nd quarter

- Procurement plan has been requested from the various directorates to ensure proper planning of expenditure

5.3	Debt impairment:

- Calculation is done at year end

5.4	Depreciation

- The calculation on the Pastel system can be done on monthly basis, but due to problems experiencing with the calculation during August and September this was not done.

- It was discovered that the system used incorrect accounting periods and methods to calculate the depreciation and the error was subsequently fixed.

5.5	Finance charges

- Finance charges on lease contracts have not been recorded yet.

# 5.6	Transfers and Grants

- This reflects the subsidies given to indigent households.  Due to the billing not done for August and September 2012, the subsidies given to indigents could not be recorded.

5.7	General Expenditure

- Grant expenditure on conditional grants (operating) still needs to be recorded (R866 485 YTD budget)

- This was normally recorded at year end when conditions have been met in total.  A project management functionality has been activated on Pastel to ensure expenditure and revenue associated with conditional grants are recorded as and when transactions take place and not at year end.  This will reflect during the 2nd quarter.

- Training for Councilors did not start yet (R146 250 YTD budget) which also have an impact on the under spending of subsistence and travel for councilors (R116 600 YTD budget)

# 5.8	Contribution to provisions

- To be recorded at year end.

### DISCUSSION OF REVENUE AND EXPENDITURE PER VOTE

Table 4:  Revenue per Vote - actual vs budget for period ending 30 September 2012

# Discussion on Revenue

# 6.1	Executive & Council

# Full portion of Equitable share budgeted for the year has been allocated

# 6.2	Finance & Administration

- Annual rates and taxes were levied during July 2012

- Billing for August and September 2012 were not done as at 30 September 2012.  Please refer to previous comments made with regards to the billing issues on Pastel

- Revenue from grants (operating) e.g. Finance Management grant and MSIG grant still needs to be recorded (R575 000 YTD budget)

- This was normally recorded at year end when conditions have been met in total.  A project management functionality has been activated on Pastel to ensure expenditure and revenue associated with conditional grants are recorded as and when transactions take place and not at year end.  This will reflect during the 2nd quarter.

# 6.3	Planning & Development

- MIG PMU grant, EPWP grant and LED still needs to be recorded.  Please refer to previous comments with regards to capital and operational grant recording (R567 735 YTD budget).

# 6.4	Community Services

- Library grant has not been received yet (R289 250 YTD budget)

# 6.5	Sports & Recreation

- MIG grant expenditure & associated revenue has been recognized on sports fields.  MIG allocation according to budget needs to be corrected as it was not allocated to sports fields.

# 6.6	Environmental Services

- Environmental health subsidy has not been received yet (R241 985 YTD budget)

# 6.7	Roads & Transport

- Income from the drivers license test centre has not realized as anticipated (64% under recovery).  According to the Traffic department this is due to shortage of staff

# 6.8	Waste Management, Waste Water Management, Water Management & Electricity

- Billing for August and September still needs to be finalized.  Please refer to previous comments with regards to Pastel problems

# Table 5:  Expenditure per Vote - Actual vs budget for the period ending 30 Sept 2012

Discussion on Expenditure

6.9	Finance & Administration

- Bad debt, depreciation and finance cost on leases captured at year end (total amount budget YTD R5.7 mil)

6.10	Planning & Development

- PMU Expenditure not recorded yet – see previous comments with regards to conditional grant expenditure (YTD budget – R283 987)

- IDP projects not started yet includes – community based planning, IDP review and Business plan development – this will commence closer to the 3rd quarter (YTD budget – R50 000)

- LED projects not started yet includes – Co-operative development,  Learnership, LED support Invest & study (YTD budget – R65 547)

6.11	Roads & Transport

- Repairs & maintenance under spent with R211 200.

- Interest on lease payments not recorded yet R62 000

- Under expenditure on general expenditure

6.12	Housing

- Under expenditure on general expenditure R30 000

6.13	Waste Management

- Billing for August and September was not done as at 30 September 2012.  The subsidy allocated to indigent debtors could thus not be recorded (R330 000 YTD budget)

- Under expenditure on repairs & maintenance (R136 000)

6.14	Waste Water Management

- Under expenditure on repairs & maintenance (R233 000)

- Billing for August and September was not done as at 30 September 2012.  The subsidy allocated to indigent debtors could thus not be recorded (R212 000 YTD budget)

6.15	Electricity

- Under expenditure on Repairs and maintenance – R158 583

- Saving on bulk electricity – R38 450

- Commission paid on prepaid electricity not paid – R36 756

6.16	Water

- Billing for August and September was not done as at 30 September 2012.  The subsidy allocated to residents could thus not be recorded (R209 270 YTD budget)

- Under expenditure on Repairs and maintenance – R111 740

### DISCUSSION OF CAPITAL EXPENDITURE

Table 6:  Capital Expenditure Actual vs budget as at 30 September 2012

# The MIG projects (Sports fields, Water reticulation, Roads, Sewerage) are all in progress.  The majority of projects were in tender stage during first quarter and it is anticipated that expenditure will increase during the 2nd quarter.

# Capital from own funds were hampered this quarter due to the financial situation of the municipality.

### CONDITIONAL GRANTS RECEIVED AND EXPENDITURE ON GRANTS AS AT

### 30 SEPTEMBER 2012

Table 7:  Conditional grants received and expenditure on grants

| GRANT | RECEIVED | EXPENDITURE |
| --- | --- | --- |
| Finance Management grant | R1 500 000 | R814 826 |
| Municipal Systems Improvement grant | R800 000 | R430 000 |
| MIG | R6 970 000 | R1 903 681 |
| EPWP | R400 000 | NIL |

Finance Management grant and Municipal Systems Improvement Grant expenditure is well under way.  Majority of MIG projects were still on tender stage during first quarter and expenditure should increase during 2nd quarter.  It is anticipated that the full MIG grant will be spent.  EPWP expenditure will start during 2nd quarter.

### CASH FLOW POSITION AS AT 30 SEPTEMBER 2012

Table 8: Summary of Cash flow position (Primary Bank Acc) as at 30 September 2012

| CASH BALANCE B/F FROM 1 July 2012 | 1 351 022 |
| --- | --- |
| CASH RECEIVED FOR THE YEAR TO DATE | 33 684 657 |
| CASH PAYMENTS MADE FOR THE YEAR TO DATE | 33 686 107 |
| CASH BALANCE AS AT 30 September 2012 | 1 349 572 |

### BANK BALANCE, INVESTMENTS AND BORROWINGS AS AT 30 SEPTEMBER 2012

Table 9: Key Treasury Information as at 30 September 2012

|  | OPENING BALANCE 01/07/2012 | MOVEMENT DURING THE PERIOD | CLOSING BALANCE 30/09/2012 |
| --- | --- | --- | --- |
| CURRENT ACCOUNT | 1 351 022 | (1 450) | 1 349 572 |
| INVESTMENTS | 1 725 694 | 4 076 387 | 5 802 081 |
| TOTAL EXTERNAL BORROWING | 11 316 516 | (396 562) | 10 919 954 |
| DBSA | 1 710 378 | (220 796) | 1 489 582 |
| DWA | 6 704 880 | NIL | 6 704 880 |
| LEASES | 2 901 258 | (175 766) | 2 725 492 |

### COLLECTION RATE

Table 10: Collection Rates as at 30 September 2011

| MAIN TARIFF | AMOUNT BILLED FOR THE YEAR TO DATE | AMOUNT RECEIVED FOR THE YEAR TO DATE | (UNDER)/ OVER COLLECTED | COLLECTION RATE % (RECEIVED/ BILLED) |
| --- | --- | --- | --- | --- |
| PROPERTY RATES | 7 073 700 | 2 239 828 | (4 833 872) | 31.66 |
| ELECTRICITY | 1 688 822 | 1 855 917 | 167 095 | 109.89 |
| WATER | 449 203 | 521 350 | 72 147 | 23.89 |
| REFUSE | 734 394 | 175 431 | (558 963) | 23.53 |
| SEWERAGE | 426 322 | 100 293 | (326 029) | 116.06 |
| SUNDRY/OTHER | 65 473 | 390 219 | 324 746 | 595.99 |
| TOTAL REVENUE | 10 437 914 | 5 283 039 | (5 154 875) | 50.61 |

### AGE ANALYSIS – TRADE DEBTORS AS AT 30 SEPTEMBER 2012

Table11:  Age analysis for period ending September 2012

| QUARTER | TOTAL | Current | 30 DAYS | 60 DAYS | 90 DAYS | 120 + DAYS |
| --- | --- | --- | --- | --- | --- | --- |
| 1st Quarter | 88 447 258 | (182 553) | (478 208) | 9 306 472 | 3 793 232 | 76 008 315 |

R2.1 million was received from Department of Public Works during this quarter.  Between National and Provincial Department of Public Works the total debt still outstanding is R7 million.  Dagbreek Spar owes the municipality R1.5 million and has been handed over to the attorneys.  SANPARKS are disputing that they are responsible for rates and have sent correspondence to the MEC, but no feedback has been received by the municipality.   SANPARKS owes the municipality R5.2 million.

### AGE ANALYSIS – TRADE CREDITORS AS AT 30 SEPTEMBER 2012

Table 12 – Creditors age analysis as at 30 September 2012

|  | TOTAL | CURRENT | 30 DAYS | 60 DAYS | 90 DAYS | 120 DAYS+ |
| --- | --- | --- | --- | --- | --- | --- |
| Trade creditors | 5 301 582 | 1 216 208 | 1 463 476 | (191 815) | 312 851 | 2 500 862 |
| Auditor General | 2 305 057 |  | 29 541 |  | 516 658 | 1 758 858 |
| TOTAL | 7 606 639 | 1 216 208 | 1 493 017 | (191 815) | 829 509 | 4 259 720 |

### CLOSURE

The performance this quarter was hampered due to cash flow constraints.  The problems experienced with the billing system are taking its toll on the cash resources of the municipality.  Discussions with the service provider are ongoing.  The billing problem was resolved during October 2012 and finance staff is ensuring that all meter readings are captured to ensure billing continues.

_________________________

Municipal Manager

______________________

Date