SUNDAYS RIVER VALLEY LOCAL MUNICIPALITY

UNAUDITED DRAFT ANNUAL REPORT 2024/2025

# CONTENTS

CONTENTS	2

REVISED ANNUAL REPORT TEMPLATE	7

CHAPTER 1 – MAYOR’S FOREWORD AND EXECUTIVE SUMMARY	9

COMPONENT A: MAYOR’S FOREWORD	9

COMPONENT B: EXECUTIVE SUMMARY	14

MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT	20

GOOD GOVERNANCE AND PUBLIC PARTICIPATION	22

FINANCIAL OVERVIEW	23

1.1.	MUNICIPAL FUNCTIONS, POPULATION AND ENVIRONMENTAL OVERVIEW	25

Demographic Information	26

SOCIO ECONOMIC STATUS	26

1.2.	SERVICE DELIVERY OVERVIEW	28

1.3.	FINANCIAL HEALTH OVERVIEW	28

1.4.	ORGANISATIONAL DEVELOPMENT OVERVIEW	28

1.5.	AUDITOR GENERAL REPORT	29

1.6.	STATUTORY ANNUAL REPORT PROCESS	29

CHAPTER 2 – GOVERNANCE	32

COMPONENT A:  POLITICAL AND ADMINISTRATIVE GOVERNANCE	32

2.1	POLITICAL GOVERNANCE	32

2.2	ADMINISTRATIVE GOVERNANCE	62

COMPONENT B: INTERGOVERNMENTAL RELATIONS	67

2.3	INTERGOVERNMENTAL RELATIONS	67

2.4	PUBLIC MEETINGS	68

2.5	IDP PARTICIPATION AND ALIGNMENT	70

COMPONENT D: CORPORATE GOVERNANCE	70

2.6	RISK MANAGEMENT	70

2.7	ANTI-CORRUPTION AND FRAUD	71

2.8	SUPPLY CHAIN MANAGEMENT	72

2.9	BY-LAWS	72

2.10	WEBSITES	72

2.11	PUBLIC SATISFACTION ON MUNICIPAL SERVICES	72

CHAPTER 3 – SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT PART I)	73

Road Network Serving the Sundays River Valley Local Municipal Area	82

Municipal Road Network	83

Paved ROADS	86

Visual Condition Assessments	86

Current Visual Condition 	86

MAINTENANCE	88

Unpaved Roads	91

Visual Condition Assessments	91

Current Visual Condition	91

1.	MUNICIPAL ROADS ASSESSMENT	93

7.1.1 HIGH MAST LIGHTS MAINTENANCE 	113

4.4	WASTE MANAGEMENT (THIS SECTION TO INCLUDE: REFUSE COLLECTIONS, WASTE DISPOSAL, STREET CLEANING AND RECYCLING)	121

3.5	HOUSING	122

3.8	TRANSPORT (INCLUDING VEHICLE LICENSING & PUBLIC BUS OPERATION)	124

COMPONENT C: PLANNING AND DEVELOPMENT	125

LOCAL ECONOMIC DEVELOPMENT OVERVIEW	125

COMPONENT D: COMMUNITY & SOCIAL SERVICES	130

3.12	LIBRARIES; ARCHIEVES; MUSEUMS; GALLERIES; COMMUNITY FACILITIES; OTHER (THEATRES, ZOOS, ETC)	130

3.13	CEMETORIES AND CREMATORIUMS	135

3.14	CHILD CARE; AGED CARE; SOCIAL PROGRAMMES .	147

COMPONENT E: ENVIRONMENTAL PROTECTION	148

3.15	POLLUTION CONTROL	148

3.16	BIO-DIVERSITY; LANDSCAPE (INCL. OPEN SPACES); AND OTHER (EG. COASTAL PROTECTION)	149

COMPONENT F: HEALTH	150

3.19	 HEALTH INSPECTION; FOOD AND ABBATOIR LICENSING AND INSPECTION; ETC	150

COMPONENT G: SECURITY AND SAFETY	151

Traffic Services	152

Fire and Disaster Management Plan	153

3.20	POLICE	153

3.21	FIRE	153

COMPONENT H: SPORT AND RECREATION	155

3.23	SPORT AND RECREATION	156

COMPONENT I: CORPORATE POLICY OFFICES AND OTHER SERVICES	162

3.24	EXECUTIVE AND COUNCIL	163

3.26	HUMAN RESOURCE SERVICES	163

3.27	INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES	164

3.28	INTRODUCTION TO LEGAL SERVICES	164

COMPONENT K: ORGANISATIONAL PERFOMANCE SCORECARD	165

CHAPTER 4 – ORGANISATIONAL DEVELOPMENT PERFORMANCE	177

(PERFORMANCE REPORT PART II)	177

COMPONENT A:  INTRODUCTION TO MUNICIPAL PERSONNEL	177

4.1.	Employee Total, Vacancies and Turnover	177

4.2	POLICIES	180

COMPONENT C: CAPACITATING THE MUNICIPAL WORKFORCE	181

4.2	 Workforce Profile	181

People with Disabilities	183

Recruitment	184

Skills Matrix	184

4.6	EMPLOYEE EXPENDITURE	185

CHAPTER 5 – FINANCIAL PERFORMANCE	186

COMPONENT A: STATEMENTS OF FINANCIAL PERFORMANCE	186

5.1	STATEMENTS OF FINANCIAL PERFORMANCE	188

5.2	GRANTS	189

5.3	ASSET MANAGEMENT	190

5.4	FINANCIAL RATIOS BASED ON KEY PERFORMANCE INDICATORS	191

5.5	CAPITAL EXPENDITURE	194

5.6	SOURCES OF FINANCE	195

5.7	CAPITAL SPENDING ON 5 LARGEST PROJECTS	196

5.8	BASIC SERVICE AND INFRASTRUCTURE BACKLOGS – OVERVIEW.	197

COMPONENT C: CASH FLOW MANAGEMENT AND INVESTMENTS	197

5.9	CASH FLOW	197

5.10	BORROWING AND INVESTMENTS	198

5.11	PUBLIC PRIVATE PARTNERSHIPS	199

COMPONENT D: OTHER FINANCIAL MATTERS	200

5.12	SUPPLY CHAIN MANAGEMENT	200

5.13	GRAP COMPLIANCE	200

CHAPTER 6 – AUDITOR GENERAL AUDIT FINDINGS	201

COMPONENT A: AUDITOR-GENERAL OPINION OF FINANCIAL STATEMENTS Year -1	201

6.1 AUDITOR GENERAL REPORTS Year -1 (Previous year) SRVM AUDIT REPORT - 30 June 2023	201

COMPONENT B: AUDITOR-GENERAL OPINION YEAR 0 (CURRENT YEAR)	201

6.2 AUDITOR GENERAL REPORT YEAR 0	201

GLOSSARY	203

APPENDIX A – COUNCILLORS; COMMITTEE ALLOCATION AND COUNCIL ATTENDANCE	206

APPENDIX B – COMMITTEES AND COMMITTEE PURPOSES	210

APPENDIX C –THIRD TIER ADMINISTRATIVE STRUCTURE	211

APPENDIX D – FUNCTIONS OF MUNICIPALITY / ENTITY	212

APPENDIX E – WARD REPORTING	213

APPENDIX F – WARD INFORMATION	217

APPENDIX G – RECOMMENDATIONS OF THE MUNICIPAL AUDIT COMMITTEE	218

YEAR 0	218

APPENDIX H – LONG TERM CONTRACTS AND PUBLIC PRIVATE PARTNERSHIPS	222

APPENDIX J – DISCLOSURES OF FINANCIAL INTERESTS	224

APPENDIX K:  REVENUE COLLECTION PERFORMANCE BY VOTE AND BY SOURCE	225

APPENDIX K (i): REVENUE COLLECTION PERFORMANCE BY VOTE	225

APPENDIX K (ii): REVENUE COLLECTION PERFORMANCE BY SOURCE	225

APPENDIX L:  CONDITIONAL GRANTS RECEIVED: EXCLUDING MIG	226

APPENDIX M:  CAPITAL EXPENDITURE – NEW & UPGRADE/RENEWAL PROGRAMMES	226

APPENDIX M (i): CAPITAL EXPENDITURE - NEW ASSETS PROGRAMME	226

APPENDIX M (ii): CAPITAL EXPENDITURE – UPGRADE/RENEWAL PROGRAMME	229

APPENDIX N – CAPITAL PROGRAMME BY PROJECT YEAR 0	232

APPENDIX O – CAPITAL PROGRAMME BY PROJECT BY WARD YEAR 0	232

APPENDIX Q – SERVICE BACKLOGS EXPERIENCED BY THE COMMUNITY WHERE ANOTHER SPHERE OF GOVERNMENT IS RESPONSIBLE FOR	233

SERVICE PROVISION	233

APPENDIX R – DECLARATION OF LOANS AND GRANTS MADE BY THE MUNICIPALITY	234

APPENDIX S – NATIONAL AND PROVINCIAL OUTCOMES FOR LOCAL GOVERNMENT	236

# REVISED ANNUAL REPORT TEMPLATE

The purpose of this revised Annual Report template is to address the need expressed by several municipalities for assistance in the preparation and development of improved content and quality of Municipal Annual Reports. This template provides an update to the MFMA Circular No. 11, issued in January 2005.

This template gives effect to the legal framework requirement, concepts and principals espoused in the White Paper on Local Government and Improving Government Performance.  It reflects the ethos of public accountability. The content gives effect to information required for better monitoring and evaluation of government programmes in support of policy decision making. The template provides an improved overview of municipal affairs by combining the performance report data required under Municipal Systems Act Section 46 with annual report data referred to in that Act and in the MFMA.

The revised template makes its contribution by forging linkages with the Integrated Development Plan, Service Delivery and Budget Implementation Plan, Budget Reforms, In-year Reports, Annual Financial Statements and Performance Management information in municipalities. This coverage and coherence are achieved using interlocking processes and formats.

The revised template relates to the Medium-Term Strategic Framework particularly through the IDP strategic objectives; cross cutting nature of services offered by different spheres of government, municipal service outcome indicators; and the contextual material as set out in Chapters 3, 4 & 5.  It also provides information on good management practice in Chapter 4; risk management in Chapter 2; and Supply Chain Management in Chapter 5; and addresses the Auditor-General’s Report, dealing with Financial and Performance Management arrangements in Chapter 6. This opens greater possibilities for financial and nonfinancial comparisons between municipalities and improved value for money.

The revised template provides information on probity, including anti-corruption strategies; disclosure of financial interests by officials and councillors; disclosure of grants by external parties, disclosure of loans and grants by municipalities. The appendices talk to greater detail including disaggregated information on municipal wards, among others. Notes are included throughout the format to assist the compiler to understand the various information requirements.

The financial years contained in this template are explained as follows:

- Year -1: The previous financial year.

- Year 0: The financial year of reporting.

- Year 1: The following year, mostly requires future targets; and

- The other financial years will follow a similar sequence as explained above.

We wish to express our gratitude to the members of the Annual Report Reference Group, consisting of national, provincial, and municipal officials for their inputs and support throughout the development of this document.

MFMA Implementation Unit, National Treasury                                                          July 2012

# CHAPTER 1 – MAYOR’S FOREWORD AND EXECUTIVE SUMMARY

## COMPONENT A: MAYOR’S FOREWORD

MAYOR’S FOREWORD - Vision: “A people-centered Municipality providing efficient and effective services to communities.” - Key Policy Developments: The SRVM Council has adopted the five-year strategic plan (IDP), and it is my great honor and appreciation to table the third IDP to you as stakeholders of the SRVM. Our IDP was assessed by the MEC and was confirmed to be basic, and introspection and reviews were done in order to improve the IDP 2025-2026 financial year. Sundays River Valley municipality has embarked on policy reviews in the 2024/2025 fiscal year with the primary objective of running clean administration on the principles of good cooperative government. All the compliant budget related policies were reviewed and adopted with the final Budget on the 30th of May 2024. A cash-less policy was developed by our traffic services unit. Other policies were reviewed to close the gaps and improve operational efficiency. The municipality stabilized in terms of senior management composition of all sec 56,57 positioned filled. Key Service Delivery Improvements: The following are the key delivery improvements in the fiscal year. The municipality through the intervention of the following grants: MIG, WSIG, INEP and EPWP ,the following were achieved: - Upgrading of roads and stormwater Enon-Bersheba - Construction of multipurpose sport recreational facility in Nomathamsanqa in Addo - Construction of Community Hall in Moses Mabida - Refurbishment of Enon Bersheba water borehole sanitation - Infrastructure asset management - Emergency flood repair at Vygie and adams Street in Valencia - Construction of roads and stormwater in Paterson - Augmentation of the water reticulation network in Paterson - Construction of bilk water reticulation on Molly Blackburn Over and above these projects, there is continuous Pothole patching across the SRVM. The introduction and operationalization of the new RTMC system Learners License test system. SRVM participated in the National Arbor City Awards and received (Position 2) on greening and Sarah Baartman Greenest municipality Awards received (Position 3) respectively. - Public Participation: The following mechanisms were used to ensure our commitment towards an accountable, efficient, and transparent government: - Ward Committees - IGR Forum - IDP Representative Forum - Public meetings - Other statutory forums - Social Media The above mentioned are the Methods and/or processes used to increase public awareness on service availability engage public in decision making and improve accountability to communities. - Future Actions: The municipality intends to improve its service delivery and will also ensure the following outcomes are realized: - Critically important is the monitoring of the development and implementation of audit action plan 2024/2025 to improve our audit finding. - The municipality is in the process of quantifying all complaints received by the municipality through a what’s-up link. In future we will be able to report on all complaints received and report on complaints resolved and reasons for those that were not resolved. - The municipality takes note of the COGTA Support plan and intends to make that a standing item in its strategic engagements. - Establishment of Community safety forum - To address the low revenue challenge, the municipality has refurbished the Driver’s license testing ground in Aqua Park for testing. - Establish a Risk management committee and Risk management unit. - Establishment of a Legal services department - Improve grant expenditure to increase funding appetite from external sources. - Improve sustainable water supply to attract and retain investment in Sundays River Valley - Construction of a weigh bridge targeting trucks diverting from N10 as a revenue source - The MEC’s comments of the IDP of the municipality are taken into consideration in the municipal operational plans, but funding of some of the recommendations remains a challenge. - It is important to note that some of the plans needed to be in place can be achieved with external financial support and engagements therefore are ongoing. These include the development of Air Quality Management Plan, Integrated Waste Management Plan (Review), Community Safety Plan and Strategy, Climate Change Response Strategy, Infrastructure Maintenance Plan (Review), Development of a Regional Landfill Site. - We intend to improve cleanliness of the Sundays River Valley municipal area and eradicate illegal dumps, utilizing sustainable methods. - The construction of District offices in SRVM is a reality, the EIA processes are underway. - We must ensure there is a reduction and or elimination of irregular, fruitless and wasteful expenditure. - The following map represents planned citrus and Agri-developments within our municipal space: Initiatives committed whereby service delivery will be improved over the next few years. Agreements / Partnerships: Sundays River Valley Municipality commits to honor all agreements that we entered with government departments and other agencies such as: - SANRAL – Road’s development projects - South African Local Government Association (SALGA) – Bargaining Council Collective Agreements - Auditor General – Audit fees - DEDEAT – Environmental Impact Assessment Services. Conclusion: Quoting from NECTAC Interactive Guide (2014), the successful implementation of any service delivery approach is dependent on widespread support among a diverse stakeholder group. Change requires champions, advocates and committed leadership. Stakeholders likely to be resistant should also be included and their input used to address concerns and garner more persuasive information. That is the reason our municipality values the contributions of other stakeholders in the development and service delivery initiatives that we boast about. The real success of Sundays River Valley Municipality will only be fully celebrated when we are eventually able to provide an efficient and effective service delivery to all our communities. With the same breath the Intergovernmental Relations Forum is supported to provide shared value and unlock bottlenecks on service delivery, share resources and plans. As the municipality, however, we have committed, capacitated, with tenacity to do it only if and only if we are all prepared to walk the talk. I would like to thank the public, councilors and the administration and sector departments and all other stakeholders for their endeavors and their pledges in ensuring that we succeed in our primary duty to bring services to the communities of SRVM. Mayor S. Lucas

## COMPONENT B: EXECUTIVE SUMMARY

MUNICIPAL MANAGER’S OVERVIEW INTRODUCTION This Annual Report is prepared in accordance with the guidelines of Circular 63 issued by the National Treasury. The purpose of the Annual Report is: - To provide a record of the activities of the municipality or entity during the fiscal year to which the report relates. - To provide a report on performance in service delivery and budget implementation for the fiscal year. - To promote accountability to the local community for the decisions made throughout the year by the municipality or municipal entity; and - To reduce the additional reporting requirements that will otherwise arise from Government Departments, monitoring agencies and financial institutions. The Integrated Development Plan (IDP) serves as a blueprint which guides and informs all planning, budgeting, management, and decision-making processes of the municipality. The Service Delivery and Budget Implementation Plan (SDBIP) is a yearly implementation tool for the priorities and projects identified in the IDP. The in-year quarterly reports on the SDBIP are consolidated into an annual performance report as contained in component K (Organisational Performance Scorecard) of the Annual Report. The executive summary provides a broad overview of the performance of the municipality in terms of its priorities and council oversight role. For the year under review the priorities that were approved by Council are: - Provision of Infrastructure and Basic Services - Local Economic Development - Community and Social Services - Institutional Transformation and Organizational Development - Good Governance and Public Participation - Financial Viability and Management OVERSIGHT ROLE The Council is the decision-making body of the municipality in line with the provisions of the relevant legislation. The IDP and the Budget are two important policy documents which are not delegated to any other Council structures for approval but the Council itself. All councilors participate in standing committees to deliberate issues and make recommendations to the Executive Committee and Council. The council is led by the Speaker, and the Executive Committee is led by the mayor. The council has established an Audit and Risk Committee (ARC) and the Municipal Public Accounts Committee (MPAC) to assist Council in its oversight role. The Intergovernmental Relations Forum sits quarterly, and it provides a platform where departments share and report on programs and projects they implement in our municipal space. There are, however, challenges in terms of attendance of the forum by sector departments. PROVISION OF INFRASTRUCTURE AND BASIC SERVICES This Key Performance Area (KPA) has the following Key Performance Elements (KPE) of focus areas: [Water, Sanitation, Electricity, Housing, Roads and Storm Water, Spatial Planning] 2024/ 2025 MIG CAPITAL BUDGET Sundays River Valley Municipality has received R 64 518 828.70 under the Division of Revenue Act to implement its capital commitments. Project Name; EPWP Y/N; Category (B, P or E); Project Type (water, sanitation etc.); Funder; Budgeted In 2024/25. Upgrading of Roads &Stormwater in Enon and Bersheba – Phase 2; Y; B; Roads; MIG; R 11 069 402. Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo; Y; P; Sports Facility; MIG; R 3 112 900. Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo; Y; P; Sports Facility; MIG; R 10 000 000. Construction of a New Community Hall in Moses Mabhida; Y; P; Community; MIG; R 4 030 119.00. Refurbishment of Enon and Bersheba Water Borne Sanitation- Phase 1; Y; B; Sanitation; MIG; R 4 990 690. Emergency flood works in Vygie and Ada4m Street; N; B; Sanitation; MIG; R2 446 218. Infrastructure Asset Management; N; N/A; N/A; MIG; R 752 500. Electrification of Bergsig Household; N; B; Electrification; INEP; R 2 495 000. Refurbishment of Kirkwood & Addo Wastewater Pumps (Kirkwood); Y; B; Sanitation; WSIG; R 6 419 796,00. Provision of Water and Sanitation services of Nomathamsanqa and Molly Blackburn; Y; B; Water; WSIG; R 6 507 689,29. Refurbishment of Addo Sewer Treatment Works and Moses Mabhida Sewer Reticulation; Y; B; Sanitation; WSIG; R 5 072 514.71. Installation of Energy saving Lights; Y; B; Electrification; EEDSM; R 4 000 000. Upgrading of Kirkwood internal Roads; Y; B; Roads; EPWP; R 949 000. LOCAL ECONOMIC DEVELOPMENT The above priority area includes some of the following key performance elements [SMME development, Agriculture, Tourism]. COGTA has 8 KPIs that must be reported on. The following table depicts those KPIs: No.; KEY PERFORMANCE INDICATOR; DELIVERABLES. 1; Existence of an LED Unit; The municipality does not have a unit for local economic development (LED), but one staff member. The municipality lacks human capacity to monitor the implementation of LED programmes including tourism and agricultural related programmes.. 2; % Of LED budget spent on LED activities; Operational expenditure incurred(100%) to be verified . This is due to low revenue collection which affects the cash flow of the municipality.. 3; Existence of an LED Strategy; The strategy is under review with assistance of COGTA. Various strategy review sessions held.. 4; Functionality of LED forums; The municipality has a functional SMME forum though there are administrative challenges emanating from the SMME structures. The Addo Elephant Park and the district run successful economic development forums where the municipality participates. 5; Plans to stimulate the second economy; There are plans to revive township tourism through the introduction of a cultural (music) festival. SANRAL are revitalizing our areas through roads infrastructure projects. The Municipality is in the process of updating its SMME policy. The Informal Trading draft policy is in place and functional Informal Trading Committee in place.. 6; % of SMME supported during the fiscal year; The following Support is provided to SMME: Policy development, Business License’s, Company registrations, SMME outreach programmes, SMME Communication and ongoing business advise.. 7; % of job created through PPP; The municipality has no PPP. 8; # of jobs created through EPWP; 161. At least 161 jobs were created through infrastructure projects and EPWP initiatives. SMME development is well catered for by the SMME Coordinator. The Addo Elephant Park and local tourism organization are primarily responsible for tourism development in the municipal area while the local office of the Department of Rural Development and Agrarian Reform attends all agricultural related programmes COMMUNITY AND SOCIAL SERVICES This priority area deals with the following focus areas: [Traffic Services, Fire & Disaster Management Services, Environmental Health, Libraries, Cleansing, Community and Social Amenities, Disaster and Transport]. The traffic services are fully functional. We are doing the refuse collection in all the wards in-house including informal settlements that are accessible. Our Environmental Health Practitioners were seconded by Sarah Baartman district municipality in SRVM as peace officers. Food sampling is done using the food sampling equipment that was bought. The Sport function is no longer the function of the municipality but of DASRC. The community services official is responsible for the maintenance of community and social amenities. ### MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT KEY PERFOMAMNCE INDICATOR; PERFORMANCE OUTCOMES. Vacancy rate for all approved posts; 10% against 10% target for the year (31 vacant post against staff compliment of 308). Appointments in s57/56posts; 5 (Full complement). % of section 54/56 attending at least 1 training course; Director: CS attended an OD course. % of Managers in Technical service with professional qualification; 97%. Level of effectiveness of PMS in the LM; Not fully effective. Reviews are done for ALL Senior Managers, and PMS has been cascaded to middle management with effect from 01 July 2024 and Performance Agreements signed. SRVM following a staggered approach to cascading and other levels from 10 downwards with be contracted from 01.10.2024 to attain 100% compliance. PMS Workshop was conducted by COGTA to the municipal employees and Councilors. The Performance Management Policy was reviewed and adopted by Council .. Adoption and implementation of HRD including WSP; WSP/ATR submitted to LGSETA on time, and its implementation at 70% targeted training with an annual budget of R800 000 for municipal officials and 300 000 for Councilors.. % of staff that have undergone skills audit within the current five-year term; No comprehensive institutional skills audit conducted. 25.3% (68 of 269 employees completed individual audit forms). % of councilors who attended a leadership training within the current five-year term; 87.5% (15 of 16 councilors). % of staff complement with disability; 2.4% (5 employees) above national target of 2%.. % of female employees; 38% (103 of 269). % of staff aged 35 or less; 25% (69 of 269). The municipality is supported by Sarah Baartman District Municipality to review and develop job descriptions for our staff which would contain job titles and job content. For this, these job descriptions would assist in embarking on a job evaluation process wherein jobs would be evaluated to arrive at systematic ranking of jobs, and to determine the worth of jobs. The organogram for the municipality was reviewed and approved by the Council on the 8th of July 2022 and undergoes a review process for the next MTEF period. The organogram has a total of 136 approved positions and 129 has written job descriptions which were all subjected to the job grading process since 2022/23. A total of 109 jobs has been graded and completed as at the end of the fiscal year 2023/24. The district has assisted with the development of a Job Evaluation Policy which was approved on the 8th of July 2022 and same is being reviewed for 2024/25 fiscal year. On the organizational structure, the Council is obliged to review it on an annual basis to be aligned with the provisions of the IDP and the budget. However, such alignment becomes a challenge due to additional demands and responsibilities that the structure should respond to. The reviewed organogram has been workshopped to the Councilors and inputs consolidated into the reviewed organogram and awaiting Council approval. The staff component of the municipality as per organogram is comprised of 306 members of which 248 posts have been filled with 39 vacancies in existence. The strategic positions of the PMU Manager and Town Planner were filled. In the ICT area of work, many challenges were identified during the audit conducted by Auditor General. Such areas have been developed in the form of an Action Plan to be addressed. Policies have been drafted and tabled for adoption by the Council. The Workplace Skills Plan has been developed to become a guided framework for training staff. The skills audit is conducted on an annual basis to be certain about skills training to concentrate on. Only 3 Traffic Officers were trained on (EDL) Examiner of Driver’s License Grade B, due to financial constraints. ### GOOD GOVERNANCE AND PUBLIC PARTICIPATION NO; KEY PERFORMANCE INDICATOR; PERFORMANCE OUTCOME. 1.; % of ward committees established; 100%. 2.; % of ward committees that are functional; 100%. 3.; Existence of a system to monitor CDWs; None. 4.; Existence of an IGR strategy; We are implementing the provincial strategy and have developed our own Terms of Reference. 5.; Effectiveness of IGR structural meetings; Meetings are held quarterly, and minutes are kept.. 6.; Existence of an effective communication strategy; The Draft Strategy is in place; however, the plans attached to it are being implemented.. 7.; No of Mayoral Imbizos conducted; 8 Mayoral IDP outreached conducted. 8.; Existence of fraud prevention mechanisms; Draft Fraud Prevention Strategy is currently under review.. The municipality is doing performance management system manually because of financial constraints. We are in consultations with the Unions to have the PMS cascaded to all municipal employees. That will require a performance incentives plan to be in place. It has been a challenge to hold quarterly performance assessments due to late submission of portfolios of evidence. The coordination of IGR meetings by the municipality is efficient and effective, however there are still departments who do not attend or send junior officials who cannot take decisions at IGR meetings. Communities were consulted during IDP, and budget processes and their priorities were reflected in the IDP. FINANCIAL OVERVIEW : SRVM is a developing or growing municipality simply because it has booming citrus industry and world-renowned national conservation parks. It is one of the economic hubs in Sarah Baartman District Municipality. As a developing municipality it requires additional resources and funding to conduct the growth it desires. COGTA has identified the following KPIs that must be reported on: No.; KEY PERFORMANCE INDICATOR; PERFORMANCE OUTCOME. 1; AG’s audit opinion; 2024/2025 Disclaimer. 2; % of expenditure on capital budget; 100%. 3; Salary budget as a % of the total Opex; 40%. 4; Total municipal own revenue as % of the total actual budget; 42,78%. 5; Rate of municipal consumer debt reduction; 0%. 6; % of MIG budget appropriately spent; 100%. 7; % of MSIG budget appropriately spent; N/A. 8; Functionality of the audit committee; The audit committee hold meetings as often as possible and provides recommendations to Council for implementation. 9; Trade creditors as a % of total actual revenue; 30,82%. 10; Submission of AFS after the end of financial year; 31 August 2025. As there are limits on revenue, it is necessary to ensure that services are provided at levels that are affordable. Our biggest challenge with our financial plan is to match increased service demands with a stagnant revenue base. Financial viability and management remain one of the key priorities of the Council. It remains more critical in the light of the current economic situation, which among other things is self-sustenance and prudent financial controls MUNICIPAL MANAGER (Mr. T Klaas).

### MUNICIPAL FUNCTIONS, POPULATION AND ENVIRONMENTAL OVERVIEW

INTRODUCTION TO BACKGROUND DATA

The Constitution, Chapter 7, Section 152 (1) and (2) as well as Section 153 (a) and (b) obliges and outlines the functions and services that are to be performed by a municipality. Sundays River Valley Municipality is mandated by these pieces of legislation. The only functions that the municipality is not doing are municipal airports, municipal public transport, beaches and amusement facilities, fences and fencing and noise pollution. The municipality is dependent mostly on grants and as a result there is strong cooperation between it, sector departments and the District Municipality. The municipality is both a water service authority and a water service provider. The Department of Water and Sanitation assists with the building of reservoirs and pump stations.

The Addo Elephant National Park and Shamwari Game Reserve are situated within SRVM, and they constitute our international tourism destination and attraction. Tourism and Agriculture are our strong sectors that contribute immensely to our economy and employment opportunities. Citrus produces almost 50% of employment in our area.

The valley is characterised by harsh climate conditions, with summer temperatures rising more than 40°C. Rainfall is spread over the year and is between 250-500mm per annum. The valley is characterised by wide, fertile flood plains and is associated with low-lying land and steep, less fertile soil. The area outside the Sundays River includes the Paterson area, the coastal belt, and the west of Alexandria.

## Demographic Information

|  | 2022 | 2016 | 2011 |
| --- | --- | --- | --- |
| Population | 53 256 | 59 793 | 54 504 |
| Age Structure |  |  |  |
| Population under 15 | 24.1% | 29.1% | 26.7% |
| Population 15 to 64 | 70.3% | 66.5% | 68.0% |
| Population over 65 | 5.6% | 4.3% | 5.2% |

### SOCIO ECONOMIC STATUS

| Household Dynamics |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Households |  |  |  |  | 19 017 | 17 221 | 14 749 |
| Average household size |  |  |  |  | 2.8 | 3.5 | 3.7 |
| Female headed households |  |  |  |  | n/a | 34.8% | 34.9% |
| Formal dwellings |  |  |  |  | 87.8% | 84.2% | 84.6% |
| Housing owned |  |  |  |  | n/a | 30.5% | 44.3% |
| Household Services |  |  |  |  |  |  |  |
| Flush toilet connected to sewerage |  |  |  |  | 81.5% | 65.0% | 58.7% |
| Weekly refuse removal |  |  |  |  | 77.1% | 61.6% | 61.2% |
| Piped water inside dwelling |  |  |  |  | 55.3% | 30.9% | 32.3% |
| Electricity for lighting |  |  |  |  | 94.4% | 89.6% | 79.8% |
| Major Natural Resources |  |  | Relevance to Community |  |  |  |  |
| Sand |  |  | It is used in housing construction and local brick manufacturing. Cooperatives Manufacture bricks using local sand. Paterson sand mining is identified in the IDP’s ward priorities as one of the catalytic projects that need assistance for resource mobilization. |  |  |  |  |
| Forests |  |  | Forests are used as grazing lands, and they present economic growth potential for game/livestock business initiatives. |  |  |  |  |
| National Park |  |  | Ecotourism opportunities, conservation, and employment. |  |  |  |  |
| Enon-Bersheba communal land |  |  | It is readily available as the source of economic activity for the benefit of the whole community. Business plans for citrus, food security, vegetable production, games are readily available for sourcing development funding. |  |  |  |  |
| Water |  |  | Canals for irrigation and domestic use. Canals for irrigation and domestic use. |  |  |  |  |

### SERVICE DELIVERY OVERVIEW

Services such as water, sanitation, electricity, road maintenance and community services are rendered by Sundays River Municipality. Services such as Environmental Health and Fire Services are rendered on an agency basis for Sara Baartman District Municipality. Service delivery overview is illustrated under the Municipal Manager’s executive summary.

### FINANCIAL HEALTH OVERVIEW

See notes on Annual Financial Statements

### ORGANISATIONAL DEVELOPMENT OVERVIEW

The organizational structure was approved in 2022 and reviewed in 2024/25 to be adopted and approved by the Council in 2025

IDP and Budget was approved on the 31 May 2023.

The approved staff complement for the Municipality is currently 308.

There are currently 269 filled positions which include 5 section 56 positions and 39 vacant       posts still to be filled. There are unfunded vacant posts due to financial constraints as well as high personnel costs. Moratorium placed on the filling of vacant post until the finalization of the review process of the organogram.

SBDM is assisting the municipality with job evaluations and currently the municipality  is busy designing job descriptions of all employees of Sundays River. The job descriptions are available, but they are all undergoing a process of review.

The Constitution (Chapter 7, section 152(1) and (2) as well as Section 153 (a) and (b) obliges and outlines the functions and services that are to be performed by local government. The Sundays River Valley Municipality (SRVM) obtains these functions through either allocation by legislative framework, Authorization by Minister of Provincial and Local Government or adjustment by the Provincial MEC for local government.

### AUDITOR GENERAL REPORT

2024/2025 Disclaimer NB: Attached AG Report.

### STATUTORY ANNUAL REPORT PROCESS

| No. | Activity | Time |
| --- | --- | --- |
| 1 | Consideration of next financial year’s Budget and IDP process plan. Except for the legislative content, the process plan should confirm in-year reporting formats to ensure that reporting and monitoring feeds seamlessly into the Annual Report process at the end of the Budget/IDP implementation period | July |
| 2 | Implementation and monitoring of approved Budget and IDP commences (In-year financial reporting). |  |
| 3 | Finalise the 4th quarter Report for the previous fiscal year |  |
| 4 | Submit draft year 0 Annual Report to Internal Audit and Auditor-General |  |
| 5 | Municipal entities submit draft annual reports to MM |  |
| 6 | Audit/Performance committee considers draft Annual Report of municipality and entities (where relevant) | August |
| 8 | Mayor tables the unaudited Annual Report |  |
| 9 | Municipality submits draft Annual Report including consolidated annual financial statements and performance report to Auditor General |  |
| 10 | Annual Performance Report as submitted to Auditor General to be provided as input to the IDP Analysis Phase |  |
| 11 | Auditor General audits Annual Report including consolidated Annual Financial Statements and Performance data | September - October |
| 12 | Municipalities receive and start to address the Auditor General’s comments | November |
| 13 | Mayor tables Annual Report and audited Financial Statements to Council complete with the Auditor- General’s Report |  |
| 14 | Audited Annual Report is made public, and representation is invited |  |
| 15 | Oversight Committee assesses Annual Report |  |
| 16 | Council adopts Oversight report | December |
| 17 | Oversight report is made public |  |
| 18 | Oversight report is submitted to relevant provincial councils |  |
| 19 | Commencement of draft Budget/ IDP finalization for next fiscal year. Annual Report and Oversight Reports to be used as input | January |

COMMENT ON THE ANNUAL REPORT PROCESS:

It is very important to adhere to the rules of Cogta and provincial government to meet the deadline and it makes it easier to prepare for year ahead because I will have a lot of information in my disposal to feed the Draft IDP.

# CHAPTER 2 – GOVERNANCE

INTRODUCTION TO GOVERNANCE

Circular 63 of the Municipal Finance Management Act (MFMA) states that good governance and public participation must “ensure accountability and government arrangements are in place. The municipal political and administrative structures have partially or fully applied the following nine major characteristics to ensure good governance:

- Participation

- Rule of Law

- Transparency

- Responsiveness

- Consensus Oriented

- Equity and inclusiveness

- Effectiveness and Efficiency

- Accountability

- Sustainability

## COMPONENT A:  POLITICAL AND ADMINISTRATIVE GOVERNANCE

### POLITICAL GOVERNANCE

The Municipal Systems Acts (MSA), section 4 (2) states that a municipal council must, within the municipality’s financial and administrative capacity and have regard for practical considerations,

- Exercise the municipality’s executive and legislative authority and use the resources of the municipality in the best interests of the community.

- Provide, without favor or prejudice, democratic and accountable government.

- Encourage the involvement of the community.

- Strive to ensure that municipal services are provided to the community in a financially and environmentally sustainable manner.

- Consult the community about the level, quality, range and impact of municipal services and the available options for service delivery.

- Give members of the community equitable access to the municipal services to which they are entitled.

- Promote and undertake development in the municipality.

- Promote gender equity in the exercise of the municipality’s executive and legislative authority.

- Promote a safe and healthy environment in the municipality; and

- Contribute together with other organs of state to the progressive realisation of the fundamental rights contained in sections 24, 25, 26, 27 and 29 of the Constitution.

The following additional executive obligations are imposed on every municipal council. A council must review annually.

- The needs of the community

- It is a priority to meet those needs.

- Its processes for involving the community.

- It’s Organisational and delivery mechanisms for meeting those needs.

- Its overall performance in achieving the objects of local government set out in the Constitution.

Mayor: S. Lucas                             Speaker: S. Nodonti                        Cllr: P .N .Ncambele

Cllr:  K. Smith                                          Cllr: M. Payi                                     Cllr: L.E .Baka

Cllr: M. Bosman	         Cllr: B. Dyantyi		          Cllr: X .J .J. Jonas

Cllr: N. Langbooi	       Cllr: A. Ndawo			    Cllr: Z .Qusheka

Cllr: N. Baxana                              Cllr: H. Hendricks                        Cllr: H. Jagers

Cllr: H. Bayini

| COUNCIL AS AT 30 JUNE 2024-2025 JUNE |  |  |  |
| --- | --- | --- | --- |
| NAME OF COUNCILLOR | CAPACITY | PARTY | WARD |
| MC PAYI | CLLR | ANC | WARD 1 |
| N LANGBOOI | CLLR | ANC | WARD 2 |
| X JONAS | CLLR | ANC | WARD 3 |
| LE BAKA | CLLR | ANC | WARD 4 |
| Z QUSHEKA | CLLR | ANC | WARD 5 |
| N BAXANA | CLLR | ANC | WARD 6 |
| AM NDAWO | CLLR | DA | WARD 7 |
| N NCAMBELE | CLLR | ANC | WARD 8 |

| PROPORTIONAL REPRESENTATIVES |  |  |  |
| --- | --- | --- | --- |
| K SMITH | CLLR | DA |  |
| B DYANTYI | CLLR | EFF |  |
| H JAGER | CLLR | ANC |  |
| H HENDRICKS | CLLR | GOOD |  |
| S NODONTI | CLLR | ANC |  |
| M BOSMAN | CLLR | DA |  |
| H BAYENI | CLLR | DA |  |
| S LUCAS | MAYOR | ANC |  |

POLITICAL DECISION-TAKING

| COUNCIL RESOLUTIONS 31 JULY 2024 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION |  | DATE OF COMPLETION |
| 1 | 5.1 | SECTION 52(D) REPORT FOR PERIOD ENDING 30 JUNE 2024 COUNCIL RESOLVED: That the Council take note of the Section 52 report for the period ending June 2024. | Chief Financial Officer | Section 52(d) report NOTED |  | 31 JULY 2024 |
| 2 | 6.1 | REVIEWAL OF THE ORGANISATIONAL STRUCTURE OF SUNDAYS RIVER VALLEY MUNICIPALITY COUNCIL RESOLVED: - That the item be referred to Management to follow proper processes of the reviewal of the Organisational Structure. - That the item be tabled to Council with clear recommendations. | Director: Corporate Services | Organogram was approved by Council on 07 March 2025. |  | 07 March 2025 |
| 3 | 6.2 | CHINA INTERNATIONAL IMPORT EXPO (05 NOVEMBER 2024 – 10 NOVEMBER 2024) COUNCIL RESOLVED: - That the item be deferred to allow management to investigate accurate costs of the trip. - That the Municipal Manager after costing the trip advised the Council if there are funds to cover the costs or not. | MM | Costing was done and Mayor undertook the trip. |  | Item 8.4 of the 30 August 2024 agenda. Completed |
| COUNCIL RESOLUTIONS 30 AUGUST 2024 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 4 | 5.1 | SUBMISSION OF ANNUAL FINANCIAL STATEMENTS 2023/2024 COUNCIL RESOLVED - The AFS 2023/2024 be reviewed to implement the inputs from the Audit Committee, Internal Audit and other Stakeholders and updated accordingly before submission to the Auditor-General (AG). - Management properly files the POE for audit purposes; and, - The draft ANNUAL FINANCIAL STATEMENTS (AFS) 2023/2024 is submitted to Auditor-General on the 31 August 2024. | MM | Submission of Annual Financial Statements 2023/2024 financial year to the office of the Auditor General. | 31 AUGUST 2024 |  |
| 5 | 5.2 | DRAFT ANNUAL REPORT 2023-2024 COUNCIL RESOLVED - Council notes the progress on the draft Annual Report for 2023/2024; and, - The first draft Annual Report 2023/2024 is submitted to the Auditor-General on the 31st of August 2024. | MM | Submission of the Draft Annual Report 2023/2024 financial year to the office of the Auditor General. | 31 AUGUST 2024 |  |
| 6 | 5.3 | ANNUAL PERFORMANCE REPORT 2023-2024 FINANCIAL YEAR COUNCIL RESOLVED - That the council take note of the Annual Performance Report for 2023/2024 financial year. - Council takes note of the Annual performance report that will be submitted to AG with AFS by the 30st of August 2024. | MM | Submission of Annual Performance Report 2023/2024 financial year to the office of the Auditor General. | 31 AUGUST 2024 |  |
| 7 | 5.4 | IDP / BUDGET PROCESS PLAN FOR 2025/2026 FINANCIAL YEAR COUNCIL RESOLVED: - That the council APPROVE the IDP/BUDGET PROCESS PLAN for 2025/2026 financial year. - That the IDP/BUDGET PROCESS PLAN for 2025/2026 is approved with amendments. | Chief Financial Officer Office of MM | IDP/BUDGET Process Plan 2025/2026 Approved by the Council | 30 AUGUST 2024 |  |
| 8 | 5.5 | DRAFT PROPOSED SDBIP 2024/2025 FINANCIAL YEAR #### COUNCIL RESOLVED - The Council consider and approve the draft SDBIP 2024/2025 Financial Year. - That Council approve the performance Agreements for 2024-2025 Financial year. | Office of MM | SDBIP 2024/2025 approved by the Council | 30 AUGUST 2024 |  |
| 9 | 6.1 | REPORT FROM THE AUDIT, PERFORMANCE AND RISK COMMITTEE COUNCIL RESOLVED - That the Council adopts and accept the recommendations of the Audit, Performance and Risk Committee. - That the Management implement the recommendations of the Audit, Performance and Risk Committee Risk Committee. | MM/ CAE | APRC recommendations adopted by Council | 30 AUGUST 2024 |  |
| 10 | 7.1 | REPORT FROM THE MUNICIPAL PUBLIC ACCOUNTS COMMITTEE COUNCIL RESOLVED: - That amount of R3 921 554.87 be written off by Council - That the progress be made in terms of finalising paperwork and further investigation for other transactions (the amount of R11 601 260.40, R742 545. 09 and R10 232 622. 62). - The Council adopt the investigation and decision made by the MPAC on the irregular expenditure 2022/23 | MPAC | Council Approved to write off R3 921 554.87 | 30 AUGUST 2024 |  |
| 11 | 8.1 | FURTHER EXTENSION OF THE VALIDITY OF THE GENERAL VALUATION ROLL COUNCIL RESOLVED That the Council approve the extension of the validity of the current valuation roll in terms of Section 32 (1)(b)(ii) of the MPRA (Local Government: Municipal Property Rates Act, as amended, 2014) to 30 June 2026 to allow billing up to 30 June 2026. | CFO | Validity of the General Valuation Roll extended by the Council. | 30 AUGUST 2024 |  |
| 12 | 8.2 | VAT ACCOUNTING CORRECTION FOR ANNUAL FINANCIAL STATEMENTS The Municipal Manager withdrew the report from the agenda. | CFO | Item withdrawn | 30 AUGUST 2024 |  |
| 13 | 8.3 | WORKMAN’S COMPENSATION FOR OCCUPATIONAL INJURIES AND DISEASES ACT (COIDA) COUNCIL RESOLVED That the Council take note of the additional liability in the 2023/24 Annual Financial Statements of the amount of R2,206,859.25 | CFO | Council acknowledged debt and a payment arrangement to be made between CFO and DoEL Compensation Commission. | 30 AUGUST 2024 |  |
| 14 | 8.4 | OPPORTUNITIES FOR COOPERATION BETWEEN CHINA AND SOUTH AFRICA: COLLABORATIVE CONSTRUCTION OF DEVELOPMENT SYSTEM LEVERAGING THE COMPLEMENTARY ADVANTAGES OF "SUNDAY’S RIVER MUNICIPALITY" AND "SCO MULTIFUNCTIONAL ECONOMIC AND TRADE PLATFORM URBAN DEVELOPMENT AND COOPERATION COMMITTEE" COUNCIL RESOLVED That the Council approve the travel of 1 representative (Mayor) to China in November 2024 as detailed in the itinerary with the business activities. | MM/ Speaker | Approved travelling of the Mayor to China in November 2024 | 30 AUGUST 2024 |  |
| COUNCIL RESOLUTIONS 27 SEPTEMBER 2024 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT/OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 15 | 14.1 | AUDIT COMMITTEE REPORT TO COUNCIL - QUARTER 4 2023/2024 COUNCIL RESOLVED: - That the Council accept and adopt the recommendations of the Audit Performance & Risk Committee. - That Management be committed to the implementation of the Audit, Performance & Risk Committee. | MM | Implementation of Audit Committee resolutions is closely monitored by the office of the Municipal Manager | On going task |  |
| 16 | 15.1 | DEPARTMENT OF WATER AND SANITATION DEBT COUNCIL RESOLVED - That the Council notes the impact of the repayment on both Council and the Administration. - (b) That expenses must be reprioritized for the sake of the available cash flow in the next adjustment budget and that absolute value addition to the institution will be the criteria in limiting expenses. Nice to have will not be considered. | MM and CFO | A payment arrangement has been made, and payment is being accordingly. | Work in progress |  |
| COUNCIL RESOLUTIONS 01 OCTOBER 2024 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / PERSON | ACTION | DATE OF COMPLETION |  |
| 17 | 12.1 | MOTION FROM THE DEMOCRATIC ALLIANCE ON TENDERING PROCESSES COUNCIL RESOLVED: The Council take note of the Motion from the Democratic Alliance on Tendering Processes. | COUNCIL | Motion was noted by the Council. | 01 October 2024 |  |
|  | 12.2 | MOTION FROM THE DEMOCRATIC ALLIANCE ON SERVICE DELEVERY AND RESPONSE TIME TO SERVICE DELIVER COMPLAINTS COUNCIL RESOLVED: The Council take note of the Motion from the Democratic Alliance on Service Delivery and response time to Service Deliver Complaints. | COUNCIL | Motion was noted by the Council. |  |  |
| 18 | 13 13.1 | REPORT FROM THE MUNICIPAL PUBLIC ACCOUNTS COMMITTEE UNAUTHORIZED, IRREGULAR, FRUITLESS AND WASTEFUL EXPENDITURE COUNCIL RESOLVED - That the Council note that the MPAC could not continue with an investigation on irregular and wasteful expenditure 2023/2024. - That Management assist the Committee with necessary support and documentation. | MPAC Chairperson | Work in progress Investigations are being conducted on the UIF & W MPAC meetings were held on 10 & 12 March 2025 to investigate the UIF & W | Work in Progress |  |
| 19 | 14 | REPORT ON THE AUDIT ACTION PLAN PROGRESS REPORT AS AT QUARTER 4 2023/2024 COUNCIL RESOLVED That the Council note the progress made on the implementation of audit action plan 2023/2024. | MM | Audit Action Plan was noted by Council. | Standing Item |  |
| 20 | 16.2 | CALENDAR OF DATES FOR 2024/2025 FINANCIAL YEAR COUNCIL RESOLVED That Council approves the calendar of dates for 2024/2025, attached to the report as Annexure E. | Director: Corporate Services | Council Institutional Calendar was approved | Completed 01 October 2024 |  |
| 21 | 16.3 | RECRUITMENT REPORT 01 JULY 2023 – 30 JUNE 2024 COUNCIL RESOLVED That Council notes the recruitment report with amendments. | Director: Corporate Services | The Recruitment Report was presented to Council and noted. | 01 October 2024 |  |
| 22 | 16.4 | UPDATE ON JOB EVALUATION PROCESS COUNCIL RESOLVED That Council note an update report on Job Evaluation Process | Director: Corporate Services | Meeting noted report | 01 October 2024 |  |
| 23 | 16.5 | REVIEWAL OF THE ORGANISATIONAL STRUCTURE OF SUNDAYS RIVER VALLEY MUNICIPALITY COUNCIL RESOLVED - That the item be deferred pending Local Labour Processes. - That a Local Labour Forum be convened to discuss the Organizational Structure - That the item be deferred to a Special Council that will be held on 11 October 2024. | Director: Corporate Services | Council approved the Organogram at a Special Council meeting held on 07 March 2025 | 07 March 2025 |  |
| 24 | 16.6 | REPORT ON LIFTING OF MORATORIUM ON FILLING OF VACANT POSITIONS COUNCIL RESOLVED - That the item be deferred. - That the item be deferred to a Special Council that will be held on 11 October 2024. | Director: Corporate Services | Item resolved in the Council meeting held 11 October 2024 | 11 October 2024 |  |
| 25 | 16.7 | 2024/25 SRVM CAPITAL PROGRAMME UPDATE COUNCIL RESOLVED That the Council take note of the 2024/25 SRVM Capital Programme Update. | Director: IPD | The SRVM Capital Projects were presented and noted. | 01 October 2024 |  |
| 26 | 16.8 | FORMATION OF MUNICIPAL HOUSING BENEFICIARY ALLOCATIONS COMMITTEE COUNCIL RESOLVED - That council notes and approves the formation of the Municipal Housing Beneficiary Allocations Committee. - That councillors do not form part of the committee to maintain neutrality in the event of appeals. - That council periodically oversees the work of the committee to ensure accountability and transparency in the allocation process. | Director: IPD |  |  |  |
| 27 | 16.9 | ROADS REHABILITATION PLAN FOR SUNDAYS RIVER VALLEY MUNICIPALITY KIRKWOOD/TOWN COUNCIL RESOLVED That the Council approves the proposed plan. | Director: IDP |  |  |  |
| 28 | 16.10 | REPORT ON APPLICATION FOR VACANT FARMLAND FOR GRASING BY MOSES MABIDA LIVESTOCK FARMERS: (REF: 7/1/R) COUNCIL RESOLVED That Council approves the application for leasing the properties as set out above to the Moses Mabida Livestock Farmers, subject to: - Council may use the flat area for a cemetery in the future. - Council determines the period for the lease and the charges, if any. - Moses Mabida Livestock Farmers are responsible for maintaining the fences and gates. - Moses Mabida Livestock Farmers are responsible for the operation cost for the daily running of the property and water for their animals. | MM and Director Community Services | Resolution implemented | Completed |  |
| 29 | 16.11 | DEPARTMENT OF WATER AND SANITATION DEBT COUNCIL RESOLVED - That the Council notes the impact of the repayment on both Council and the Administration. - (b) That expenses must be reprioritized for the sake of the available cash flow in the next adjustment budget - (c ) That absolute value addition to the institution will be the criteria in limiting expenses. Nice to have will not be considered. | MM and CFO | A payment arrangement has been made and payment is being made. | Work in progress |  |
| 30 | 16.12 | 2024/25 SRVM CAPITAL PROGRAMME UPDATE – REQUESTING APPROVAL FOR BUDGET MAINTENANCE FUNDING COUNCIL RESOLVED - That council approves the request for additional funding and acknowledges the budget increase on the Project. - That the said additional funds will enable refurbishment of the Ponds, to receive the effluent. - That council approve the submission of the Additional funding request to the Department of Cooperative Governance and Traditional Affairs (COGTA) | Director: IPD | Capital Projects were presented and approved by Council. | 01 October 2024 |  |
| COUNCIL RESOLUTIONS 11 OCTOBER 2024 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT/OFFICICAL | ACTION | DATE OF COMPLETION |  |
| 31 | 5.1 | REVIEWAL OF THE ORGANISATIONAL STRUCTURE OF SUNDAYS RIVER VALLEY MUNICIPALITY COUNCIL RESOLVED - That the item be deferred back for proper consultation. - That Local Labour Forum be convened on 17 October 2024 to discuss the review of the Organisational Structure. | Director: Corporate Services | The Item was deferred back for further consultations with Labour and consultations are underway. | Completed on 07 March 2025 |  |
| 32 | 6.1 | REPORT ON UPLIFTING OF MORATORIUM ON FILLING OF VACANT POSITIONS THE COUNCIL RESOLVED That THE Council uplift of the moratorium on filling of FOLLOWING POSITIONS: - Strategic Manager – Office of the Municipal Manager - Manager: PMU - Directorate: Infrastructure - Manager: Roads and Stormwater - Directorate: Infrastructure - Supervisor: Water & Sanitation - Directorate: Infrastructure - Caretakers – Directorate: Community Services - Examiner/Officers – Directorate: Community Services - Replacement of post of General Workers - That Council approve the upliftment of the moratorium on the filling of funded vacant posts that adversely affect service delivery. | Director: Corporate Services | Strategic Manager – Appointment done Manager: PMU – advertised Supervisor: W & S – advertised Caretakers – advertised Traffic officers/Examiners advertised General Workers – advertised | Partially implemented. |  |
| 33 | 6.2 | FORMULAE FOR DETERMINATION OF THE NUMBER OF COUNCILLORS OF MUNICIPAL COUNCILS COUNCIL RESOLVED That Council take note of Government Gazette Nr 51331 dated 02 October 2024. | CFO and Director: Corporate Services | Gazette presented to Council and was noted for implementation. | Completed |  |
| COUNCIL RESOLUTIONS 23 OCTOBER 2024 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT/OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 34 | 4.1 | DETERMINATION OF UPPER LIMITS OF THE SALARIES, ALLOWANCES AND BENEFITS OF DIFFERENT MEMBERS OF MUNICIPAL COUNCILS COUNCIL RESOLVED That Gazette 51407 being implemented backdated from the day of date 1st of July 2023 for the following councillor positions’ 1. Eleven ordinary part-time Councillors 2. One Part-time MPAC Chair 3. Two full-time Exco members 4. One full-time Speaker 5. One full-time Mayor | CFO and Director: Corporate Services | Gazette noted and to be implemented. MEC Submission to be made | Completed |  |
| COUNCIL RESOLUTIONS 30 OCTOBER 2024 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT/OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 35 | 4.1 | SECTION 52(D) REPORT FOR PERIOD ENDING 30 SEPTEMBER 2024 COUNCIL RESOLVED That the content of the first quarter financial report of 2024/25 financial year on the implementation status of the budget of the municipality be noted. | MAYOR | Section 52(d) report NOTED | 30 OCTOBER 2024 |  |
| 36 | 5.1 | MANAGEMENT OF BAD DEBT WRITE-OFFS COUNCIL RESOLVED That the Council's approve the write offs reflecting in annexure B to D A. Write-off as an incentive for settling outstanding accounts: - Interest write-offs as an incentive for settling outstanding accounts - - Bad debt write-offs totalling related to agricultural assessment rates as per the Council resolutions - Annexure A - R 2,255,673.30 B. Indigent write offs. 1. Indigent write-offs totalling R1,307,768.00 in terms of the applicable policy. Annexure B C. Correction of Interest Levied on Outstanding Government accounts. - An investigation revealed incorrect interest levied on government accounts. - Annexures C, (1) R 5,270.85, (2) R 494,474.53, (3) R 235,001.45. Annexure D R 763,029.94 | CFO | Council Approved and amended Council resolution. | 30 OCTOBER 2024 |  |
| 37 | 5.2 | REPORT FOR POCKETS OF LAND IN SRVM COUNCIL RESOLVED That the report be deferred for thorough investigation | Director IPD | Item in the agenda 11 December 2024 | Outstanding |  |
| COUNCIL RESOLUTIONS 11 DECEMBER 2024 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT/OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 38 | 16.1 | FIRST QUARTER PERFORMANCE REPORT 2024/2025 COUNCIL RESOLVED That Council take note of the First quarter Performance report for 2024. | Council | Council took note of the 1st Quarter Performance report for 2024/2025 FY | Complete |  |
| 39 | 16.2 | SUNDAYS RIVER VALLEY MUNICIPALITY REPORTING ON FRAUD PREVENTION POLICY COUNCIL RESOLVED - That Council approve the Fraud Prevention Policy/ Plan attached to the report as Annexure E. - That the Plan includes Terms of Reference and composition of Ethics Committee. - That a workshop be conducted on the plan. | Council Municipal Manager / Director Corporate Services/ Chief Audit executive | Policy was approved Workshop still outstanding | Work in progress |  |
| 40 | 16.3 | SUNDAYS RIVER VALLEY LOCAL MUNICIPALITY BLUE, GREEN AND NO DROP COMPLIANCE (2022/23) COUNCIL RESOLVED That Council SUPPORT the implementation of the Green, Blue and No drops requirements in Sundays River Valley Municipality. | Council | Council supported the implementation of the Green, Blue and No drops requirements in the municipality. IPD to implement. | 11 December 2024 |  |
| 41 | 16.4 | REPORT ON APPLICATION FOR WAYLEAVE APPLICATION TO INSTALL TELECOMMUNICATIONS SERVICES (FIBRE) WITHIN SUNDAYS RIVER VALLEY LOCAL MUNICIPALITY (VALENCIA & NOMATHAMSANQA) COUNCIL RESOLVED # That Council approve the wayleave application for the installation of Fiber services in order to improve telecommunication services within Nomathamsanqa and Valencia. | Council | Council approved the wayleave application. | 11 December 2024 |  |
| 42 | 16.5 | COUNCIL ITEM FOR POCKETS OF LAND IN SUNDAYS RIVER VALLEY MUNICIPALITY COUNCIL RESOLVED That Council the item be deferred to the next Council meeting. | Council | Item deferred |  |  |
| 43 | 16.6 | DRAFT INTEGRATED WASTE MANAGEMENT PLAN COUNCIL RESOLVED That the Council: - Note the Report. - Approve the Proposed IWMP Goals and Objectives. - Support Stakeholder Engagement. - Allocate Resources for Implementation. | Council Director Community Services | Council approved the Draft Integrated waste Management Plan | 11 December 2024 |  |
| 44 | 16.7 | INTERNATIONAL PARTNERSHIP WITH FALKENBERG MUNICIPALITY - PROGRESS REPORT COUNCIL RESOLVED That Council note the progress report on International Partnership with Falkenberg Municipality. | Council | Council took note of the report. | Partnership is an ongoing project. |  |
| 45 | 16.8 | REPORT ON STANDARD DRAFT BY-LAW FOR TOWNSHIP ECONOMIES COUNCIL RESOLVED - That the Council adopt the standards draft by-law for township Economies as is. - That a workshop be arranged to get inputs from relevant stakeholders in customizing the by-law to suite the local conditions. | Director Community Services Director Corporate Services | Draft Bylaw adopted by the Council | 11 December 2024 |  |
| 46 | 16.9 | APPLICATION BY BORN FREE FOUNDATION TO LEASE ERF 754 MORESON, PATERSON COUNCIL RESOLVED - That the item be deferred to the office of the Ward Councilor to consult with Shamwari, Born Free Foundation (b)That Public consultation be conducted. | MM Ward 4 Councillor | Item was deferred. | Item tabled to the Council on 28 February 2025. Item was approved. |  |
| COUNCIL RESOLUTIONS 24 JANUARY 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 47 | 4.1 | STATUS OF THE EMPLOYMENT CONTRACTS FOR MANAGERS DIRECTLY ACCOUNTABLE TO MUNICIPAL MANAGER AS PER GOVERNMENT GAZETTE NO. 46740 COUNCIL RESOLVED: - The Council notes the Government Gazette read with the COGTA Circular No. 24 of 2022. - The Council notes the amendments in the Municipal Systems Act, Act 32 of 2000 and the position to be made permanent in line with the above amendment on the appointment of managers directly accountable to the municipal manager. - The detailed Recruitment Process Plan to be presented and approved by Council and an advertisement to be placed in the national and regional newspapers for this critical position. | Council Municipal Manager / Director Corporate Services | The position of Director: IPD was advertised in National and Regional newspapers. The position was advertised as a permanent appointment. | Completed |  |
| COUNCIL RESOLUTIONS 31 JANUARY 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 48 | 5.1 | SRVM 2023-2024 AUDIT OPINION COUNCIL RESOLVED That the Council accept the Audit report and noted audit findings. That the Audit Action Plan be developed to deal with the audit findings of the 2023-2024 financial year. | Council Municipal Manager | Audit Action Plan updated to include 2023- 2024 financial year. The Municipal manager is monitoring implementation of the Audit Action Plan | In progress |  |
| 49 | 5.2 | SECTION 52(D) REPORT AND SECTION 72 REPORT FOR PERIOD ENDING 31 DECEMBER 2024 COUNCIL RESOLVED - That the section 52(d) ending September 2024, 1st quarter results as required by the Section 52(d) of the MFMA be noted - That the report of the financial results for month ending December 2024, 2nd quarter results as required by s52(d) and the mid-year results as required by s72 of the Municipal Finance Management Act be noted. - That the 2024-2025 operating budget be adjusted based on the revenue and expenditure patterns contained in this report. - That the SDBIP also be adjusted accordingly and that the adjusted budget be implemented in accordance with the adjusted SDBIP. - That the adjustment budget be submitted to Council before the end of February 2025. - That identified cases of Unauthorised, Irregular, Fruitless and Wasteful Expenditure as of 31 December 2024 is noted by Council and be submitted to MPAC for investigation as per Section 32. | Council Chief Financial Officer Municipal Manager | Reports were noted by Council. Budget was adjusted and Adjustment Budget was tabled and approved by Council on 28 February 2025. Adjusted SDBIP was also tabled on 28 February 2025. Unauthorised, Irregular, Fruitless and Wasteful Expenditure as of 31 December 2024 was referred to MPAC for further investigation | 28 February 2025 Ongoing |  |
| 50 | 5.3 | MIDTERM PERFORMANCE REPORT 2023-2024 FINANCIAL YEAR COUNCIL RESOLVED That the Council take note of the Midterm performance report for 2024 – 2025 financial year. | Council | NOTED | 31 January 2025 |  |
| 51 | 5.4 | DRAFT ANNUAL REPORT 2023-2024 COUNCIL RESOLVED - That the council approve the draft annual report 2023-2024 for public comment. - That council refer the draft annual report to MPAC for oversight. - That copies of the approved draft annual report be advertised and be made available in all municipal facilities including the municipal website for public access and comments. - That the comments and recommendations of the Audit Committee be included in the draft. | Council Municipal Manager | Resolution was executed Copies of draft annual report was made available at all Libraries and other municipal facilities. Draft Annual report was presented to MPAC on 10 March 2025 | 31 January 2025 |  |
| 52 | 6.1 | AUDIT, PERFORMANCE AND RISK COMMITTEE REPORT QUARTER 1 & 2 2024/25 FY COUNCIL RESOLVED - That Council note the report of Audit, Performance and Risk Committee for Quarter 1 & 2 2024/25 FY attached to the report as Annexure D. - That the Council adopts recommendations of the Audit, Performance and Risk Committee on Quarter 1 & 2 2024/25 FY | Council Municipal Manager | ARC recommendations were adopted by the Council. | 31 March 2025 |  |
| 53 | 7.1 | AUDIT ACTION PLAN COUNCIL RESOLVED That the implementation of the Audit Action Plan is noted. | COUNCIL | Audit Action Plan noted by the Council | 31 January 2025 |  |
| 54 | 7.2 | REPORT ON SAND MINING PROJECT IN PATERSON COUNCIL RESOLVED That the Council approves CDA to conduct a feasibility study on the Sand Mining in Paterson. | Council Municipal Manager |  |  |  |
| 55 | 7.3 | APPLICATION FROM SINETHEMBA DEVELOPMENT PRIMARY COOPERATIVE TO LEASE ERF 115 PATERSON COUNCIL RESOLVED: a) That Council approves leasing the commonage land portion of remainder ERF115 to the Sinethemba Development Primary Cooperative for a period of 5years at no fee due to the indigent nature of the applicants. b) That on approval of the lease agreement by Council, a lease agreement be entered into between SRVM and Sinethemba Development Primary Cooperative. | Council Municipal Manager and Director: Corporate Services | Approved by the Council | 31 January 2025 |  |
| 56 | 7.4 | REQUEST FOR EPWP RATE INCREASEMENT COUNCIL RESOLVED: That the council Approve increase of the EPWP rate from R200-R230. | Council Municipal Manager and Director: Infrastructure | EPWP rate increase Approved | 31 January 2025 |  |
| 57 | 7.5 | 2024/25 SRVM CAPITAL PROGRAMME UPDATE COUNCIL RESOLVED That the update report on Capital Program be noted. | Council | Report was noted by Council. | 31 January 2025 |  |
| COUNCIL RESOLUTIONS 10 FEBRUARY 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 58 | 4.1 | RECRUITMENT PROCESS FOR THE FILLING OF THE POSITION OF DIRECTOR: IPD COUNCIL RESOLVED - That the approved panel consist of the following members: - The Municipal Manager as the Chairperson of the panel. - Sarah Baartman District Municipal Manager. - Portfolio Head of Infrastructure Planning & Development (IPD). - An expert in the Engineering Field or Professional Engineer from SALGA - An Engineer from Sarah Baartman District Municipality. - A letter of invitation to be extended to the institution by the Municipal Manager, upon Council approving the selection panel. | Municipal Manager | Members of the Panel were all informed in writing of the Council resolution. | 10 February 2025 |  |
| COUNCIL RESOLUTIONS 17 FEBRUARY 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 59 | 4.1 | REQUEST FOR DONATION FROM XHOTHOVA & TYAMKA TRADITIONAL CREW COUNCIL RESOLVED - That the Council adopt the Annual Xhothova & Tyamka Traditional Event. - That the Council approves budget provision for the event in the adjustment budget of February 2025. - That the Annual Xhothova & Tyamka Traditional Event be budgeted for annually. | Council Municipal Manager Chief Financial Officer | Donation approved Accommodated in the Adjustment Budget | 17 February 2025 28 February 2025 |  |
| COUNCIL RESOLUTIONS 28 FEBRUARY 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 60 | 4.1 | ADJUSTMENT BUDGET 2024/25 COUNCIL RESOLVED - The total operating revenue including capital transfers of R339,642m approved by Council in out in Table 1 of the 2024/25 Main Adjustment Budget Report. - The operating expenditure of R247,765m approved by Council in Table 2 of the 2024/25 Main Adjustments Budget Report. - The capital budget expenditure of R63,473m approved by Council in Table 3 of the 2024/25 Main Adjustments Budget Report. - Council takes note that no taxes and tariffs are affected with the approval of this adjustments budget. - Schedules B1 to B10 attached as Appendix to the 2024/25 Main Adjustments Budget Report be approved by Council - That Council approves the correction of unauthorized expenditure incurred during the year as legislated through the adjustment budget. | Council Municipal Manager and Chief Financial Officer | Adjustments were made to the budget and approved by Council. | 28 February 2025 |  |
| 61 | 4.2 | ADJUSTED SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP) 2024/25 COUNCIL RESOLVED That Council note and adopt the adjusted or amended SDBIP 2024/2025 Financial Year. | Council Municipal Manager | Council noted adjustments | 28 February 2025 |  |
| 62 | 5.1 | AUDIT COMMITTEE REPORT ON ADJUSTMENT BUDGET 2024/ 25 AND ADJUSTED SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP) 2024/25 COUNCIL RESOLVED - To note the concerns of the committee regarding the adjusted SDBIP 2024/25 presented to the Audit Committee. - That a reviewed updated adjusted SDBIP 2024/25 be resubmitted to the committee. | Council Municipal Manager | Council noted concerns of the ARC | 28 February 2028 |  |
| 63 | 6.1 | 2024/25 SRVM CAPITAL PROGRAMME UPDATE COUNCIL RESOLVED - That Council approve and acknowledge the variance in the Project due to the refurbishment of the Ponds, so they can receive the effluent. - That Council Note the progress in the capital projects | Council Municipal Manager | Variance approved by the Council. | 28 February 2025 |  |
| 64 | 6.2 | REPORT TO REQUEST COUNCIL’S SUPPORT FOR SUNDAYS RIVER VALLEY AGRI-HUB PROJECT COUNCIL RESOLVED That the item be deferred to the next Council meeting. | Municipal Manager | Report deferred to next Council meeting | Report was tabled to Council on 7 March 2025 |  |
| 65 | 6.3 | APPLICATION BY BORN FREE FOUNDATION TO LEASE ERF 754 MORESON, PATERSON COUNCIL RESOLVED That Council approve leasing erf 754 Eerste laan, Moreson, Paterson to the Born Free Foundation for a period not exceeding three (3) years. | Council Municipal Manager | Lease approved by the Council. Applicant was informed of Council resolution on 11 March 2025. A Lease agreement will be drafted for signing by both parties. | 28 February 2025 |  |
| 66 | 6.4 | TABLING OF THE CODE OF CONDUCT IN TERMS OF SCHEDULE 2 OF THE MSA COUNCIL RESOLVED - The Code of Conduct for municipal officials in terms of the Municipal Systems Act, Act 32 of 2000, as amended, was noted by Council. - The Code of Conduct to be put on the SRVM Letterhead and signed by the Mayor, for subsequent enforcement. - All employees to be workshopped and sign off the Code and failure to adhere thereto to attract consequence management. - Director Corporate Services to lead the process and ensure institution-wide awareness. | Director Corporate Services |  |  |  |
| COUNCIL RESOLUTIONS 07 MARCH 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 67 | 4.1 | REVIEWAL OF THE ORGANISATIONAL STRUCTURE OF SUNDAYS RIVER VALLEY MUNICIPALITY COUNCIL RESOLVED - The Council approve the reviewed organogram. - That a position of a Manager in the Office of the Speaker and the Mayor be included in the Structure. - That the proposed positions of the manager in the office of the Speaker and the Mayor be properly motivated with clear functions - That the positions of the manager in the office of the Speaker and the Mayor be budgeted for and filled in the within the period of 3 months. - The Municipal Manager monitor the implementation of the approved organogram. - That the position of filing clerk reporting to the Chief Financial Officer be excluded from the organisational Structure. - The filling of the vacant posts must be sensitive to the precarious financial position of the municipality and only compliance and service delivery-related positions be filled. Other positions to be filled as the financial position improves. | The Municipal manager/ Director Corporate Services | Council approved the Organisational structure. | 07 March 2025 |  |
| 68 | 4.2 | REPORT TO REQUEST COUNCIL’S SUPPORT FOR SUNDAYS RIVER VALLEY AGRI-HUB PROJECT COUNCIL RESOLVED - That the Council support and endorse the SRV Agri-Hub Project’s application for 300 hectors water rights for Remainder Farm 191/3 farm use. - That the approval of water rights is for exclusive use of 300 hectors Remainder Farm 191/3 farm. | The Municipal Manager | Approve by the Council | 07 March 2025 |  |
| 69 |  | MOTION BY THE DERMOCRATIC ALLIANCE COUNCIL RESOLVED That the Council support application for consent from the MEC for Basic Education by the SPAR Kirkwood. | Municipal Manager | Wildfees application supported by the Council | 07 March 2025 |  |
| 70 | 4.3 | FORMALIZING SPAZA SHOPS IN SUNDAYS RIVER VALLEY MUNICIPALITY COUNCIL RESOLVED - Compliance with SPLUMA and SDF: - Ensure that all land transactions comply with the principles of SPLUMA and are consistent with the municipality’s Spatial Development Framework & Land Use Scheme. - Monitoring and Reporting: - Establish mechanisms for ongoing monitoring and reporting of land disposal and leasing activities to ensure continued compliance with legislative and policy requirements. | Municipal Manager |  |  |  |
| 71 | 4.4 | STATUS UPDATE ON RESOLVING MATERIAL IRREGULARITY RESULTING FROM OPEN-ENDED WASTE LICENSES AND SUPPLY CHAIN MANAGEMENT PROCESS FOR LANDFILL SITE LICENSE REVIEW COUNCIL RESOLVED - Council notes the report - Support the Environmental Review Process: notes the continued stakeholder engagement and public consultations as part of the environmental review process. - Allocate Budget: Approve the allocation of the necessary financial resources to complete the environmental review and obtain the necessary amendments to the landfill site licenses. - Monitor and Oversee the Process: Ensure that regular updates are provided to Council, with monthly progress reports and urgent reporting as necessary. Endorse Compliance with Relevant Legislation: Ensure full compliance with the NEMA, NEMWA, and MFMA during the process, ensuring environmental sustainability and financial accountability. | Municipal Manager/ Director Community Services/ Chief Financial Officer |  |  |  |
| 72 | 4.5 | REQUEST FOR APPROVAL TO ATTEND THE HUMAN RIGHTS YOUTH NETWORK TRAINING IN GOTHENBURG, SWEDEN COUNCIL RESOLVED - That the report be referred to the office of the Municipal Manager for further investigation. - That the Municipal Manager table the report with clear recommendations to the Council. . | Municipal Manager |  |  |  |
| COUNCIL RESOLUTIONS 31 MARCH 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 73 | 15.1 | MPAC OVERSIGHT REPORT ON IRREGULAR EXPENDITURE 2022/23 COUNCIL RESOLVED - That the Council note the report tabled by MPAC - That Council write off all irregular transactions relating to 2022/2023 financial year as investigated by MPAC - that an amount of R24 921 094.78 be written off by Council. | Council | Irregular expenditure written off by the Council. | 31 March 2025 |  |
| 74 | 16.1 | REPORTS FROM THE AUDIT, PERFORMANCE AND RISK COMMITTEE No report was submitted. |  |  |  |  |
| 75 | 17.1 | REPORT ON DRAFT IDP REVIEW FOR 2025/2026 COUNCIL RESOLVED That council take note of the report of the Draft Review IDP 2025/2026 financial year. | Noted | Draft IDP 2025/26 noted by the Council | 31 March 2025 |  |
| 76 | 17.2 | DRAFT ANNUAL BUDGET 2025 – 2026 COUNCIL RESOLVED - That the Council of Sundays River Valley Municipality, acting in terms of section 24 of the Municipal Finance Management Act, (Act 56 of 2003) ADOPTS: 1.1. The Draft annual budget of the municipality for the financial year 2025/26 and the multi-year and single-year capital appropriations as set out in the following tables: 1.1.1. Budgeted Financial Performance (revenue and expenditure by standard classification) as contained in Table 12 of Annexure A. 1.1.2. Budgeted Financial Performance (revenue and expenditure by municipal vote) as contained in Table 13 of Annexure A. 1.1.3. Budgeted Financial Performance (revenue by source and expenditure by type) as contained in Table 14 of Annexure A; and 1.1.4. Multi-year and single-year capital appropriations by municipal vote and standard classification and associated funding by source as contained in Table 15 of Annexure A. 1.2. The financial position, cash flow budget, cash-backed reserve/accumulated surplus, asset management and basic service delivery targets are approved as set out in the following tables: 1.2.1. Budgeted Financial Position as contained in Table 16 of Annexure A. 1.2.2. Budgeted Cash Flows as contained in Table 17 of Annexure A. 1.2.3. Cash backed reserves and accumulated surplus reconciliation as contained in Table 18 of Annexure A. 1.2.4 Asset management as contained in Table 19 of Annexure A; and 1.2.5. Basic service delivery measurement as contained in Table 20 of Annexure A. 2. That the Council of Sundays River Valley Municipality, acting in terms of section 75A of the Local Government: Municipal Systems Act (Act 32 of 2000) APPROVES AND ADOPTS with effect from 1 July 2025 the tariffs as contained in Annexure B: 2.1. the tariffs, rebates and exemptions for property rates 2.2. the tariffs for electricity 2.3. the tariffs for the supply of water 2.4. the tariffs for sanitation services 2.5. the tariffs for solid waste services 3. That the Council of Sundays River Valley Municipality, acting in terms of section 75A of the Local Government: Municipal Systems Act (Act 32 of 2000) ADOPTS with effect from 1 July 2025 the tariffs for other services, as set out in Annexures B. 4. That the Council of Sundays River Valley Municipality, acting in terms of section 17 of the Municipal Finance Management Act, (Act 56 of 2003) ADOPTS with effect from 1 July 2025 the following budget related policies for the 2025/26 financial year. 4.1 Asset management policy - No Change 4.2 Cash Management and Investment policy – No Change 4.3 Credit control and Debt collection policy - No Change 4.4 Property Rates policy - No Change 4.5 Tariff policy – No Change 4.6 Supply Chain Management policy - New Legislation 4.7 Indigent Policy – No Change 4.8 Methodology for the impairments of receivables – No Change 4.9 Principles and Policy on writing-off irrecoverable debt – No Change 4.10 Financial Management Policy – No Change 4.11 Virement Policy – No Change 5. That Council ADOPTS the DRAFT Service Level Standards for the 2025/26 financial year. | Noted | Draft Budget 2025/26 noted by the Council | 31 March 2025 |  |
| 77 | 18.1 | APPROVAL OF TERMS OF REFERENCE FOR THE MUNICIPAL PUBLIC ACCOUNTS COMMITTEE (MPAC) COUNCIL RESOLVED That Council approve the Terms of Reference for MPAC. | Council | Terms of Reference approved by the Council | 31 March 2025 |  |
| 78 | 18.2 | PROGRESS REPORT TO COUNCIL ON THE IMPLEMENTATION OF AUDIT ACTION PLAN COUNCIL RESOLVED - That the Council to considered, comment and noted on the implementation of audit action plan. - That there should be a frequently reporting on the progress made in terms of addressing findings. | Council | NOTED | 31 March 2025 |  |
| COUNCIL RESOLUTIONS 03 APRIL 2025 CONTINUATION OF 31 MARCH 2025 MEETING |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 79 | 18.3 | DRAFT LAND DISPOSAL POLICY COUNCIL RESOLVED: - That the Council acknowledges the Land Disposal Policy. - That the Council approves the proposed land disposal process. - That the Council ensure that all land disposal activities are in line with the policy guidelines. - That the Council establish a Land Committee consisting of Town Planning, Supply Chain Unit, Asset Unit, Health Services, MMs office and Legal Services - That the Council adopt the formulation of the Land Disposal Committee. | Council | The Council approved the Land disposal policy | 31 March 2025 On going process |  |
| 80 | 18.4 | REVIEW OF STANDING RULES AND ORDERS FOR THE MEETINGS OF COUNCIL AND ITS COMMITTEES COUNCIL RESOLVED: That Council approve the Draft reviewed Policy on Standing Rules and Orders for meetings of Council and its Committees, attached to this report as Annexure J. | Council | Ruled and Orders reviewed by the Council | 31 March 2025 |  |
| 81 | 19.1 | REPORT ON THE ESTABLISHMENT OF A HOUSING ALLOCATION COMMITTEE COUNCIL RESOLVED - Approval of the Housing Allocation Committee That the council approve the names of the individuals who will constitute the Housing Allocation Committee, consisting of: - Mr Vuyo Tambo - Ms Lithakazi Kobese - Mr Thobela Masumpa - Ms Nosipho Tsobo - Approval of the Committee Structure That the council approve the following structure for the committee: - Town Planner – Chairperson of the Housing Allocation Committee - Vuyo Tambo – Deputy Chairperson, Human Settlements - Thobela Masumpa – Super User - Nosipho Tsobo – Secretary, Deputy Secretary: Human Settlements - Submission of the Committee to the Sarah Baartman Regional Office That the municipality formally submit the names and structure of the Housing Allocation Committee to the Sarah Baartman Human Settlements Regional Office for further approval and registration. - Inclusion of the Department Human settlement to the committee. That a relevant official from Department of Human Settlement be part of the commit. | Council | Housing Allocation Committee approved by the Council | 31 March 2025 |  |
| 82 | 19.2 | 2024/25 SRVM CAPITAL PROGRAMME UPDATE COUNCIL RESOLVED - Council to note the additional funding report and recommend the implementation. - Council to note that the additional will be utilised on projects that are ongoing as per the report. - The additional funding must be utilised and completed in the current financial year (2024/25 FY) to avoid Roll overs | Council | The Council NOTED an additional funding | 31 Marh 2025 |  |
| 83 | 19.3 | CONSIDERATION OF LAND OFFER BY HABATA BOERDERY PTY LTD FOR HOUSING DEVELOPMENT IN EXCHANGE FOR WATER RIGHTS COUNCIL RESOLVED 1. Notes the proposal from Habata Boerdery Pty Ltd dated 14 March 2025. 2. Authorises the Municipal Manager to initiate a feasibility assessment, including land suitability, legal due diligence, and water rights verification. 3. That after the feasibility assessment has been completed, the report be tabled to the Council for approval. 4. Mandates the Infrastructure Planning and Development Directorate, in collaboration with Legal Services, to engage with Habata Boerdery Pty Ltd for further negotiations and reporting back to Council. 5. Supports in principle the exploration of mutually beneficial land and water rights arrangements to unlock housing and economic development opportunities. | Municipal Manager Director Infrastructure | Habata proposal NOTED by the Council | 31 March 2025 |  |
| 84 |  | REQUEST FOR APPROVAL TO ATTEND THE HUMAN RIGHTS YOUTH NETWORK TRAINING IN GOTHENBURG, SWEDEN COUNCIL RESOLVED - That Council notes the report and attempts made to speedily implement the Council and Council resolution in relation to removal and replacement of participants. - That Council considers the changes for the September 2025 visit to Sweden. - That Council pinpoints reasons that will be acceptable to ICLD as serious reasons for the change, which will assist in strengthening the communique. - The Council is requested to recommend the participation of Councilor K Smith, Mrs. Andiswa Mbongwe and Mrs. Zusiphe Jaji to the 2nd Human Rights Youth Network Training from May 5th to May 8th, 2025. - That Council recommends the cost of subsistence & traveling allowance for the days stated above. - Approve the travel and attendance of the participants in line with SRVM’s international collaboration goals and youth engagement priorities. | Council | Delegation visited Gotham |  |  |
| COUNCIL RESOLUTIONS 17 APRIL 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 85 | 4.1 | LIQUOR APPLICATION – 2025 SPAR KIRKWOOD WILDSFEES COUNCIL RESOLVED That Council approve the following trading hours for the duration of the 2025 Spar Kirkwood Wildsfees: - 09:00 Friday, 27 June to 01:00 on Saturday 28 June 2025 - 09:00 Saturday, 28 June to 01:00 on Sunday 29 June 2025 - 09:00 Sunday, 29 June to 17:00 on Sunday 29 June 2025 | Council | Wildfees trading hours approved. | 17 April 2025 |  |
| 86 | 4.2 | ### REPORT ON WATER RIGHTS ASSOCIATED WITH PORTION COUNCIL RESOLVED - That Council authorize the Municipal Manager to initiate all necessary applications with the Department of Water and Sanitation (DWS), including: - Engagement with the Catchment Management Agency (CMA). - Appointment of relevant specialists, if required. - Submission of licensing and registration documentation. | The Municipal Manager |  |  |  |
| COUNCIL RESOLUTIONS 23 APRIL 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 87 | 4.1 | SECTION 52(D) REPORT FOR PERIOD ENDING 31 MARCH 2025 COUNCIL RESOLVED - That the content of the third quarter financial report of 2024/25 financial year, on the implementation status of the budget of the municipality, as required by the Section 52(d) of the Municipal Finance Management Acting be noted. - That identified cases of Unauthorised, Irregular, Fruitless and Wasteful Expenditure as of 31 March 2025 is noted by Council and referred to the Municipal Public Accounts Committee for investigation as per Section 32. | Council Municipal Public Accounts Committee | 3rd quarter section 52(d) NOTED by the Council. | 23 April 2025 |  |
| 88 | 5.1 | REPORT ON WATER DEBT RELIEF COUNCIL RESOLVED - That the Council of Sundays River Valley Municipality, approves the participation in the Water Debt Relief scheme. - That the Council of Sundays River Valley Municipality, authorise the submission of the application by 30 June 2025. - That the Council of Sundays River Valley Municipality commits to full compliance with the conditions outlined in the Water Debt Relief Guidelines, particularly regarding the consistent payment of current water invoices. - That administration submit section 71 monthly reports reflecting the payments to the Department of water and sanitation | Council Municipal Manager Chief Financial Officer | On 30 July 2025, confirmation to participate in the Water Debt Relief Scheme was received | Commencing in July 2025 |  |
| 89 | 5.2 | REPORT ON URGENT WATER SUPPLY CHALLENGES AND DISRUPTION DUE TO SECURITY CONTRACTOR CONDUCT AT NOMATHAMSANQA WATER TREATMENT WORKS COUNCIL RESOLVED - That the Council refer the report to the Executive committee for further scrutiny and clear recommendations. - That an Executive Committee report back to the Council. | Executive Committee | Item referred to the Executive committee. |  |  |
| COUNCIL RESOLUTIONS 09 MAY 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 90 | 4.1 | PROGRESS REPORT ON AUDIT ACTION PLAN 2023/ 2024 FINANCIAL YEAR #### COUNCIL RESOLVED - The report was withdrawn. | MUNICIPAL MANAGER | Item withdrawn | Submitted to the Council on 30 May 2025 |  |
| 91 | 4.2 | PERRFORMANCE REPORT QUARTER 3 2024/2025 FINANCIAL YEAR #### COUNCIL RESOLVED That the report be deferred to the next Council meeting. | Municipal Manager | Item deferred | Submitted to the Council on 30 May 2025 |  |
| COUNCIL RESOLUTIONS 30 MAY 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 92 | 4.1 | FINAL IDP REVIEW 2025 – 2026 COUNCIL RESOLVED That the Council defer the adoption of the final IDP 2025/2026 attached as annexure to this report be adopted. to a future meeting, pending the completion of the following statutory and procedural requirements: - Completion of Public Participation Process - Alignment of the Integrated Development Plan (IDP) with the Budget - Prioritization of Projects Based on Ward Inputs | Council Municipal Manager | Item deferred | Tabled to the Council on 06 June 2025 |  |
| 93 | 4.2 | DEFERRAL OF ORIGINAL BUDGET 2025/26 APPROVAL COUNCIL RESOLVED That the Council defer the adoption of the 2025/26 municipal budget to a future meeting, pending the completion of the following statutory and procedural requirements: - Completion of Public Participation Process - Alignment of the Integrated Development Plan (IDP) with the Budget - Prioritization of Projects Based on Ward Inputs - Engagement with Provincial Treasury for Funding Assessment | Council Municipal Manager Chief Financial Manager | Item deferred | Tabled to the Council on 06 June 2025 |  |
| 94 | 4.3 | THIRD QUARTER PERFORMANCE REPORT: 1ST JULY2024 – MARCH 2025 FOR 2024/2025 FINANCIAL YEAR #### COUNCIL RESOLVED That Council notes the third quarter performance report 2024-2025 financial year. | COUNCIL | 3rd quarter performance report noted by the Council. | 30 May 2025 |  |
| 95 | 5.1 | AUDIT ACTION PLAN PROGRESS IMPLEMENTATION COUNCIL RESOLVED The Council note the progress made on the implementation of Audit Action Plan 2024/205 quarter 3. | COUNCIL | Audit Action Plan noted by the Council | 30 MAY 2025 |  |
| 96 | 5.2 | REVIEWAL OF SUNDAYS RIVER VALLEY MUNICIPALITY POLICIES COUNCIL RESOLVED - That Council approve the following policies: - Overtime Policy - Recruitment & Selection Policy - Leave Policy - Rules and orders: Dress Code - Acting Allowance Policy - Induction Policy - Counselling / Wellness Policy - Termination Policy - Integrated Waste Management Plan - Land Disposal Policy - Cost Containment Policy - ICT Steering Committee (Terms of Reference) - Patch Management Policy - Business Continuity Plan - ICT SLA Management Policy - ICT Project Management Policy - Corporate Governance of ICT Charter - ICT User Access Management Policy - Server Room Access Policy - That the approved policies be workshopped with all staff. - That Council establish a Rules Committee as stipulated in the approved SRVM Policy on Roles and responsibilities and the Delegation of Power. | COUNCIL | Policies approved by the Council | 30 May 2025 |  |
| COUNCIL RESOLUTIONS 06 JUNE 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 97 |  | FINAL IDP REVIEW 2025 – 2026 COUNCIL RESOLVED That the Council defer the adoption of the 2025/26 municipal Integrated Development Plan (IDP) to a future meeting, pending the completion of the following statutory and procedural requirements: - Completion of Public Participation Process - Alignment of the Integrated Development Plan (IDP) with the Budget - Prioritization of Projects Based on Ward Inputs | Council Municipal Manager | Item deferred | Table to the Council on 13 June 2025 |  |
| 98 |  | DEFERRAL OF ORIGINAL BUDGET 2025/26 APPROVAL COUNCIL RESOLVED That the Council defer the adoption of the 2025/26 municipal budget to a future meeting, pending the completion of the following statutory and procedural requirements: - Completion of Public Participation Process - Alignment of the Integrated Development Plan (IDP) with the Budget - Prioritization of Projects Based on Ward Inputs - Engagement with Provincial Treasury for Funding Assessment | Council Municipal Manager Chief Financial Manager | Item deferred | Table to the Council on 13 June 2025 |  |
| 99 |  | REPORT ON THE VACANT POSITION OF DISCIPLINARY BOAD CHAIRPERSON COUNCIL RESOLVED - It is recommended that the vacancy of the SRVM DB Chairperson to be declared vacant. - That the Municipal Manager facilitates the filling of this vacancy utmost urgency and report to the Council. - That Council authorizes or support Councilor Nodonti to attend the funeral service Advocate Songo on behalf of SRVM. | Council Municipal Manager | Vacancy declared by the Council | 06 June 2025 |  |
| COUNCIL RESOLUTIONS 13 JUNE 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 100 | 4.1 | ADOPTION OF THE FINAL INTERGRATED DEVELOPMENT PLAN 2025/2026 That the Council defer the adoption of the 2025/26 municipal Integrated Development Plan (IDP) to a future meeting, pending the completion of the following statutory and procedural requirements: - Completion of Public Participation Process - Alignment of the Integrated Development Plan (IDP) with the Budget - Prioritization of Projects Based on Ward Inputs | Council Municipal Manager | Item deferred | Tabled to the Council on 20 June 2025 |  |
| 101 | 4.2 | DEFERRAL OF ORIGINAL BUDGET 2025/26 APPROVAL That the Council defer the adoption of the 2025/26 municipal budget to a future meeting, pending the completion of the following statutory and procedural requirements: - Completion of Public Participation Process - Alignment of the Integrated Development Plan (IDP) with the Budget - Prioritization of Projects Based on Ward Inputs. - Engagement with Provincial Treasury for Funding Assessment | Council Municipal Manager Chief Financial Manager | Item deferred | Tabled to the Council on 20 June 2025 |  |
| COUNCIL RESOLUTIONS 20 JUNE 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 102 | 4.1 | ADOPTION OF THE FINAL INTERGRATED DEVELOPMENT PLAN 2025/2026 COUNCIL RESOLVED: - That the Council defer the adoption of the 2025/26 municipal Integrated Development Plan (IDP) to a future meeting, pending the completion of the statutory and procedural requirements: - That the ward 7 Councillor and IDP/PMS Practitioner decide on the date for an IDP/Budget 2025/26 public consultation meeting in ward 7. | Council Municipal Manager | Item deferred | Tabled to the Council on 27 June 2025 |  |
| 103 | 4.2 | DEFERRAL OF ORIGINAL BUDGET 2025/26 APPROVAL COUNCIL RESOLVED: That Council defers the adoption of the 2025/26 Municipal Budget to a future meeting, pending the completion of the following statutory and procedural requirements: - EXCO Consideration The inputs and recommendations from the Executive Committee (EXCO), particularly regarding additional projects proposed for inclusion in the final budget, must be reviewed and considered. - Alignment with the SDBIP All final projects included in the budget must align with the Service Delivery and Budget Implementation Plan (SDBIP), which will be adopted concurrently with the Integrated Development Plan (IDP) and the Budget. - Audit Committee Review The final draft budget 2025/26 must be submitted to the Audit Committee for oversight. Any gaps or issues identified during this review must be addressed prior to the final adoption. - Adoption of Budget 2025/26 That the final Budget 2025/26 be submitted to the Council for adoption on 27 June 2025. | Council Municipal Manager Chief Financial Manager | Item deferred | Tabled to the Council on 27 June 2025 |  |
| ORDINARY COUNCIL RESOLUTIONS 27 JUNE 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 104 | 14.1 | PRESENTATION OF DRAFT BYLAWS AND PROPOSED BYLAW INFRINGEMENT TARIFF PLAN COUNCIL RESOLVED - That the Council notes the draft bylaws and the bylaw Infringement Tariff plan and endorses the initiation of the public participation process. - That the Council approves the publication of draft bylaws, supports the allocation of necessary financial and human resources for implementation. - That the directs the administration to finalise bylaws, post public consultation, prepare it for gazetting, and approves the phase implementation plan and training of relevant officials. | Council Municipal Manager Director Community services | The Council approves the publication of draft bylaws | 27 June 2025 |  |
| 105 | 14.2 | REVIEWED STRATEGY FOR CLEANING, ENVIRONMENTAL MANAGEMENT, AND GREENING COUNCIL RESOLVED - That the Council approve the comprehensive strategy for cleaning environment management and greening. - That the Council approve the strategy and supports the allocation of required funding and human resources. - That the Council direct administration to finalise implementation tools and monitoring mechanisms, and initiates partnerships with private sector and NGOs to support greening and waste initiatives. | Council Municipal Manager Director Community services | The Council approved the strategy for cleaning environment management and greening. | 27 June 2025 |  |
| 106 | 14.3 | ADOPTION OF THE FINAL INTERGRATED DEVELOPMENT PLAN 2025/2026 ITEM 11.1) COUNCIL RESOLVED - That the final IDP 2025/2026 attached as annexure to this report be adopted. - That a copy of the IDP be submitted to the MEC for local government, provincial and national treasury after adoption. - That the IDP 2025/2026 be publicised in all municipal offices. - That the final SDBIP be presented to the Mayor within 14 days after the adoption of the budget. | . Council Municipal Manager | The Council Adopted the Integrated Development Plan 2025/2026 | 27 June 2025 |  |
| 107 | 14.4 | APPROVAL OF ORIGINAL BUDGET 2025/26 (ITEM: 11.2) COUNCIL RESOLVED - That the Council of Sundays River Valley Municipality, acting in terms of section 24 of the Municipal Finance Management Act, (Act 56 of 2003) APPROVES AND ADOPTS: - The annual budget of the municipality for the financial year 2025/26 and the multi-year and single-year capital appropriations as set out in the following tables: - Budgeted Financial Performance (revenue and expenditure by standard classification) as contained in Table 12 of Annexure A. - Budgeted Financial Performance (revenue and expenditure by municipal vote) as contained in Table 13 of Annexure A. - Budgeted Financial Performance (revenue by source and expenditure by type) as contained in Table 14 of Annexure A; and - Multi-year and single-year capital appropriations by municipal vote and standard classification and associated funding by source as contained in Table 15 of Annexure A. The financial position, cash flow budget, cash-backed reserve/accumulated surplus, asset management and basic service delivery targets are approved as set out in the following tables: - Budgeted Financial Position as contained in Table 16 of Annexure A. 1.2.2. Budgeted Cash Flows as contained in Table 17 of Annexure A. 1.2.3. Cash backed reserves and accumulated surplus reconciliation as contained in Table 18 of Annexure A. 1.2.4. Asset management as contained in Table 19 of Annexure A; and 1.2.5. Basic service delivery measurement as contained in Table 20 of Annexure A. - That the Council of Sundays River Valley Municipality, acting in terms of section 75A of the Local Government: Municipal Systems Act (Act 32 of 2000) APPROVES AND ADOPTS with effect from 1 July 2025 the annual tariffs as contained in Annexure B: - the tariffs, rebates and exemptions for property rates - the tariffs for electricity - the tariffs for the supply of water - the tariffs for sanitation services - the tariffs for solid waste services - That the Council of Sundays River Valley Municipality, acting in terms of section 17 of the Municipal Finance Management Act, (Act 56 of 2003) APPROVES AND ADOPTS with effect from 1 July 2025 the following annual budget related policies for the 2025/26 financial year. - Asset management policy - No Change - Cash Management and Investment policy – No Change - Credit control and Debt collection policy - No Change - Property Rates policy - No Change - Tariff policy – No Change - Supply Chain Management policy – Yes - Indigent Policy – No Change - Methodology for the impairments of receivables – No Change - Principles and Policy on writing-off irrecoverable debt – No Change - Financial Management Policy – No Change - Virement Policy – No Change - That the Council of Sundays River Valley Municipality APPROVES AND ADOPTS the Service Level Standards for the 2025/26 financial year. - That the Council of Sundays River Valley Municipality APPROVES AND ADOPTS the Budget Funding Plan for the 2025/26 financial year. - That the Council of Sundays River Valley Municipality APPROVES AND ADOPTS the Procurement Plan for the 2025/26 financial year. - That the Council of Sundays River Valley Municipality APPROVES AND ADOPTS the UIFWE reduction action plan for the 2025/26 financial year. | Council Municipal Manager Chief Financial Manager | The Council approved and adopted the Annual budget 2025/2026 | 27 June 2025 |  |
| 108 | 14.5 | SUBMISSION OF THE FINAL INTEGRATED WASTE MANAGEMENT PLAN (IWMP) FOR SUNDAYS RIVER VALLEY MUNICIPALITY (ITEM: 11.3) COUNCIL RESOLVED - That the Council supports the adoption of the Final Integrated Waste Management Plan by the Council. - That the Council advocates for the allocation and mobilisation of adequate human and financial resources necessary for the effective implementation of the IWMP. - That the municipality prioritizes the integration of the IWMP into the next IDP cycle and communicates this to the MEC for Environmental Affairs for endorsement. - That implementation of the IWMP be closely monitored, and quarterly progress reports be submitted to the Council. - That partnerships be pursued with provincial and national departments, as well as private sector entities, to address funding, technical support, and innovation in waste management. | Council Municipal Manager Director Community services | The Council approved and adopted the IWMP. | 27 June 2025 |  |
| 109 | 15.1 | MPAC OVERSIGHT REPORT ON UIFWE 2024/2025 FOR PRIOR PERIOD 2019/20 COUNCIL RESOLVED - That Council condone the work done by Municipal Public Accounts Committee on 2019/20 prior years Unauthorised, Irregular and Fruitless and Wasteful Expenditure. - That the Council approve the write-off of the Unauthorised, Irregular and Fruitless and Wasteful Expenditure amounting to R408 807 639.00 incurred prior to 2019/20 as irrecoverable in terms of Section 32(2) of the MFMA. - That there will be no consequence management due to unavailability of records except to strength the internal control environment. - That if new evidence arises, that evidence be brought back to the Council for consideration. |  |  |  |  |
| 110 | 16.1 | AUDIT COMMITTEE REPORT TO COUNCIL QUARTER 3 for 2024/2025 COUNCIL RESOLVED - That the Council adopts and accept the recommendations of the Audit, Performance and Risk Committee. - That the Management implement the recommendations of the Audit, Performance and Risk Committee Risk Committee. | Council Management | Audit Committee recommendations adopted by the Council | 27 June 2025 On going |  |
| ORDINARY COUNCIL RESOLUTIONS 02 JULY 2025 |  |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT / OFFICIAL | ACTION | DATE OF COMPLETION |  |
| 111 |  |  |  |  |  |  |
| 112 | 17.1 | PROGRESS REPORT TO COUNCIL ON THE IMPLEMENTATION OF AUDIT ACTION PLAN 2024/2025 COUNCIL RESOLVED - That the Council emphasises application of consequence management by the accounting officer on those that fail to implement the audit action plan. - That there should be a frequently reporting on the progress made in terms of addressing findings. | Council | Council NOTED the implementation of the Audit Action Plan | 02 July 2025 |  |
| 113 | 17.2 | REPORT ON CURRENT STATE OF RECORDS MANAGEMENT COUNCIL RESOLVED That the Council take note of the current state of records management. | Council | NOTED | 02 July 2025 |  |
| 114 | 17.3 | APPLICATION OF RENEWAL OF LEASE AGREEMENT – FARM ENON MISSION STATION NO 40 COUNCIL RESOLVED - That Council approve the lease agreement between Vodacom and SRVM. - That the municipality do a benchmark in terms of the lease amount, - That Council authorize the Municipal Manager to sign the Lease agreement on behalf of Council. | Council Municipal Manager | Lease approved | 02 July 2025 |  |
| 115 | 17.4 | ## PROPOSED WATER RIGHTS EXCHANGE INVOLVING PORTION KK113 ADDO KOMARTI ## DRIFT AND LAND FROM HABBATA FARM BOERDERY COUNCIL RESOLVED - That, Council notes the delay in finalizing a complete feasibility study due to internal capacity limitations in geotechnical engineering, town planning, and human settlements regulations. - That Council approves the appointment of suitably qualified private consultants to undertake a detailed feasibility study incorporating: - Full geotechnical investigation (soil composition and bearing capacity) - Environmental compliance (wetland verification, BAR/EIA) - Bulk service assessments and land-use planning - Spatial compliance in line with SPLUMA, NEMA, and the SRVM SDF - That, the proposed water rights exchange with Habata Farm Boerdery be deferred pending the outcome and tabling of the final feasibility report to Council. - That engagements be initiated with the DWS, and the Provincial Departments of Human Settlements and Cooperative Governance to ensure legal and procedural compliance. - That, a multi-disciplinary internal team with the inclusion of the Portfolio Councilor and a ward Councilor be established to oversee the project, support the consultants, and ensure alignment with Council’s service delivery mandate. That the affected councilors be part of the multi-disciplinary internal team, - That, Council notes the importance of this transaction for advancing municipal housing objectives and commits to prioritising the completion of the study and related legal processes. | Council Municipal Manager | Council approved appointment of the suitable qualified consultants | 02 July 2025 Work in progress |  |
| 116 | 17.5 | REPORT TO SUNDAYS RIVER VALLEY MUNICIPAL EXCO ON APPROVAL FOR ATTENDANCE AT ÖCKERÖ LIGHTHOUSE CONVERSATIONS 2025, SWEDEN COUNCIL RESOLVED - That the Council approve attendance of the Mayor, Councillor Solethu Lucas, Alderman Karen Smith and Mrs Andiswa Mbongwe at the Öckerö Lighthouse Conversations 2025 in Sweden from September 5–7, 2025 - The Council authorises allocation of a budget, for programmes targeting development of you people in the Valley. - The delegation submits a post-visit report to Council within 30 days of return, outlining key insights, networks established, and recommendations for local implementation. - The Council endorses the strategic value of this engagement in advancing Sundays River Valley Municipality’s visibility and participation in global platforms aligned with SDG targets and local development goals. | Council | Council approve attendance at the Öckerö Lighthouse Conversations 2025 in Sweden from September 5–7, 2025 | 02 July 2025 |  |
| 117 | 17.6 | VISIT TO FALEKNBERG MUNICIPALITY (SWEDEN) BY SRVM DELEGATE (8-12 SEPTEMBER 2025) COUNCIL RESOLVED - That the Council approval of the travelling of the Mayor, Opposition Party Leader, Director of Community Services and the Communications Officer to Falkenberg, Sweden from 8 - 12 September 2025 - That a report to be submitted to Council on return from the visit to Falkenberg municipality Sweden - That the standard subsistence allowance be provided to the SRV M delegates. | Council | Council approved the travelling of the two Falkenberg, Sweden | 02 July 2025 |  |
| 118 | 17.7 | CALENDAR OF DATES FOR 2025/2026 FINANCIAL YEAR COUNCIL RESOLVED That Council approves the calendar of dates for 2025/2026, attached to the report as Annexure K. | Council | Calendar of dates approved by the Council | 02 July 2025 |  |

| COUNCIL IN COMMITTEE MEETING HELD ON 27 SEPTEMBER 2024 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 1. | 7.1 | LITIGATIONS REGISTER COUNCIL RESOLVED That the Council take note of the municipal litigations register. | MUNICIPAL MANAGER DIRECTOR CORPORATE SERVICES | NOTED | 27 September 2024 |
| 2 | 7.2 | LEGAL OPINION ON TRAVELLING ALLOWANCES Minutes of this item taken by Director Corporate Services and resolution not submitted |  |  |  |
| 3 | 7.3 | REPORT ON THE PROVISION OF CLOSE PROTECTION SERVICES FOR COUNCILLORS AND SENIOR MANAGERS – SUNDAYS RIVER VALLEY MUNICIPALITY COUNCIL RESOLVED: That Due to the high cost incurred and the dire financial health of the Sundays River Valley Municipality, the close protection services for - Councillor Mandile Payi, be terminated at the end of September 2024. - Councillor Solethu Lucas be terminated at the end of September 2024. - Director Corporate Services; Mr Kondile be terminated at the end of September 2024. - That a cost breakdown on spending on official duties and personal matters in order know how much Council can recoup from the cost. | MUNICIPAL MANAGER | 1 month notice of contract termination was issued to the service provider. Letter dated 05 June 2024. | COMPLETED |
| 4 | 7.4 | TERMINATION OF SERVICES: WEST RAND CONSULTING COUNCIL RESOLVED: - That the Council note the letter of termination from WRCON - That the Municipal Manager writes a letter of response acknowledging the WRCON letter of termination and conditions for mutual termination | MUNICIPAL MANAGER |  | Completed |
| SPECIAL COUNCIL IN COMMITTEE MEETING HELD ON 31 OCTOBER 2024 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 6. | 5.1 | GRIEVANCE AGAINST THE MUNICIPAL MANAGER: MR T KLAAS COUNCIL RESOLVED: - That an independent committee be established to investigate if the matter requires mediation or disciplinary action: - That the Mayor Writes to the identified organisations and request their availability to serve in the committee. - That the following members be part of the committee: - Councillors: S. Nodonti K. Smith (ii) Ndlambe LM Municipal Manager: Mr Dumezweni (iii) SALGA: Office of Provincial Director of Operations (iv) Department of Cooperative Governance & Traditional Affairs (COGTA) c) That the Committee reports back to the Council within 90 days of establishment. | COUNCIL MAYOR | Committee was established by Council Letter written and forwarded to relevant departments. | Ongoing |
| ORDINARY COUNCIL IN COMMITTEE MEETING HELD ON 11 DECEMBER 2024 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 7 | 7.1 | GRIEVANCE FROM THE CHIEF FINANCIAL OFFICER COUNCIL RESOLVED That the item be withdrawn. | MAYOR | Item was withdrawn | Item was withdrawn |
| 8 | 8.1 | RECRUITMENT PROCESS FOR THE FILLING OF THE POSITION OF DIRECTOR: IPD COUNCIL RESOLVED - The Council notes the expiry date of the fixed-term Employment Contract of the Director: IPD on the 31st of March 2024. - The Council considers the amendments in the Municipal Systems Act, Act 32 of 2000 and the position to be made permanent in line with section 56 on the appointment of managers directly accountable to the municipal manager. - A Notice of the expiry of the Contract of Employment to be sent to the incumbent. - The detailed Recruitment Process Plan to be presented and approved by Council and an advertisement to be placed in the national newspapers if the Council decides to follow this route. | COUNCIL MUNICIPAL MANAGER DIRECTOR CORPORATE SERVICES | Council noted the report. Recruitment process was started, and position was advertised in the Sunday Times on 26 January and EP Herald 27 January 2025. Closing date – 07 February 2025. Director IPD received a notice of expiry of contract on 15 January 2025. Members of Panel were informed and shortlisting for position was done on 10 March 2025. | Work in progress |
| 9 | 8.2 | ITEM ON ILLEGAL OCCUPATION OF MUNICIPAL LAND UPDATE ON THE JOVUKA AND OTHERS COUNCIL RESOLVED - That the Council notes the report on the illegal occupation of municipal land. - That the Council affirms its opposition to any illegal occupation of land in Sundays River Valley Municipality. - That the Municipal Manager explore options of settling on the matter. - That the item be tabled to the Council before a final settlement is reached. | MUNICIPAL MANAGER |  |  |
| 10 | 8.3 | REPORT ON CONSEQUENCE MANAGEMENT RELATED 2023/24 POOR AUDIT OUTCOMES AND OTHER MATTERS COUNCIL RESOLVED - That Council consider the draft 2023/24 Draft Management Report - That Council consider and approve the consequence management for failure to implement the Audit Action Plan on the Chief Financial Officer and the Director: Corporate Services - That due to the gravity and serious nature of the alleged offences against the Chief Financial Officer and the Director: Corporate Services, the Accounting Officer be authorised to seek legal advice with the intention to institute Disciplinary Action in line with the Local Government Disciplinary Regulations for Senior Managers - That the alleged R1.3 m fraud related to payment to WRCON be investigated and disciplinary actions be instituted. - That an Independent Qualification Audit be undertaken of top to middle management (TG 10) be undertaken. - That an Independent Employee Verification of all employees to identify the existence of ghost employees at SRVM be undertaken. | MUNICIPAL MANAGER | A report was submitted to Council on 07 March 2025, Resolving the suspension of the Chief Finance Officer and Director: Corporate Services. Specifications were done for the appointment of a services provider to undertake the qualification audit and do a headcount for employees. | Ongoing |
| 11 | 8.4 | REPORT ON THE HAWKS/SIU INVESTIGATIONS AT SUNDAY’S RIVER VALLEY MUNICIPALITY COUNCIL RESOLVED - That Council note the joint HAWKS and SIU alleged WRCON investigation at SRVM. - That Councill condones and support actions by the Accounting Officer in co-operating with the Law Enforcement Agencies in this regard. - That the Council be regularly updated on the investigation. | COUNCIL | Councill noted the report and condoned support actions by the Accounting Officer in co-operating with the Law Enforcement Agencies in this regard. | Ongoing |
| COUNCIL IN COMMITTEE MEETING HELD ON 24 JANUARY 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 12 |  | DETERMINATION OF UPPER LIMITS OF THE SALARIES, ALLOWANCES AND BENEFITS OF DIFFERENT MEMBERS OF MUNICIPAL COUNCILS COUNCIL RESOLVED: That Gazette 51419 being implemented backdated from the 1st of July 2024 for the following councillor positions’ - Eleven ordinary part-time Councillors - R307,494 (pa) - One part-time Whip - R406,565 (pa) - One Part-time MPAC Chair - R394,630 (pa) - Two full-time Exco members - R728,770 (pa) - One full-time Speaker - R777,353 (pa) - One full-time Mayor - R971,690 (pa) | Finance | Resolution was implemented | Complete |
| COUNCIL IN COMMITTEE MEETING HELD ON 10 FEBRUARY 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 13 | 4.1 | REPORT ON THE INVESTIGATION OF THE PROCUREMENT AND PAYMENTS ON THE WEST RAND CONSULTING CONTRACT- BID NO. REG 32/01/2022. COUNCIL RESOLVED - An investigation is to be made into whether the out-of-scope payments were made lawfully and in terms of the contract entered into with WRCON. - SALGA / OTP / COGTA to be approached and requested to conduct a Forensic investigation of the entire contract, since the DB could not tie back the expenditure incurred on the contract, due to the lack of proper responses by the CFO and the unavailability of documents. - The Council note the conduct of the CFO in his failure of his duties to assist the DB in the conduct of its investigation of this contract, and his conduct is tantamount to dereliction of his duties or other sanctions which the council may impose. - That the CFO be subjected to disciplinary processes. | Municipal manager | A report was submitted to Council on 07 March 2025. | Work in progress |
| 14 | 4.2 | CONSEQUENCE MANAGEMENT; NON-IMPLEMENTATION OF THE AUDIT ACTION PLAN Report to the Municipal Council regarding allegations of misconduct against the Chief Financial Officer and the Director: Corporate Services and recommendations concerning the appointment of a firm of attorneys to investigate the allegations and as regards the proposed suspension of the said Senior Managers COUNCIL RESOLVED The item was deferred to the next meeting | Municipal Manager | A report was submitted to Council on 07 March 2025, Resolving the suspension of the Chief Finance Officer and Director: Corporate Services. | Work in progress |
| COUNCIL IN COMMITTEE MEETING HELD ON 17 FEBRUARY 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 15 | 4.1 | CONSEQUENCE MANAGEMENT; NON-IMPLEMENTATION OF THE AUDIT ACTION PLAN Report to the Municipal Council regarding allegations of misconduct against the Chief Financial Officer and the Director: Corporate Services and recommendations concerning the appointment of a firm of attorneys to investigate the allegations and as regards the proposed suspension of the said Senior Managers 1. COUNCIL RESOLVED as follows: - Attorneys Wesley Pretorius and Associates Inc. are hereby appointed to investigate the allegations of misconduct brought against the Chief Financial Officer and the Director: Corporate Services, respectively, as envisaged in Regulation 5 of the Local Government: Disciplinary Regulations for Senior Manager. Because it is alleged that the senior managers concerned have committed acts of misconduct and in view thereof that the municipal council has reason to believe that their presence at the workplace may jeopardise any investigation into the alleged misconduct given their seniority and access to critical information pertinent to any investigation, that they may commit further acts of misconduct, or that their presence may be detrimental to stability in the municipality in the light of the seniority and the fact that they are subject to an investigation, that it is proposed to suspend the Chief Financial Officer and the Director: Corporate Services as a precautionary measure, as envisaged in regulation 6 of the Local Government: Disciplinary Regulations for Senior Managers. To this end, the senior managers concerned must be given an opportunity to make written representations to the municipal council why they should not be suspended within seven days of them being notified of their proposed suspension, and the Accounting Officer is authorised to notify the senior managers concerned of their proposed suspensions. | Municipal Manager | A report was submitted to Council on 07 March 2025, Resolving the suspension of the Chief Finance Officer and Director: Corporate Services. | Work in progress |
| 16 | 4.2 | CONSEQUENCE MANAGEMENT: WRCON DISCIPLINARY BOARD REPORT COUNCIL RESOLVED - That Council through the Accounting Officer refer the findings and recommendations of the Disciplinary Board to the Independent Investigator appointment in terms of the Local Government Disciplinary Regulations for Senior Managers for possible disciplinary charges against the Chief Financial Officer. That in the event that anyone be found guilty of financial misconduct, and or any financial losses incurred by SRVM, this be recovered jointly from former Municipal Manager, Chief Financial Officer and WRCON. | Municipal Manager |  |  |
| COUNCIL IN COMMITTEE MEETING HELD ON 28 FEBRUARY 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 17 | 4 4.1 | REPORT FROM THE WHIP OF COUNCIL THREATHS AGAINST THE DIRECTOR COMMUNITY SERVICES FROM THE SPEAKER OF SRVM COUNCIL RESOLVED That the item be deferred to the next Council meeting. | WHIP OF COUNCIL | A report was submitted to Council on 07 March 2025, Resolving the appointment of Ad Hoc Committee of Council. | Work in progress |
| COUNCIL IN COMMITTEE MEETING HELD ON 07 MARCH 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 18 | 4 4.1 | REPORT FROM THE WHIP OF COUNCIL ITEM FROM THE WHIP OF COUNCIL ON THE WHIPPERY REPORT That the Council appoint the following Councillors to be part of the Ad Hoc Committee: Cllr Bosman Cllr Payi Cllr Ncambele | Council | Committee was established by Council | Work in progress |
| 19 | 5 5.1 | REPORT FROM AN ADHOC COMMITTEE OF COUNCIL REPORT TO THE SUNDAYS RIVER VALLEY MUNICIPAL COUNCIL: GRIEVANCE LODGED BY MISS ZUKISWA MSENGI AGAINST THE MUNICIPAL MANAGER, MR. THABISO KLAAS Based on the findings from the and the report from the Ad Hoc Committee, the following the COUNCIL RESOLVED: - Review the Full Grievance: To review the entire grievance document, as it was not presented previously, to determine if it still warrants investigation. - Consider Alternative Resolution: If the grievance relates to fostering a healthier work environment, Corporate Services may address the matter without requiring the full committee investigation. Corporate Services should evaluate the situation and explore opportunities for mediation and conflict resolution. - Separate Issues for Consideration: If the grievance involves both workplace safety and alleged misconduct, Council may consider separating the issues to allow Corporate Services to manage the workplace environment aspects, while retaining the committee's oversight of any potential misconduct. - Clear and Transparent Process: Ensure that all grievances are handled in accordance with municipal policy, the Labour Relations Act, and the municipality's internal codes of conduct, ensuring fairness and impartiality in resolving conflicts. - That Council notes the contents of the report. - That Council resolved to refer the matter to Corporate Services Director if the primary concern is a healthier work environment. - That Council ensures due process and fair handling of the grievance in accordance with the relevant legislation. | Council | Grievance referred to Corporate Services. | Work in progress |
| 20 | 6.1 | REPORT TO THE MUNICIPAL COUNCIL REGARDING THE PROPOSED SUSPENSIONS OF THE MUNICIPALITY’S CHIEF FINANCIAL OFFICER AND ITS DIRECTOR: CORPORATE SERVICES - COUNCIL RESOLVED as follows: - That the additional allegation that the CFO has abused his sick leave, also be referred to attorneys Wesley Pretorius and Associates Inc for investigation. - That having considered the representations of the Chief Financial Officer and the Director: Corporate Services as to why they should not be suspended, and all other relevant information, including the matters referred to in regulation 6(1) of the Local Government: Disciplinary Regulations for Senior Managers (“the Disciplinary Regulations”), it is resolved to suspend both senior managers with immediate effect, for the following reasons. - The Municipal Council is satisfied that there is reasonable cause to believe that they have committed acts of misconduct as set out in the letters from the municipal manager dated 25 February 2025 and has at its meeting of 17th February 2025 resolved that a law firm be appointed to investigate the allegations of misconduct, as envisaged in regulation 5 of the Disciplinary Regulations. - It is alleged that the senior managers concerned have committed acts of misconduct, as envisaged in regulation 6(1). - The Municipal Council has reason to believe that the presence of the senior managers concerned at the workplace may jeopardise any investigation into the alleged misconduct given their seniority and access to critical information pertinent to any investigation, that they may commit further acts of misconduct (as is now alleged to be the case in respect of the Chief Financial Officer), or that their presence may be detrimental to stability in the municipality in the light of their seniority and the fact that they are subject to an investigation, as envisaged in regulation 6(1)(a) and (b). - In addition, the Municipal Council notes that it is now alleged that the Chief Financial Officer has committed further misconduct (by abusing his sick leave) after he was issued with a letter informing him of the municipal council’s intention to suspend him. - As regards the representations of the Chief Financial Officer, the Municipal Council notes, prima facie, that he has not seriously challenged the allegations against him and that to the extent that he has challenged the allegations such challenges appear to be inadequate and without merit. Moreover, it is apparent that the adverse audit findings in question have not yet been resolved. In addition, the Municipal Council is not persuaded that the alternatives to suspension proposed by him are reasonable in the circumstances, particularly given the allegation that he has committed further misconduct. Finally, he has also not seriously addressed the municipality’s contention that the Municipal Council has reason to believe that his presence at the workplace may jeopardise any investigation into the alleged misconduct given his seniority and access to critical information pertinent to the investigation, that he may commit further acts of misconduct, or that his presence may be detrimental to stability in the municipality in the light of his seniority and the fact that he is subject to an investigation. - As regards the representations of the Director: Corporate Services, the Municipal Council notes, prima facie, that he, too, has not seriously challenged the allegations against him and that to the extent that he has challenged the allegations such challenges appear to be inadequate and without merit. Moreover, it is apparent that the adverse audit findings in question by and large remain unresolved. In addition, he has also not seriously addressed the municipality’s contentions that the Municipal Council has reason to believe that his presence at the workplace may jeopardise any investigation into the alleged misconduct given his seniority and access to critical information pertinent to the investigation, that he may commit further acts of misconduct, or that his presence may be detrimental to stability in the municipality in the light of his seniority and the fact that he is subject to an investigation. - The suspension is a precautionary measure, as envisaged in the regulations, and will be on full pay. The duration of the suspension will be for the period envisaged in the regulations. - The Municipal Manager is authorised to notify the Chief Financial Officer and the Director: Corporate Services of their suspensions. | Council Municipal Manager | A report was submitted to Council on 07 March 2025, Resolving the suspension of the Chief Finance Officer and Director: Corporate Services. | Work in progress |
| ORDINARY COUNCIL IN COMMITTEE MEETING HELD ON 31 MARCH 2025 |  |  |  |  |  |
| 21 | 7. 7.1 | REPORT FROM THE DISCIPLINARY BOARD REPORT FOR THE DISCIPLINARY BOARD ON PAYROLL IRREGULARITIES THE COUNCIL RESOLVED: - Having considered the findings of the Misconduct Disciplinary Board, the Council referred the report to the office of the Manager. - That the Municipal manager table the report with clear recommendations on the matter to the Council | Council Municipal Manager |  |  |
| 22 | 8.1 | EXTENSION OF CONTRACT FOR THE DIRECTOR IPD COUNCIL RESOLVED: That the employment contract of Director: Infrastructure, Planning & Development, Mr. X Mntonintshi, be extended on a month-to-month basis for a period not exceeding three (3) months. | Council |  |  |
| 23 | 8.2 | REPORT ON THE PRECAUTIONARY SUSPENSION OF CFO AND DIRECTOR CORPORATE SERVICES REPORT TO THE MUNICIPAL. COUNCIL REGARDING FURTHER ALLEGATIONS OF MISCONDUCT AGAINST THE CHIEF FINANCIAL OFFICER AND THE DIRECTOR: CORPORATE SERVICES. COUNCIL RESOLVED: Attorneys Wesley Pretorius and Associates Inc. must within a period of 30 calendar days submit a report with recommendations to the Municipal Manager in respect of all the allegations of misconduct referred to them for investigation, as set out above, as envisaged in regulation 5 (4) of the Local Government: Disciplinary Regulations for Senior Managers. | Municipal Manager |  |  |
| 24 | 8.3 | APPOINTMENT OF ACTING DIRECTOR CORPORATE SERVICES AND ACTING CHIEF FINANCIAL OFFICER COUNCIL RESOLVED - That Council ratify the appointment of the Manager: Administration & Council Support (Mrs. S E Fourie) as acting Director: Corporate Services, for a period of three months effective 17 March 2025. - That Council ratify the appointment of the Accountant: Budget & Treasury (Mrs. O Kona) as Acting Chief Financial Officer on a month-to-month basis, effective 27 February 2025. - That an acting allowance calculated in terms of the staff Regulations and guidelines be paid to the incumbents. | Council |  |  |
| COUNCIL IN COMMITTEE MEETING HELD ON 17 APRIL 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 25 | 4.1 | REFERRAL OF DISCIPLINARY BOARD PAYROLL REPORT COUNCIL RESOLVED That Council approves the referral of the Disciplinary Board Payroll Report to the Council appointed Independent Investigator in terms of the Local Government Regulations on Disciplinary Hearings for Senior Managers. | Council |  |  |
| COUNCIL IN COMMITTEE MEETING HELD ON 23 APRIL 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 26 | 4.1 | PROGRESS REPORT ON THE SELECTION PROCESS TO THE EXPIRED CONTRACT POSITION OF DIRECTOR: INFRASTRUCTURE PLANNING AND DEVELOPMENT (IPD) AT SRVM COUNCIL RESOLVED That Council take note the progress report on the appointment of Director: Infrastructure Planning and Planning. | Council |  |  |
| COUNCIL IN COMMITTEE MEETING HELD ON 09 MAY 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 27 | 4.1 | # APPOINTMENT OF DIRECTOR INFRASTRUCTURE PLANNING AND DEVELOPMENT COUNCIL RESOLVED - That the Council meeting be adjourned to allow the Municipal Manager to convene the Selection Panel appointed by the Council for the selection process of the Director Infrastructure, Planning and Development, to respond to the questions raised by Councillors on the decisions and recommendations of the panel. - That the Council refers the questions raised by the Councillors on the matter to the selection panel for responses. - That the Councillors submit their written questions related to the selection process of the Director Infrastructure, Planning and Development to the Office of the Speaker by 13 May 2025. - That a Special Council reconvening the council be scheduled on receipt of the responses. | Council Selection panel |  |  |
| 28 | 4.2 | ELECTION OF THE CHAIRPERSON FOR AN AD-HOC COMMITTEE OF COUNCIL: THREATHS AGAINST THE DIRECTOR COMMUNITY SERVICES FROM THE SPEAKER OF SRVM COUNCIL RESOLVED - That the Council elect Councillor Ncambele as a Chairperson of the Ad hoc Committee to investigate the grievance against the Speaker. - That the Ad hoc Committee after having investigated table the report with recommendations to the Council. |  |  |  |
| COUNCIL IN COMMITTEE MEETING HELD ON 30 MAY 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 29 | 4.1 | EXTENTION OF TENURE OF ACTING CHIEF FINANCIAL OFFICER COUNCIL RESOLVED - That Council extends the appointment of the Accountant: Budget & Treasury (Mrs. O Kona) as Acting Chief Financial Officer for a further period of three months, effective 28 May 2025. - That an acting allowance calculated in terms of the staff Regulations and guidelines be paid to the incumbents. - That Council, through the Office of the Municipal Manager, seeks concurrence from the MEC for the extension of the acting appointment of MS O Kona as Acting Chief Financial Officer. | Municipal Manager |  |  |
| 30 | 4.2 | REPORT ON APPOINTMENT OF DIRECTOR INFRASTRUCTURE PLANNING AND DEVELOPMENT COUNCIL RESOLVED - That Council considered the written responses to the questions by Council. - That Council considered and adopted the legal opinion by the Municipal Attorneys. - That the Municipal Manager be authorised to write a one month notice letter to Acting Director Infrastructure Planning and Development that his 3-month contract ending on 30 June 2025 will not be extended beyond that date. - That Council approve the re-advertisement of the position of Director: Infrastructure Planning and Development. - That a further charge of gross negligence be instituted against the Director: Corporate Services. - That where possible the re-advertising costs be recovered from the Director: Corporate Services. | Municipal Manager |  |  |
| 31 | 4.3 | INVESTIGATION REPORT: ALLEGATIONS OF MISCONDUCT AGAINST THE CHIEF FINANCIAL OFFICER AND THE DIRECTOR: CORPORATE SERVICES COUNCIL RESOLVED - The council determines that the alleged misconduct, as set out in the report of WP&A, is of a serious nature, as envisaged in regulation 5(7) of the Disciplinary Regulations. - The council ratifies the decision by the Municipal Manager to refer the allegation that the Director: Corporate Services has failed to manage the recruitment process relating to the vacant position of Director: Infrastructure, Development and Planning, appropriately, to WP&A to for investigation. (c) Disciplinary proceedings are hereby instituted against both the CFO and the Director: Corporate Services, as envisaged in the Disciplinary Regulations, on the allegations of misconduct in the investigation report in respect of which WP&A’s report has concluded there is prima facie evidence that serious misconduct has been committed, a conclusion with which the council agrees. - The municipal manager is authorised to appoint an independent and external presiding officer and an officer to lead evidence in respect of both disciplinary proceedings, and to sign the letters of appointment. | Municipal Manager |  |  |
| 32 | 4.4 | REPORT ON ALLEGATIONS OF BRIBERY COUNCIL RESOLVED - That Council consider the letters related to the complaint and responses thereto. - That the Disciplinary Board investigate both the allegation and counter allegations made by both employees. - That if the allegations on both sides are substantiated, consequence management follow. | Municipal Manager |  |  |
| ORDINARY COUNCIL IN COMMITTEE MEETING HELD ON 27 JUNE 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 33 | 7.2 | EXTENTION OF TENURE OF ACTING DIRECTOR CORPORATE SERVICES COUNCIL RESOLVED - That Council extends the appointment of the Manager: Administration as Acting Director Corporate services for a further period of three months, effective 17 June 2025. - That an acting allowance calculated in terms of the staff Regulations and guidelines be paid to the incumbents. - That Council, through the Office of the Municipal Manager, seeks concurrence from the MEC for the extension of the acting appointment of Mrs. S Fourie as Acting Director Corporate Services. | Council |  |  |
| 33 | 8.2 | REPORT ON APPOINTMENT OF DR LUVUYO BONO AS THE CHAIRPERSON OF THE SRVM DISCIPLINARY BOARD That Council consider appointing Dr Advocate Luvuyo Bono as the Chairperson of the Disciplinary Board of Sundays River Valley Municipality for the remainder of the term of Advocate Songo. | Council |  |  |
| 34 |  | DESIGNATION OF MUNICIPAL VALUER Council resolved - NOTES the appointment of Zack Van Der Merwe of Gov Pro South Africa as a municipal valuer. - Notes the designation of the municipal valuer and the determined date of valuation in terms of sections 33 (1) and 31 (1) respectively of the Municipal Property Rates Act (MPRA), No 6 of 2004 | Council |  |  |
| COUNCIL IN COMMITTEE MEETING HELD ON 02 JULY 2025 |  |  |  |  |  |
| RES. NR | ITEM NR | RESOLUTION | RESPONSIBLE DEPT | ACTION | DATE OF COMPLETION |
| 35 | 7.1 | REPORT ON LITIGATIONS AS AT 30 MAY 2025 COUNCIL RESOLVED That the Audit Committee take note of the content of the municipal litigations register. | Council |  |  |
| 36 | 8.1 | RECRUITMENT PROCESS FOR THE FILLING OF THE POSITION OF DIRECTOR: IPD COUNCIL RESOLVED - The Municipal Manager as the Chairperson of the panel. - Portfolio Head of Infrastructure Planning & Development (IPD). - An expert in the Engineering Field or Professional Engineer from COGTA - A letter of invitation to be extended to the institution by the Municipal Manager, upon Council approval of the selection panel. - That the Council a Mr appoints Mntonintshi temporarily for 2 months. - That the accounting officer seek approval from the MEC. | Council Municipal Manager |  |  |

### 2.2	ADMINISTRATIVE GOVERNANCE

The municipal Manager is the accounting officer of the municipality for the purposes of the Finance Management Act. He provides guidance in compliance with this Act and other legislation applicable to local government.

Senior management positions of the municipality are all filled. They comprise of the Municipal Manager and four section 56 managers. The section 56 managers are responsible for providing reports to the standing committees, the Exco and Council. The Municipal Manager and the Directors work together to formulate policies and procedures for adoption by Council. The performance agreements of senior managers outline the strategies and projects to be developed, together with targets for service delivery. Each department is provided with a budget through which the IDP is implemented.

The council has established and implemented a Performance Management System, and it is administered in-house.

FUNCTIONS In terms of Section 55 of the Municipal Systems Act, the Municipal Manager is responsible and accountable for some of the following functions: - The formation and development of an economical, effective, efficient, and accountable administration. - The management of the municipality’s administration in accordance with this Act and other legislation applicable to the municipality. - The implementation of the municipality’s Integrated Development Plan, and the monitoring of progress with implementation of the plan. - The management of the provision of services to the local community in a sustainable and equitable manner. - The appointment of staff other than those referred to in section 56 (a), subject to the Employment Equity Act, 1998 (Act No.55 of 1998). - The management, effective utilization, and training of staff. - The maintenance of discipline of staff. The promotion of sound labour relations and compliance by the municipality with applicable labour legislation. There are also functions entrusted in the office of the Municipal Manager. These include: - Local Economic Development - Performance Management - Intergovernmental Relations - Special Programmes - Service delivery - Financial Management TIER 2: section 56 DIRECTOR” S Director: Corporate Services (Mr.P.Kondile); Director: Technical Services (Mr. X Mntonintshi); Director: Community Services (Mrs.A.N. Mbongwe); Chief Financial Officer (Mr. H Krapohl). Functions: Human Resources management Skills Training and Development Registry and Archives Administration; Functions: Basic service delivery and infrastructure development Electrical distribution and system maintenance; Functions: Traffic Services Fire and Disaster Management Library Services Environmental Health and Cleansing; Functions: Income and Revenue Management Expenditure Management Supply Chain Management. Legal Services Labour Relations Council Support Information & Communications Technology (ICT); Planning, development and maintenance of roads, streets and storm water infrastructure Planning, operation and maintenance of water reticulation systems and sewerage treatment infrastructure Management of civil engineering contracts and projects; Sport, Recreation, Arts and Culture; Budget and Reporting Asset management Contract Management Risk management and internal controls.

Municipal Manager: T. Klaas	                     Chief Financial Officer: J. Krapohl

Director of Safety and Community Services                    Director of Corporate Services

Director of Infrastructure Planning and Development

## COMPONENT B: INTERGOVERNMENTAL RELATIONS

INTRODUCTION TO CO-OPERATIVE GOVERNANCE AND INTERGOVERNMENTAL RELATIONS

The SRVM IGR structure is functional, and it meets once per quarter. It is under the office of the mayor, and it is chaired by the Mayor and Municipal Manager responsible for secretarial and administrative support. SRVM participates in the local, district and provincial IGR structures. The effectiveness of the forum can be measured by implementation of resolutions and great attendance by sector departments, the private sector and other community stakeholders and successful partnerships in developmental projects.

### 2.3	INTERGOVERNMENTAL RELATIONS

PROVINCIAL INTERGOVERNMENTAL STRUCTURE

SRVM participates in the following Provincial Intergovernmental Relations:

- Premiers Coordinating Council

- Technical and Political MUNIMEC comprising of the province and all local municipalities in the Eastern Cape

- Provincial Speakers’ Forum

- District Mayor’s Forum

- COGTA and Treasury engagements

- District Water and Infrastructure Forum

- District Development Model Forum

RELATIONSHIPS WITH MUNICIPAL ENTITITIES

At a local level, the municipality still has some challenges of which some are a competency of sector departments. These challenges have been recurring since the previous fiscal year:

- Sewer pipe connections for housing development which result in sewer overspill.

- Poor road infrastructure

- Housing development

- Land for emerging stock farmers.

- Formalization of informal settlements

- Land audit and access to land for development.

- Formal clinic for Enon-Bersheba community

DISTRICT INTERGOVERNMENTAL STRUCTURES

We further participate in the following District Intergovernmental Relations:

- IGR Forum

- IDP Representative Forum

- District Support Team

- District Mayors’ Forum

- Municipal Managers’ Forum

- Chief Financial Officers’ Forum

- District Wide Infrastructure Forum

- District Communicators’ Forum

- Provincial Communicators’ Forum

- Chief Auditors Forum

- District SMME Coordinating Committee

COMPONENT C: PUBLIC ACCOUNTABILITY AND PARTICIPATION

OVERVIEW OF PUBLIC ACCOUNTABILITY AND PARTICIPATION

The municipality holds public meetings where the IDP is presented and take comments or inputs from community members on the services they would like to receive in each financial year. Ward Councillors also hold meetings in their respective wards to provide feedback and listen to the needs of their communities. There is an official Facebook page, WhatsApp Channel, TikTok, where the municipality posts about its service delivery programmes, notices about service delivery challenges and any other relevant information. The municipality is also making use of WhatsApp line to receive complaints and general enquiries.

### 2.4	PUBLIC MEETINGS

COMMUNICATION, PARTICIPATION AND FORUMS The municipality holds public meetings where the IDP is presented and take comments or inputs from community members on the services they would like to receive in each financial year. These meetings are hosted in all wards. There is an official Facebook page where the municipality posts about its service delivery programmes, notices about service delivery challenges and any other relevant information. The municipality is also making use of WhatsApp line to receive complaints and general enquiries. Due to budget constraints, the municipality is unable to purchase space in the media to communicate its programmes, however, to mitigate this the Communications Unit utilizes news coverage to communicate its programmes. Media entities we have relations with include the SABC, Mpuma Kapa TV, Nkqubela FM, EC Daily News Digital Platform, Die Burger, Uitenhage Express and Herald newspaper which runs print and online. We have a functional and updated website which assists in amplifying the voice of the municipality. The municipality produces information pamphlets and posters which are distributed to public spaces and posted in visible places across the Valley. During emergencies we also communicate through loud hailing.

WARD COMMITTEES

The function of ward committees resides with the Office of the Speaker. The corporate Services department is responsible for secretariat services of ward committee meetings. The schedule of ward committee meetings was developed. Notices are sent out for the meeting. There are minutes and attendance registers for the meetings that are set.

List of meetings.

COMMENT ON THE EFFECTIVENESS OF THE PUBLIC MEETINGS HELD:

- There is poor attendance in some wards by community members.

- Some members of the ward committees are not active in the community and the forums they represent are not holding them accountable.

- Not all issues of ward committees find expression to council.

- Some ward councilors are not holding feedback meetings in their constituencies.

The implementation of civic education programmes remains a challenge with officials clashing with Ward Councillor’s / Speaker on their roles and functions and this needs to be addressed. The Public Participation Units is not fully staffed, and this remains a challenge which impacts the unit’s ability to conduct its function effectively.

### 2.5	IDP PARTICIPATION AND ALIGNMENT

| IDP Participation and Alignment Criteria* | Yes/No |
| --- | --- |
| Does the municipality have impact, outcome, input, output indicators? | Yes |
| Does the IDP have priorities, objectives, KPIs, development strategies? | Yes |
| Does the IDP have multi-year targets? | Yes |
| Are the above aligned and can they calculate into a score? | Yes |
| Does the budget align directly to the KPIs in the strategic plan? | Yes |
| Do the IDP KPIs align to the Section 57 Managers | Yes |
| Do the IDP KPIs lead to functional area KPIs as per the SDBIP? | Yes |
| Do the IDP KPIs align with the provincial KPIs on the 12 Outcomes | Yes |
| Were the indicators communicated to the public? | Yes |
| Were the four quarterly aligned reports submitted within stipulated times? | Yes, miss deadline |
| * Section 26 Municipal Systems Act 2000 |  |

## COMPONENT D: CORPORATE GOVERNANCE

OVERVIEW OF CORPORATE GOVERNANCE

### 2.6	RISK MANAGEMENT

To achieve of Municipal objectives

-The executive management will at any time know where & what are the critical risks within the municipality.

-To enhance informed decision-making processes.

-To ensuring compliance with laws and regulations

-To close of gaps that can slow the processes.

-To reduces operational surprises and losses.

-To manage resources effectively.

The following are the top five risks identified in the Municipality.

1           Inability to maintain electricity infrastructure.

2           Lack of contract agreement with chemical suppliers and water testing laboratory

- Ineffective waste management

- Noncompliance with legislation and bylaws by the municipality

- Poor bylaw enforcement

### 2.7	ANTI-CORRUPTION AND FRAUD

The municipality developed a fraud prevention plan that is in draft stage, and it require approval by Council.

The following are the key fraud risk areas identified within the municipality.

1 SCM

2 Asset management

3 Human resources and Payroll

4 Revenue management

5 Expenditure management

6 Fleet management

7 ICT

There were processes/ controls put in place to manage or mitigate risks occurrence on the above areas which are:

Approved policy on Anti-Fraud and corruption

Segregation of duties

Security system in place

Anti-virus in place

Approved Password Policy

Approved ICT Strategy in place

'Tracking

Approved litigation policy

Trip authorities

Monthly monitoring of tracker reports

Logbooks

Overtime policy

HR officers to run operations.

It should be noted that during 2022.23 fiscal year Payroll staff were suspended due to fraud signals identified on the payroll run.

### 2.8	SUPPLY CHAIN MANAGEMENT

The municipality has a Supply Chain Management Policy, and it incorporates the recent amendment of B-BEE Regulations which came into effect on the 1st of April 2017. The internal control environment is not so strong, and it needs some improvements.

All the bid committees are in place and sufficient warm bodies are employed to ensure adherence to procurement regulations. Training has been provided for SCM unit to capacitate officials ensuring improved service delivery.

### 2.9	BY-LAWS

### No by-laws were introduced during the year.BY LAWS OUTDATED need to be revieD

### 2.10	WEBSITES

We do have a functional website, and it is up to date.

### 2.11	PUBLIC SATISFACTION ON MUNICIPAL SERVICES

There was one public satisfaction survey conducted in the current financial year. Generally, people are not satisfied with the services that the municipality is rendering. The evidence to that is received during community consultation on IDP ward priorities. More than 80% of ward priorities are issues that are recurring and not implemented. There is currently very minimal to no protest in SRVM. There are 3 outstanding petitions (Enon-Bersheba Petition, Zuney Petition, Nomathamsanqa Petition. Petitions are directed to the Offices of the Speaker and Municipal Manager to ensure they are resolved.  Petitioners are kept informed on the status of petitions on a regularly basis and after every Petitions Committee Meeting.

# CHAPTER 3 – SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT PART I)

INTRODUCTION

The Infrastructure & Planning Department is responsible for the delivery service of the Sundays River Valley Municipality. The Department compromises of the KPA’s are listed below:

Project Management Unit

Water & Sanitation

Roads & Stormwater

Electricity

Town Planning & Housing

The following are priority problems that need to be addressed as a matter of urgency.

Old, dilapidated, and Irreparable infrastructure (Roads & Stormwater, Water and Sewer Pipelines, Water & Sewer Treatment Works)

Poorly planned, poorly designed infrastructure (with inherent challenges)

Neglected infrastructure (due to poor or no maintenance and insufficient finances to eradicate the backlog.)

Services provided at a loss resulting in loss of revenue due to water losses and illegal electricity connections.

Vandalism to all Infrastructure assets (Water & Waste Treatment Works Plants, theft of high mast lights cables, Copper from overhead lines)

Rapid illegal growth of informal settlements due to population growth that Is not catered for.

No Land audit to identify pockets of land for development.

The Infrastructure Planning and Development is guided by the strategic objectives below:

Upgrade electricity network for future development.

Ensure access and continuous supply of excellent quality water and sanitation to each user by 2030.

Ensure SRVM communities have access to excellent quality roads built according to applicable standards.

To ensure complaint reporting in all aspects of all grants.

To promote programmes of shared economic growth, land redistribution and general economic redress for the poor and disenfranchised.

To enhance internal capacity to improve service delivery performance.

2024/2025 Capital Projects

Sundays River Valley Municipality will receive R 39 150 000.00 to implement its capital commitments. Below are the projects to be implemented:

| MIS NUMBER | PROJECT NAME | MIG AMOUNT REGISTERED (Rands) | BUDGETED IN 2024/25 |
| --- | --- | --- | --- |
| EC2017/18/03/23 | Upgrading of Roads & Stormwater in Enon and Bersheba – Phase 2 | R 24 354 663,94 | R 11 069 402.00 |
| CS/EC/2020/21/11/67 | Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo Phase 1 | R 24 337 418,58 | R 3 625 496 |
|  | Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo Phase 2 | R 10 000 000.00 | R 10 000 000.00 |
| CS/EC/2020/21/11/68 | Construction of a New Community Hall in Moses Mabhida (Budget Maintenance) | R 23 480 697.00 | R 2 348 070.00 |
| EC/2021/22/12/147 | Refurbishment of Enon and Bersheba Water Borne Sanitation- Phase 1 | R 13 948 110,00 | R 4 990 690.00 |
| R/EC/19575/21/22 | Emergency flood works in Vygie and Adam Street | R 8 861 405,00 | R 2 446 218.00 |
| EC/2022/23/11/155 | Infrastructure Asset Management | R 1 500 000,00 | R 752 500 |
| R/EC/20298/24/25 | Construction of Roads and Stormwater in Paterson | R 23 851 282,00 | R 1 384 956.00 |
| EC/2024/24/11/369 | Augmentation of the water reticulation network in Paterson | R 16 572 000.00 | R 1 467 804.00 |
| N/A | PMU Administration | R 1 496 050,00 | R 1 556 460.00 |
| TOTAL |  |  | R 39 150 000 |

Water & Sanitation

The municipality is both a water services authority and a water services provider. The municipality is in a process of reviewing the WSDP as per Water Services Act 108 of 1997.Sarah Baartman District Municipality is assisting the Sundays River Valley Municipality & other local municipalities in reviewing a Water Services Development Plan and will be submitted to for Council approval. According to the 2022 community survey, SRVM population is approximately 53 256 people within 19 017 households (HH) residing within the Sunday's River Valley Local Municipality. The average number of people per HH is 3,5.

SRVM is responsible for ensuring that efficient, quality, affordable, economical, and sustainable water services are accessible to all the communities.

Kirkwood & Surroundings: Water is purchased from the Lower Sundays River Water Users Association to a raw water catchment storage. Raw Water is then pumped to the Kirkwood Water Treatment, Addo Nomathamsanqa, Enon-Bersheba Plants where it is purified as per SANS Standard 241: 2015 of drinking water. Purified Water is then stored in reservoirs for distribution to the Kirkwood Town, Bergsig, Aqua Park, Moses Mabida and Emsengeni Communities.

· Addo & Paterson: Raw water from the canal is channeled into Caesar’s Dam. From Caesar’s Dam raw water is pumped to the Addo Water Treatment Plant where it is purified to SANS Standard 241:2015 for drinking water. Purified Water is then pumped into reservoirs and distributed to Addo Town, Nomathamsanqa, Noluthando, and Langboos. The same water is also pumped to Paterson through a 35km rising main and then stored in retention reservoir and elevated tower.

· Enon & Bersheba: Raw water from the canal is channeled into the Dam water is gravitated into the Enon/Bersheba Water Treatment Plant where it is purified as per SANS 241:2015 of drinking water standard. Purified water is pumped into water reservoirs where it is stored and gravitated to Enon and Bersheba Communities.

· Glen Connor: Raw water is pumped from the boreholes to elevated tank, treated, and distributed to communal standpipes.

· Kleinpoort: Raw water is pumped from the boreholes to elevated tank, treated, and distributed to communal standpipes.

· Zuney: Raw water is pumped from the boreholes to elevated tank, treated, and distributed to communal standpipes.

The SRVLM has identified the following challenges with respect to water provision and supply:

· Kirkwood WTW: - Currently under capacity due to population growth. - Raw water storage capacity is insufficient, and unable to sustain for a period more than 48hours - Clean Water Storage Reservoirs not sufficient to last for a period more than 48 hours. This results in water shedding; however, the Department of Water & Sanitation has initiated an augmentation project to address water shortages.

· Paterson Bulk Water Supply: Paterson Bulk is still problematic due to the Caesars water treatment works project that is incomplete.

· Enon & Bersheba Bulk Reticulation: Enon and Bersheba are serviced with poorly aligned bulk and distribution pipe system which leads to low pressures, high pressures, and inherent pipe bursts.

Bulk Water Supply Analysis

· Exponential Growth of Greenfields & Informal Settlements: Due to growing levels of informal settlements the valley has been challenged to meet the infrastructure requirements.

| NO. |  | TOWN |  | TOTAL WATER DEMAND |  |  | TOTAL WATER SUPPLY |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. |  | Kirkwood |  | 5.2.0 ML/ day |  |  | 4,0 ML/day |
| 2. |  | Addo |  | 7.7 ML/day |  |  | 5,0 ML/day |
| 3. |  | Enon Bersheba |  | 3,2 ML/day |  |  | 3,3 ML/day |
| POTABLE BULK WATER SUPLY STATUS OF BOREHOLES |  |  |  |  |  |  |  |
| NO. | BOREHOLE NAME |  | SAFE SUSTAINABLE YIELD (L/S) |  | OPERATIONAL (YES/NO) | COMMENTS |  |
| PERSTON |  |  |  |  |  |  |  |
| 1. | Glen Connor |  | 0.56 |  | Yes | Borehole has high levels of calcium and magnesium. Functional Functional Due to cable theft & vandalism it is now non-functional, however a business proposal has been submitted for funding. Functional |  |
| 2. | Kleinpoort |  | 0.86 |  | Yes |  |  |
| 3. | Zuney |  | 1.94 |  | Yes |  |  |
| 4. | Paterson X5 |  | 0.94 |  | Decommissioned |  |  |
| 5 | Bergsig |  | 1.2 |  | Yes |  |  |

The Sundays River Valley Municipality’s Green Drop Score currently stands at 0% due to dysfunctional wastewater treatment works and the score for Blu drop is 92% which is below the required 95%. The Process Controllers and plumbers are in training with LGSETA facilitated by Sarah Baartman district municipality and this will improve the blue drop status. The WSDP is being reviewed for approval by the Council, and it will be implemented, and this will improve the blue drop status score.

The Sunday Rivers Valley Green Drop Improvement Plan (GDIP) provides a system-specific work-plan to improve the Green Drop score of each of the 4 wastewater systems which are:

· Kirkwood: Kirkwood services the Greater Kirkwood WWTW which is located south of Moses Mabida. This works now serve the whole of the town as the old Kirkwood WWTW was decommissioned. A pump station at the old Kirkwood WWTW pumps the sewage from Kirkwood to the WWTW at Moses Mabida.

· Addo & Surrounds: The WWTW in Addo consists of a large oxidation pond with a single floating aerator.

· Paterson: Paterson is served by oxidation ponds with a design capacity of 0.5ml/day.

· Enon & Beersheba: The WWTW in Enon/Bersheba consists of 7 evaporation ponds situated on the outskirts of the town.

Green drop score improvement include:

The refurbishment of Kirkwood WWTW is underway.

The project will include construction of emergency ponds at Kirkwood WWTW with all security measures.

Construction of gravity Wastewater ponds in Addo and include both water and sewer bulk and internal reticulation.

Refurbishment of Enon and Bersheba water borne sanitation -phase 1

Construction of Langboos and Molly Outfall Sewer

Development of Infrastructure and equipment Maintenance plan that includes preventative, planned and daily maintenance.

Blue drop score improvement include:

Implementation and monitoring of the Water Safety Development Plan.

Training of Process Controllers and plumbers through LGSETA facilitated by Sarah Baartman District Municipality

SANS 241:2015 compliance

Water purification Chemical compliance

Water and wastewater infrastructure maintenance implementation.

| Compliance Status | Interventions |  |
| --- | --- | --- |
|  | Short Term | Long Term |
| Green Drop Score (2021/2022) = 0 % Lack of Infrastructure within informal settlements and ageing infrastructure | The refurbishment of Kirkwood WWTW completed Business Plans to be submitted for funding proposals | The project will include construction of emergency ponds at Kirkwood WWTW with all security measures. Implement projects and make sure that all SRVM communities have access to basic services |
| Blue Drop PAT Score 2021= 68 % | All Treatment Works have been Classified. Installation of Inflow Meters at WTW &WWTW’s 25/26. Reviewed Water Safety Plan to be Approved by Council Development &Implementation of O & M Plan in all WTW & WWTW’s.25/26 | Compliance in all WTW Upgrade of Kirkwood Raw water storage reservoirs through RBIG |

2024/2025 Capital Projects

Sundays River Valley Municipality will receive R 39 150 000.00 to implement its capital commitments. Below are the projects to be implemented:

| PROJECT NAME | WSIG AMOUNT REGISTERED (Rands) | BUDGETED IN 2024/25 |
| --- | --- | --- |
| Refurbishment of Kirkwood and Addo Wastewater Mid-Pump Station | R 15 957 796.81 | R 6 419 796,00 |
| Provision of Water and Sanitation services of Nomathamsanqa and Molly Blackburn | R 6 507 688,49 | R 4 507 689,29 |
| Refurbishment of Addo Sewer Treatment Works and Moses Mabhida Sewer Reticulation | R 15 072 514,71 | R 5 072 514,71 |
| TOTAL |  | R 16 000 000 |

ROADS & STORMWATER

Introduction

This report outlines the performance of the Roads and Stormwater Section for the 2024/5 financial year. The roads and stormwater section has achieved 63% of its predetermined SDBIP targets, navigating significant challenges including budget shortages on operational expenditure and additional work during the year.A total of 2055 potholes were repaired for the 2024/5 financial year.

Primary challenges were severe vandalism of stormwater grate covers, damage to double-kerb inlets, delays in procurement, and an unsustainable infrastructure maintenance backlog, now estimated at R56 million as per the latest draft of the roads and stormwater maintenance plan.For the 2025/2026 financial year, key priorities are the completion of Upgrading of roads and stormwater in Enon/Bersheba Phase 2, Construction of roads and stormwater in Paterson , the implementation of a new Pothole Patching Programme using innovative jet-patcher(rental) technology, and a detailed assessment of the stormwater network in the flood-prone Zone 4, Nomathamsanqa main road(Next to the stadium), Paterson and Valencia(Vygie street) area. An urgent motivation for additional funding is required to address the critical backlog.

1. SECTION MANDATE

The Roads and Stormwater Section is mandated to provide, maintain, and manage the municipal road network and stormwater drainage system. This ensures safe mobility for residents and protects municipal and private property from stormwater damage. Our operations cover approximately the total road network within the Sundays River Valley, and the jurisdiction of the municipality comprises 142.26km, of which 46.51km (or 32.7%) are paved roads and approximately 10 km of formal stormwater infrastructure across the Sundays River Valley Municipal area.

Length of Road (km) per Surface by Town

2. Organisational Structure & Human Resources

- Permanent staff: 8 (including 1 x manager(vacant), 1 x technician, 1 x supervisor, 2 x plant operators, and 3 x general workers).

- EPWP staff: 20 workers engaged in road maintenance and stormwater clearing which were contracted on 3 months intervals.

- Skills Development:

  - 10 workers trained in pothole patching.

Challenges:

- Shortage of permanent/long term contracted skilled workers (bricklayers, kerb-installers, pipe layers).

- Roads & stormwater manager position not yet filled.

- Vehicle(truck with a crane mounted).

3. PERFORMANCE AGAINST SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP)

| SDBIP Key Performance Indicator | Annual Target | Actual Performance | Variance | Reason for Variance |
| --- | --- | --- | --- | --- |
| Upgrading of roads and stormwater in Enon/Bersheba Phase 1 | Please contact PMU for more information |  |  |  |
| Construction of roads and stormwater in Paterson | Please contact PMU for more information |  |  |  |
| Rehabilitation of internal streets | 1 km | 0 km | 1 km | Still procuring material. Currently100 Parlett’s of interlocking bricks and 100ton of sand purchased. |
| Number of potholes repaired | 2,000 | 2055 | +55 | Higher-than-average rainfall led to increased road surface failures. Target exceeded due to additional material donated by SANRAL. |
| Gravel streets blading | 96.7km | 60km | -36.7 | Not enough budget, machine breakdown(blade purchase) |
| Installation of speedhumps and signs across the Valley | 19 & 38 | 19 & 38 | 0 | Successfully completed July 2024. |

3.1 UNPLANNED OR ADDITIONAL WORK COMPLETED

On March 12, 2025, a protest action by the local Taxi Association took place in Nqweba. The strike was initiated in response to the deteriorating condition of key access roads, which posed significant risks to public safety and vehicle maintenance.

The protest specifically highlighted the poor state of District Road 02006 (DR02006), a critical thoroughfare connecting the Moses Mabhida and Eno/Bersheba communities. While this road does not fall under the direct jurisdiction of the Nqweba Local Municipality's road network, its daily use by local residents necessitated immediate intervention.

To address the situation and facilitate an end to the strike, the Executive Mayor of the Municipality facilitated a meeting with the Taxi Association. An agreement was reached whereby the Municipality’s Roads section would deploy resources for emergency pothole patching on DR02006. This action was taken as an interim measure to ensure public safety while the appropriate road authority responsible for the long-term maintenance of the route is formally identified and engaged.

The intervention resulted in the use of approximately 700 bags of 30kg asphalt mix to conduct extensive pothole repairs along the affected stretch of road. This proactive measure successfully mitigated the issue and restored a level of serviceability to the route, allowing for the resumption of normal public transport operations.

4. DETAILED OPERATIONAL REVIEW

A. ROADS AND STORMWATER ASESSMENT AND MAINTENANCE

1. ENQWEBA/TOWN

8.5km assessed(paved)

| STREET | DISTANCE (Apprx) | POTHOLES (mm dia) |  | CRACKS (m) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 50-300 | 301-3m |  | Q1 | Q2 | Q3 | Q4 | VARIANCE |
| Whytesweg | 1km | 234 | 0 | 100 | 0 | 100 | 100 | 34 | 0 |
| Angle | 380m | 88 | 5 | 0 | 0 | 20 | 20 | 35 | 13 |
| Middle | 550m | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 |
| John | 1km | Beyond repair |  | - | 0 | - | - | - | - |
| Shand | 680m | 0 | 5 | 0 | 0 | 0 | 4 | 1 | 0 |
| Mark | 330m | Beyond repair |  | 660 | 0 | - | - | - | - |
| Searle | 1km | 330 | 155 | 0 | 0 | 91 | 174 | 0 | 220 |
| Isabel | 680m | Beyond repair |  | - | 0 | - | - | - | - |
| McDonald | 680m | 0 | 0 | 0 | 0 | - | - | - | - |
| Mimosa | 500m | 0 | 0 | 0 | 0 | - | - | - | - |
| Skoolsingel | 400m | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17 |
| Voortrekker | 490m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Harrod | 300m | Beyond repair |  | - | 0 | - | - | - | - |
| Oranjesingel | 570m | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 |
| TOTAL | 8,5km | 672 | 167 | 0 | 0 | 211 | 298 | 75 | 253 |
| TOTAL POTHOLES= |  | 839 |  | ACHIEVED= |  | 584 |  |  | 253 |

Summary:  70% achieved in this area and 30% variance.

note: Majority of the roads in this area are damaged beyond repair and is deemed wasteful to repair. Hence the Rehabilitation of internal streets project.

1.1 STORMWATER MAINTENANCE

8 Inlet/outlets assessed and 2km of stormwater channel

| AREA | TASK TYPE |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  | VARIANCE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | INLETS | CHANNEL |  |  |  |  |  |  |  |  |  |  |
| Town | 16 | 2km | 4 | 250 | 4 | 250 | 4 | 250 | 4 | 250 | 0 | 1km |
| TOTAL | 32 | 12 | 4 | 250 | 4 | 250 | 4 | 250 | 4 | 250 | 0 | 1km |

Summary: 100% achieved for the inlets, 50% achieved for the channels and half the streets are not accessible due to damage to the aging infrastructure, residents deliberately blocking channels due to complaints of residents drinking and sitting on the channels etc. Channels and inlets are cleaned every quarter and when required, especially if there is a possible heavy rain warning forecast.

2. BERSIG

1540m assessed(paved)

| AREA | DISTANCE (APPRX) | POTHOLES(DIA) |  | Not applicable |
| --- | --- | --- | --- | --- |
|  |  | 50-300mm | 301-3m |  |
| Arend | 800 | 0 | 0 |  |
| street 1 | 150 | 0 | 0 |  |
| Berggans | 290 | 0 | 0 |  |
| street 2 | 300 | 0 | 0 |  |
| TOTAL | 1540 | 0 | 0 |  |

Note: paved roads in the area are still in a good condition and requires not major works.

3. AQUA-PARK

1920m assessed(paved)

| AREA | DISTANCE (APPRX) | POTHOLES(MM DIA) |  | Not applicable |
| --- | --- | --- | --- | --- |
|  |  | 5-300 | 300-3m |  |
| Eureka drive | 1800 | 0 | 0 |  |
| street 1 | 60 | 0 | 0 |  |
| street 2 | 60 | 0 | 0 |  |
| TOTAL | 1920 | 0 | 0 |  |

Note: No major works identified in this area.

4. MOSES MABIDA

4950m assessed

4.1 POTHOLE REPAIRS

| AREA | DISTANCE (APPRX) | POTHOLES(DIA) |  | Q1 | Q2 | Q3 | Q4 | VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 5-300mm | 300-3m |  |  |  |  |  |
| Entrance road | 800 | 0 | 2 |  | 2 |  |  |  |
| Chris Hani | 2200 | 215 | 388 | 0 | 279 | 111 | 213 | 0 |
| Taxi loop | 1200 | 0 | 0 | - | - | - | - | - |
| Emsengeni Entrance road | 400 | 275 | 129 | 0 | 0 | 150 | 254 | 0 |
| TOTAL | 4200 | 490 | 519 | 0 | 281 | 261 | 467 | 0 |
| TOTAL POTHOLES= |  | 1009 |  | ACHIEVED= | 1009 |  |  |  |

Summary: 100% achieved on the assessed potholes.

Note: New potholes can surface and patched potholes can resurface due to numerous factors like weather damage, design failure, poor workmanship, road user factors etc.

4.2 STORMWATER MAINTENANCE

44 manhole assessed

| AREA | NO. OF MAHOLES | TASK TYPE |  | Q1 | Q2 | Q3 | Q4 | VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | UNBLOCKING | CLEANING |  |  |  |  |  |
| Chris Hani | 44 | 32 | 12 | 15 | 11 | 8 | 7 | 3 |
| TOTAL | 44 | 32 | 12 | 15 | 11 | 8 | 7 | 3 |
| TOTAL MANHOLES= |  | 44 |  | ACHIEVED= | 41 |  |  |  |

Summary: 93% achieved

Note: the remaining 7% require extensive work and rebuilding.

4.3 INLETS CONDITIONAL ASSESSMENT

| AREA | NO. OF MAHOLES | CONDITION |  |  |
| --- | --- | --- | --- | --- |
|  |  | GOOD | FAIR | BAD |
| Chris Hani | 44 | 11 | 18 | 15 |
| TOTAL | 44 | 11 | 18 | 15 |

Comment: Due to the following reasons:

- Vehicle damages: Buses and trucks from the nearby farms and packhouses  when dropping off their workers, they drive on top of the manholes and cause damage to the infrastructure.

- Vandalism: Residents just break the covers for no known reasons and throw stones and rubble inside which causes blockages later.

5. NOMATHAMSANQA

4300m assessed

| Area | distance (Apprx) | potholes(mm dia) |  | Q1 | Q2 | Q3 | Q4 | VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Nomathamsanqa |  | 0-300 | 300-3m |  |  |  |  |  |
| Main road | 4300 | 196 | 235 | 0 | 238 | 0 | 0 | 193 |
| TOTAL | 4300 | 196 | 235 | 0 | 238 | 0 | 0 | 193 |
| TOTAL POTHOLES |  | 431 |  | ACHIEVED= | 238 |  |  | 193 |

Summary: 55% achieved and 45% not achieved due to being chased by certain community members due to them requesting to be serviced only by workers from that area.

6. VALENCIA

2530 assessed

| AREA | DISTANCE (APPRX) | POTHOLES(DIA) |  | Q1 | Q2 | Q3 | Q4 | VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 0-300mm | 300-3m |  |  |  |  |  |
| Aloes | 390 | 44 | 19 | 0 | 63 | 0 | 0 | 0 |
| Billes | 760 | 10 | 0 | 0 | 0 | 0 | 0 | 10 |
| Entrance | 450 | 116 | 36 | 0 | 100 | 23 | 0 | 29 |
| Crous | 930 | 9 | 29 | 0 | 38 | 0 | 0 | 0 |
| Wilger | 350 | 12 | 3 | 0 | 0 | 0 | 0 | 15 |
| TOTAL | 2880 | 201 | 87 |  | 201 | 23 | 0 | 54 |
| TOTAL POTHOLES= |  | 288 |  | ACHIEVED= | 224 |  |  | 54 |

Summary: 77% completed and 23% not completed.

Note: this area experiences flooding, blockages and leaks which require constant patching.

7. PATERSON

2227 assessed

| AREA | DISTANCE (APPRX) | POTHOLES(DIA) |  | Q1 | Q2 | Q3 | Q4 | VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 0-300mm | 300-3m |  |  |  |  |  |
| Butchner | 2227 | 366 | 312 | 0 | 0 | 0 | 0 | 678 |
| TOTAL | 2227 | 366 | 312 |  |  |  |  | 678 |
| 678 |  |  |  |  |  |  |

Summary: Lower entrance of this road requires resurfacing not patching hence it has 100% variance.

5. PICTURES OF THE WORKS

6. OVERALL SUMMARY

A. POTHOLES BY AREA:

| AREA | POTHOLES ASSESED | POTHOLES ACHIEVED |
| --- | --- | --- |
| Kirkwood/Town | 839 | 584 |
| Aqua-park | 0 | 0 |
| Bergsig | 0 | 0 |
| Moses Mabida | 1009 | 1009 |
| Nomathamsanqa | 431 | 238 |
| Valencia | 288 | 224 |
| Paterson | 678 | 0 |
| 3246 | 2055 |

Overall performance for pothole repairs is: 63%

Pothole Repairs: 2055 repairs completed, utilizing 120 tons of asphalt(60 tons hot mix and 60 tons cold mix) excluding the unbudgeted DR02006 project.

Surface Roads: 50m section in Addo Nomathamsanqa main road rehabilitated, including a portion in Kirkwood/Town that was added a finishing layer of 200 x 100 x 80 interlocking pavers for an approximate of 90m².

B. STORMWATER INFRASTRUCTURE MAINTENANCE

| AREA | IN/OUTLETS ASSESED |  | CHANNELS |  | MANHOLES |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | target | achieved | target | achieved | target | achieved |
| Kirkwood/Town | 16 | 16 | 2km | 1km | - | - |
| Aqua-park | - | - | - | - | - | - |
| Bergsig | - | - | - | - | 6 | 0 |
| Moses Mabida | - | - | - | - | 44 | 41 |
| Nomathamsanqa | - | - | - | - | 3 | 0 |
| Valencia | 6 | 0 | 2km | 0.5km | 3 | 0 |
| Paterson | - | - | - | - | - | - |
| 72% |  | 38% |  | 73% |  |

Overall performance on stormwater infrastructure is: 61%

Stormwater Infrastructure:

- Routine Cleaning: 2km of pipes, 1km of open channels cleaned, 44 double-kerb inlets and channels cleaned, removing over 10-ton truck of debris and silt.

- Flood Response: Responded to 4 minor flood events due to heavy rains, deploying teams to unblock inlets and pump out flooded areas, notably in in Kirkwood/town and Zone 4(1 event).

- Road Signs & Markings: 20 road signs replaced and 1.5km of road markings painted for the Municipal testing route and general roads in both lower and upper valley.

C. GRAVEL ROADS

| AREA | STREETS BLADING per quarter |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |
|  | target | achieved | target | achieved | target | achieved | target | achieved |
| Kirkwood/Town | - | - | - | - | - | - |  |  |
| Aqua-park | 1km | 0.5km | 0.5km | 0 | 0.5km | 0 | 0.5km | 0 |
| Bergsig | 1km | 1km | 0km | 0km | 0km | 0km | 0km | 0km |
| Moses Mabida | 4km | 1km | 3km | 1km | 2km | 1km | 1km | 1km |
| Nomathamsanqa | 6km | 2km | 4km | 0km | 4km | 0km | 4km | 0km |
| Valencia | 8km | 2km | 6km | 2km | 4km | 2km | 2km | 2km |
| Langboos | 1km | 1km | 0km | 0km | 0km | 0km | 0km | 0km |
| Paterson | 8km | 0km | 8km | 3km | 5km | 0km | 5km | 0km |
| 25% |  | 27% |  | 19% |  | 24% |  |

Gravel Roads: routinely graded 29km(certain areas were bladed multiple times).

Summary: Overall performance is 24%
Reasons:

- Budget constraints.

- Difficult terrains for machinery navigation.

- Illegal water connections by residents and they refuse for blading.

- Brake down and turnaround time for repairs(blade and general repairs).

- Transportation issues for the grader.

7. Projects:

A. Completed: Speedhumps and signs installation across the valley.

| ITEM |  | MOSES MABIDA | BERSIG | ADDO | VALENCIA |  | PATERSON |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Speed hump |  | 8 | 2 | 3 | 3 |  | 3 |  |
| 2. Sign (with clamps) |  | 16 | 4 | 6 | 6 |  | 6 |  |
| 3. Pole |  | 16 | 4 | 6 | 6 |  | 6 |  |
| 4. Cement |  | 4bags | 1 bag | 1 | 1 |  | 1 |  |
| 5. Stone | 16(25kg bag) |  | 2(25kg bag) | 3(25kg bag) |  | 3(25kg bag) |  | 3(25kg bag) |

Speedhumps		: 19

Signs (with clamps)	: 38

Pole			: 38

Cement		: 8 bags

Stone			: 27 (25 kg bags)

B. Ongoing:

  - Upgrading of roads and stormwater in Enon/Bersheba Phase 1.

  - Construction of roads and stormwater in Paterson.

  - Rehabilitation of internal streets(procurement).

  - Pothole patching.

  - Stormwater infrastructure maintenance.

8. Assets & Infrastructure

Machinery fleet condition:

  - 1 Graders (fully functional).

  - 1 TLB – (fully functional).

Intervention: Request for a truck with a crane instead of a bukkie and a tip truck.

Hand-held machinery:

- 1 x Walk-behind roller

- 1 x Jumping jack

- 1 x Bitumen sprayer

- 1 x Plate compactor

- 1 x Tar cutter

9. Community Engagement

- Attended 1 ward meetings to address service delivery concerns and introduction of SANRAL contractor introduction to the public.

- Member of SANRAL PLC for the R335 Project.

- Community satisfaction is tolerable in majority areas where maintenance and capital projects are implemented

10. Health, Safety & Compliance

- No major incidents reported.

- Safety talks were conducted with 20 EPWP workers.

- Compliance maintained with OHS Act, Municipal Bylaws, and Environmental Regulations

11. Overall challenges and constraints

- Staff shortage: Roads section is seriously experiencing shortage of permanent skilled manpower and requires urgent attention to address the issue.

- High service delivery demand exceeding available resources.

- Threats: Roads team has been threatened and chased away from the lower valley, Addo/Nomathamsanqa to be precise and the complaint is that they want a roads team that will specifically deal with the area and not have a team coming from Kirkwood to work in the area.

- Vandalism and Theft: The theft of 36 cast-iron stormwater grate covers (still to be replaced) and ongoing damage to manhole covers by citrus buses when dropping off their workers severely hamper service delivery and drain financial resources for replacing infrastructure.

- Illegal Dumping: Dumping in open channels remains a primary cause of stormwater blockages. Continuous public awareness is required.

- Aging Infrastructure: Much of the infrastructure show deterioration due to aging and is no longer fit for purpose, leading to frequent failures(roads and stormwater).

- Turnaround time to receive material delays: Delays in the Supply Chain Management process result in project delays and operational underspending.

12. Key Recommendations:

- Funding: The Municipality must add more operational allocation to address the critical maintenance and infrastructure rehabilitation backlog.

- Security: The Municipality must address the issue of protests in the lower valley for the safety of the roads team by looking at the item of having a team in for the lower valley as in the case of Water and sanitation section.

- Policy: Approve the following drafted policies:

  - Pothole Management Policy.

  - Permit Policy for Works within the Road Reserve.

  - Road and Stormwater Maintenance Policy.

  - Environmental Compliance Policy.

13. Conclusion

Despite operational and financial constraints, the section is determined to maintain a consistent level of service delivery. Strategic investment and addressing systemic challenges in procurement and security are crucial to improving the state of municipal infrastructure and meeting the community's growing expectations.

Electricity

Electricity Department

- High mast lights maintenance

- Streetlights maintenance

- Connection of new high mast lights

- High mast lights components request.

- Cable thieves

- Repairs of vandalized services

# 7.1.1 HIGH MAST LIGHTS MAINTENANCE

7.1.4 CABLES THEFT

Supplying cable theft incident at Kirkwood Raw Water Pump station

The whole communities of Kirkwood were affected (Aquapark, Bergsig, Moses Mabida, Emsengeni and Kirkwood town).

The above is the least cable theft incident which happened from 01 April 2023 to 30 June 2023.The department noticed a spike in cable theft incidents where every week there will always be one or two incidents of cable theft. Load shedding has also contributed to an increase in cable theft incidents. Cable theft incidents are reported to the SAPS (case numbers: 135 / 3 / 2023, 60 / 5 / 2023, 24 / 6 / 2023, 13 / 7 / 2023, and 14 / 7 / 2023).

Maintenance of Kiosk

CONTENT AND DISCUSSIONS:

- Network Reticulation challenges for LV and MV.

- The areas that need to be electrified ASAP.

The following work was not done.

- Electrical kiosk in Bergsig (old, damaged kiosk needs to be changed ASAP)

- Aquapark, Bergsig shacks and 7 Dee laan RDP houses (must be electrified and connected permanently ASAP to prevent electrical hazard for animals and people).

- Molly Village (please note that this area service by Eskom) at Nomathamsanqa (Project on going).

- Electrical breakdowns in Eskom areas reported and attended.

The following work was done.

- Call Eskom customer service to report power failure and faulty meters to assist SRVM communities that are supplied by Eskom (Nomathamsanqa, Valencia, Moses Mabida, Enon/Bersheba, Paterson Morrison, Kwazenzele & Zinyoka).

- Pre-Paid Meter

- Fines for illegal connection on pre-paid meters

The following work was done.

- Paid fines (7)

- Unpaid fines none

5.	New connection for high mast lights

Application completed for four high mast lights three in Nomathamsanqa and one in Paterson and we are waiting for Eskom to send the invoice. The quotation was accepted by the Municipality Manager and signed.

- The number of high mast lights that were maintained were 26 in total.

- Moses Mabida (2 in Platini and Bontrug) was 100% completed.

- Bersheba 3 high mast lights maintenance done.

- Nomathamsanqa (Addo 11) maintenance none and we are waiting for materials.

- Emsengeni (4) 90% NB: timer installed removed day and night switch done.

- Valencia (Addo 4) 90% NB: timer installed removed day and night switch done and one connected permanent to Eskom power supply.

- Number of high mast lights were fixed after was vandalized (5)

- Bersheba (3) Done and completed (materials were purchased and received)

- Moses Mabida (2) Done and completed (Zone 4)

6.         Pumps for Water Treatment work were vandalized

- Supplying cable theft incident at Kirkwood Raw Water Pump station

- The whole communities of Kirkwood were affected (Aquapark, Bergsig, Moses Mabida, Emsengeni and Kirkwood town).

7.       Pumps for Wastewater Treatment works were vandalized

- Pumps were vandalized. (Mid-pump station & Enon pump station)

8.         Other related issues and maintenance projects

- Service Provider must provide us with MV and LV single line diagram (for INEP projects) and no updates for informal settlement electrification (for all Aquapark shacks and Bergsig shacks)

9.          Maintenance at Municipal Buildings

- None

10.     Challenges

- Lack of material and tools (we need power tools, crane truck and Bakkie)

- Outstanding payment of Standby (from 31 July 2021 until April 2023).

- Lack of communication between Management and Staff (example Municipal Manager, CFO and HR Department they failed to communicate with the staff regarding overtime, standby, car allowances, cell phones, 2 laptops and one desktop) cut off overtime (Mr Moeti Taidile) by sending email for notice period.

- Finance must monitor all customers having pre-paid meter and most of the customers in town they bypass the Municipality boxes (e.g., 1. Finance department having access to the meter system and 2. They must give us all the customers that are not paying their rate for electricity cut off).

- Lack of communication between technical team (Electrical Team) and Finance Department (CFO Office) example 1. Finance purchasing electrical equipment’s and materials without consulting Technical Director, Senior Electricians, and IT Manager. 2 When we request materials for maintenance of High Mast lights and Street lights we are waiting too long.

- Cables Theft around Kirkwood town, Moses Mabida, Enon and Bersheba Water Treatment Works and Wastewater Treatment Works.

- Shortage of Staff Fault reporting Centre position (where number of faults reporting centres operating 24hours a day) to issue fault reference numbers to customers, obtain the name, telephone numbers, nature of fault and physical address of the customer and facility to redirect after hours calls.

- Shortage of Staff Artisan, electrical assistance, and general workers.

- Unsafety working conditions (because of employer does not provide workers with PPE).

- NB: We cannot climb some of the poles, because are rotten (service provider must transfer the LV line to the new poles).

- No storeroom to safely keep electrical materials.

- Finance department must assist technical department to processing of pre-paid meter registration on the system for all RDP houses and shacks in 7 De-Laan Aquapark.

- Our electrical team were chasing out by community to stop them not cutting off their illegal connection or straight connection on the kiosk until they got permanent connection supply by municipality.

- We have 30 RDP houses at 7 De-Laan that are getting straight connection from the vandalized kiosk and therefore 180 informal settlement they also connected illegal (76 in Bergsig and 104 in Aquapark shacks.

- There are 65 electricity kiosks at Bergsig needed to be replaced ASAP, because all these kiosks are very dangerous, unsafety and harmfully to the community more especially children and animals.

- We also have problem of the rotten Mini Sub-station, electrical poles around town, and this make it difficult for us to climb to those poles when we have fault because its note safety.

- Lack of maintenance capacity.

11. Causes of electrical losses

- The reasons for electricity losses are caused by a lot of houses that are not paying the bill to municipality because they are connected straight connections and illegal on the municipality line. There is also an increase in informal settlements where there are illegal connections available.

- Illegal connections in Aquapark at 7 De Laan RDP houses, Aquapark 7 De Laan shacks and Aquapark new shacks.

- Illegal connections in Bergsig shacks.

12. Complaints attended on daily basis

- Attending callout from customers.

- Faulty meters.

- Request for new connections for pre-paid meters.

- Customers request to change from KWH meter to pre-paid meter.

- Resetting timer and replacing day night for streetlights and high mast lights.

- Meter registration and filling of documents.

- Repair and joining faulty damaged underground cables.

- Attend emergency on overhead LV line damaged by heavy trucks.

Town Planning

A Municipal Spatial Development Framework (MSDF) is an important Municipal Policy instrument provided for in legislation. Spatial development planning is a process to co-ordinate and optimize human activities, which require physical space or have an impact on physical space. Physical planning is therefore a public sector function which aims to promote public investment and regulatory frameworks within which private sector and public sector decision making and investment can take place.

The following represents the SRV Municipality institutional mechanisms and tools for land use management and implementation. SRVM has become fully compliant with the Spatial Planning & Land Use Management Act 16 of 2013. The SRVM SDF/LUMS was completed in June 2023.

· Approved Spatial Planning & Land Use Management By-laws (No. 3635 dated 24 March 2016)

· Spatial Development Framework (2022) & Sundays River Vally Integrated Land Use Scheme approved by SRVM Council on 15 June 2023

· Zoning Maps dated 2004 and outdated

· Zoning Register kept, but not accurate.

· In-house GIS function not available

· SRVM has joined the District Municipal Planning Tribunal which is fully functional.

· A council resolution recommending the Appeal Authority be EXCO was recommended for approval.

### WASTE MANAGEMENT (THIS SECTION TO INCLUDE: REFUSE COLLECTIONS, WASTE DISPOSAL, STREET CLEANING AND RECYCLING)

INTRODUCTION TO WASTE MANAGEMENT

The setting of of National Domestic Waste Collection Standards, was informed by, among other pieces of legislation, the Constitution of Republic of South Africa(1996) and National Environmental Management: Waste Act, 2008(Act No. 59 0f 2008). The level of service rendered within SRVM area of jurisdiction by the method of supervised disposal as guided by Waste Management Officer (later known as Waste Management Practitioner). The municipality had is recently enjoyed the adoption of the approved Intergrated Waste Management Plan that is currently out for MEC endorsement; the plan is a corner stone for an effecient and effective waste management programme.

During the year 0 the municipality was operating with only two 4 tons refuse trucks which could not provide adequate coverage in areas such as Lower Valley (Addo,  Enon/Bersheba, Paterson and Langbos areas). In order to mitigate this the council had to outsource the refuse removal services to the service providers who were contracted on month to month basis(TO BE REMOVED) The street cleaning services were almost non-existent at these areas during this period mainly because of staff shortage. The introduction of EPWP programme through the support of Public Works department managed to bring more improvement as the municipal staff was beefed-up; furthermore Sarah Baartman District donated to the municipality with extra two refuse trucks.

The top four service deliveries entieties are as follows:

- Collection: which entails regular and consistent household refuse removal services. Each location enjoying once a week collection and provision of refuse bags to the residents on by-monthly basis.

- Refuse removal trucks: It is crucial that the SRVM refuse trucks are well serviced and maintained in good standard.

- Communication and Awareness: The seamless partnerships, working together with the local councillors proved to pay great rewards in ensuring that the community waste management needs are addressed; furthermore the close inter-departmental relations paved the way for successful interventions on addressing waste management services so is the positive role of other stakehlders.

- Greening: The greening programme entails maintanance of exsting municipal trees, planting of new trees within the valley as well as beautification of illegal dump sites and municipal yards.The tree maintanance programm is further guided by the recently introduced Sundays River Valley Municipal Tree Policy.

The municipality has a fully integrated waste management service which is executed by the department of Community Services. It comprises of household and business collection, transportation and disposal including the disposal of dead animals. Management and clearing of illegal dumps, street sweeping. Monitoring and introduction of recycling activities. Management of municipal owned trees and parks/open spaces. Community Service is responsible for the management of the three Landfill Sites, namely Emsengeni, Sunland and Paterson. Refuses are collected two days per week in business areas and once for residential areas per week. In the Lower Valley (Addo, Valencia, Nomathamsanqa, Paterson, Kwazenzele, Morrison) and Enon-Bersheba (Upper Valley) waste was collected by local Cooperatives but now it is collected by the municipality. The existing landfill sites are now operating with expired/outdated landfill sites licenses; in view of this there is a service provider that had been appointed to review conditions that will warrant the reinstatement of the expired licenses. Out of 13 576 households in our billing system, 100% have access to waste removal services.

The Department of Forestry, Fisheries and Environment is one of the important and significant municipal partners that contributed to poverty alleviation with its programme of employing more that two hundred participants for street cleaning and greening of the setllements within the SRVM. Secondly Department of Cooperative Governance and Traditional Affairs through the Community Works Programme (Job creation). This programme contributed to a remarkable reduction of dumpsites within the valley.

### 3.5	HOUSING

Project Name: Upgrading of Informal Settlements Programmes ( UISP)

NOSINI

1.Standpipes 0, Jojo Tanks 4, Pour flush Toilets 0, Communal Ablution Facility 1,Skip Bins 2

2.Zone 4[r[-r54

Standpipes 0,Jojo Tanks 4, Pour flush toilets 0,Communal Ablution Facilities 3, Skip Bins 3 Total 10

3.Behind Creche

Standpipes0, Jojo Tanks 2, Pour flush Toilets 0, Communal Ablution Facilities 2, Skip Bins 2, Total 6

Springane

Standpipes 8, Jo-jo Tanks 4, Pour Flush Toilets 8,Communal Facility 0,Skip Bins 0, Total 20

Platini

Standpipes tap 0,Jo-jo Tanks 4,Pour flush Toilets 0,Communal Ablution Facility 3, Skip Bins 3, Total 10

Orange Farm

Standpipes Taps 0,Jo-jo Tanks 2,Pour Flush Toilets 0, Communal Ablution facility 2,Skip Bins 0,Total 4

Molly Blackburn

Standpipes Taps 0,Jo-jo Tanks 4,Pour Flush Toilets 350,Communal Ablution facility 0,Skip Bins 4, Total 358.

Valencia

Standpipes Taps 4, Jo-jo Tanks 0, Pour Flush Toilets 86, Communal Ablution Facility 0, Skip Bins 3 Total, 93

Total Standpipes =12                                                      Skip Bins=17

Total Jo-jo Tanks=24                                                         Total =501,00

Total Pour Flush Toilets=444

Total Communal Ablution facilities=11

Deliverables to date

Nosini

1= Jo-jo Tank

ZONE 4

2= Jo-jo Tanks

SPRINGANE

= 2 Jo-jo Tanks

PLATINI

=2 Jo-jo Tanks

ORANGE FARM

=2 Jo-jo Tanks

MOLLYBLACKBURN

=4 Jo-jo Tank

102 Pour Flush Toilets

VALENCIA

=4 Standpipes

45 Pour Flush Toiles

### 3.8	TRANSPORT (INCLUDING VEHICLE LICENSING & PUBLIC BUS OPERATION)

INTRODUCTION TO TRANSPORT

The road transport function is administered by the Community Services directorate. The municipality is dependent on the district for transport planning through an Integrated Transport Plan. We have a unit for motor vehicle licensing and registration. Our Traffic Officers provide an excellent traffic law enforcement and licensing services. The municipality does not have its own public bus operation. However, bus services are rendered by private companies to transport employees of citrus industry. The municipality has provided taxi ranks in several areas across the valley, both in Kirkwood and Addo Central Business District.

## COMPONENT C: PLANNING AND DEVELOPMENT

### LOCAL ECONOMIC DEVELOPMENT OVERVIEW

Local Economic Development (LED) in Sundays River Valley Municipality plays a vital role in promoting inclusive growth, job creation, and sustainable development within the region. The municipality is strategically positioned to harness opportunities in agriculture, tourism, and small business development, particularly through support for SMMEs and cooperatives.

However, the implementation of LED initiatives faces significant challenges, primarily due to a shortage of staff and limited human resource capacity. Currently, the LED unit operates with minimal personnel, which constrains its ability to effectively plan, coordinate, and monitor development programs. Notably, only one official has been appointed specifically for SMME Development, which places considerable pressure on the unit to meet the growing needs of local entrepreneurs and emerging businesses. This staffing limitation underscores the urgent need for capacity enhancement to ensure that LED strategies are executed efficiently and that the municipality can fully realize its economic potential.

LED Strategy Development

The municipality’s LED Strategy is currently under review with the support of the Department of Cooperative Governance and Traditional Affairs (COGTA). This process has included consultations with various stakeholders to gather inputs and comments, ensuring that the strategy is responsive to local needs and priorities. The revised strategy is now in its final stages of completion and is expected to provide a more focused and actionable framework for economic development in the region.

SMME Development

SMMEs are a cornerstone of local economic growth and job creation. The municipality is in the process of updating its SMME Policy to better align with current economic realities and support mechanisms. Stakeholder consultations have commenced, and the policy is expected to be finalized in the next financial year.

To support coordination and planning, the municipality maintains an SMME database, which is updated regularly. This database serves as a key resource for identifying active businesses, tracking development needs, and facilitating access to opportunities. In addition, the municipality provides technical support to local small businesses, which includes:

Assistance with business registration and compliance

Guidance on accessing funding and government support programs

Capacity-building workshops and training sessions

Linkages to procurement opportunities within municipal and public sector projects

Despite these efforts, SMME development faces several challenges in the municipal area, including:

Limited access to funding and business support services

Inadequate infrastructure and market access

Low levels of business skills and capacity among emerging entrepreneurs

Insufficient coordination between government departments and development agencies

Economic Growth and Job Creation Initiatives

There are encouraging signs of economic activity and growth within the municipality. Road construction projects led by SANRAL have contributed significantly to local infrastructure development, while also creating employment opportunities. Additionally, various initiatives from other government departments, including the Expanded Public Works Programme (EPWP), have played a vital role in job creation and skills development for local residents.

These projects not only stimulate the local economy but also help build a foundation for long-term development by equipping community members with valuable skills and work experience.

LED Policy Framework

Local economic development and the drafting of the Sundays River Valley municipal LED strategy and priorities are guided by the principles and objectives of the National Development Plan, the New Growth Path, the National Spatial Development Perspective (NSDP), etc.

The LED Plan had ensured synergy and alignment with the objectives of national and provincial government programs.  In addition to the Constitution, several government policies and statutes are relevant to LED at the local government level.

The White Paper on Local Government (1998) reinforces the concept of developmental local government which is defined as:

“Local government committed to working with citizen and groups within the community to find sustainable ways to meet their social, economic and material needs and to improve the quality of their lives”  It further states that the powers and functions of local government should be exercised in such a way that it has maximum impact on the development of communities, to meet the basic needs of the poor and to grow the local economy. Due to its influence on local economies, local government needs a clear vision for the local economy and needs to work in partnership with local business to maximize job creation and investment by taking responsible steps to ensure the overall economic and social conditions of the locality are conducive to the creation of employment opportunities.

Relevance: The White Paper guides LED at a local government level, as it advocates support services and leadership in the field of economic development and provides a mandate for LED to create an enabling environment for sustainable economic growth.

The objectives and municipal performance for LED is depicted under the organizational scorecard in Component K

## COMPONENT D: COMMUNITY & SOCIAL SERVICES

This component includes libraries and archives; museums, arts, and galleries; community halls; cemeteries and crematoria; childcare; aged care; social programmes, theatres.

INTRODUCTION TO COMMUNITY AND SOCIAL SERVICES

SRVM Libraries form an important part of the services offered to the people of all communities including the disadvantaged ones. The entire community has the right to free access to the library and information services. The reason for this is that it promotes a culture of reading, library use and learning that enriches the whole community and to ensure that we accommodate people with disabilities (mini-lib services for the blind and partially sighted). Library Services ensures that this information is free, equitable and accessible to everyone.

Through our mobile library we assist underprivileged communities who cannot easily reach our libraries by providing free access. We also render our services to old age homes, pre-schools, local schools, and prisons by means of book loans.

### 3.12	LIBRARIES; ARCHIEVES; MUSEUMS; GALLERIES; COMMUNITY FACILITIES; OTHER (THEATRES, ZOOS, ETC)

##### LIBRARIES

Book Circulation

- Library Services is responsible for improving public library access to all communities. This is done by developing and sustaining a culture of reading and the provision of access to information of all throughout community of SRVM. This year we succeeded in rendering:

- Information resources in various formats, available for loans as well as reservation services for such resources.

- Research and reference resources in various formats for use in the library.

- Educational resources are supplementary to the formal education sector and for informal educational endeavors.

- Readers’ advisory and guidance services for library users of all ages and all educational levels.  Accepting that the vast amount of information that can be accessed via the Internet is of variable quality and accuracy, and thus it is the function of the librarian to guide users towards reliable information and resources that meet the users’ requirements.

- Exhibits and displays to promote library material and activities, and a reading culture.

Library Programs

SRVM libraries develop interest of using library Services to the community. The programmes provides a unique opportunity to improve public image within a service community and offers excellent collaboration opportunities with community leaders, groups and organizations that will enhance overall use and access of library services:

By doing storytelling to the nearest preschools

We partnered with local schools to include awareness-building of the value of libraries and reading, inculcating a culture of lifelong learning, and providing access to resources that are complementary to the formal educational sector. This includes building up a collection of career-oriented resources, both printed and electronic. Awareness campaigns such as celebrating library week, world read aloud day, career expo, national book week, and world play day, holiday program and international literacy day. These had an impact and opportunities to expose young library users to a wide range of fields and subjects (career expo) and for students to discover career interests and aptitudes.

##### COMMUNITY FACILITIES

Communities have a range of needs - social, cultural, recreational and informational. Strong and healthy communities are built on their capacity to meet these needs through encouraging participation, forming relationships and instilling a sense of belonging.

Thus, community facilities are not just about buildings and space – they are the arena for a range of services that provide opportunities for people to come together to meet, play, learn, share information and help each other. They are venues for arts, cultural, educational, recreational, and leisure activities, provide accommodation for voluntary groups, and are important gathering points in civil defense emergencies.

As the municipality it then becomes mandatory that as an institute to prescribe a set of norms and objectives for the management of these facilities that should align to:

The provision of a public facility to the local and wider community for recreation, community activities and services, training etc.

To ensure equitable access to diverse recreation and social opportunities across the Municipality.

To encourage multiple use of facilities.

To safeguard the community by taking appropriate measures to control risk.

To effectively manage assets held by municipality on behalf of the community.

To develop a sense of belonging and ownership amid constituencies

To build a sense of place/sense of community.

To provide an economic return to municipality commensurate with the use of the facility.

To manage facilities in an environmentally sensitive manner where appropriate.

The 2024/2025 financial year presented significant operational challenges for the Sundays River Valley Municipality (SRVM), particularly within the portfolio of parks, cemeteries, community halls, the municipal swimming pool, recreation facilities, and social amenities. Despite the municipality operating on an unfunded mandate, essential services were delivered within constrained financial resources, with a focus on maintaining community dignity, safety, and accessibility to public spaces.

This situational analysis provides a consolidated overview of the current state of facilities, performance gaps, and implications for service delivery under the Integrated Development Plan (IDP) Goal 1: Improve Infrastructure Quality and Accessibility, with the strategic objective that the community of SRVM will have access to sustainable and affordable recreational and sport facilities as well as public amenities.

Parks

State of Facilities: Most municipal parks remain under-maintained, with deteriorated infrastructure, vandalised play equipment, overgrown vegetation, and inadequate lighting. Community use has declined due to safety concerns and poor aesthetics.

Performance Limitation: No ring-fenced budget for regular maintenance or refurbishment. Operations depended on ad hoc Expanded Public Works Programme (EPWP) support, which provided temporary relief but no sustainable solution.

Impact: Parks failed to fully contribute to social cohesion, children’s recreation, or economic opportunities for informal traders.

Cemeteries

State Facilities: Cemeteries face acute challenges of overcrowding, lack of fencing, and poor landscaping. Water shortages further constrained burial dignity and hygiene standards.

Performance Limitation: Absence of a Cemetery Master Plan and reliance on reallocation of minimal operational funds. No provision for expansion or acquisition of new cemetery land during the reporting year.

Impact: Growing public dissatisfaction, illegal burial practices, and pressure on existing sites.

Community Halls

State of Facilities: Community halls remain key community assets, but several facilities lack proper maintenance, digital connectivity, and modern amenities. Some halls were underutilised due to lack of effort for local groups and the absence of structured management models.

Performance Limitation: With no dedicated funding, minor repairs were carried out through ward allocations or limited in-house technical support. Income generated from hiring fees was insufficient to cover running costs.

Impact: Reduced accessibility for vulnerable community groups, limiting halls’ potential to serve as centers for social, cultural, and LED activities.

Swimming Pool and Recreation Facilities

State of Facilities: The Kirkwood swimming pool remained closed for most of the reporting year due to structural damages, inadequate filtration systems, and lack of compliance with health standards. Sports fields and recreation grounds showed visible decline due to lack of irrigation, vandalism, and deteriorated ablution blocks.

Performance Limitation: No capital budget for rehabilitation. Maintenance was reactive, depending on reported incidents, while sports development programmes were suspended.

Impact: Loss of recreational opportunities for youth and local leagues, undermining sports development and community wellness.

Municipal Security of Facilities

State of Facilities: Vandalism, cable theft, and illegal occupation continued to plague facilities. Most facilities lacked perimeter fencing, adequate lighting, and surveillance systems.

Performance Limitation: Security budget remained underfunded. Contracts for guarding services were limited to high-risk sites only, leaving many facilities exposed.

Impact: Continuous cycle of repair costs, community distrust, and reduced attractiveness of public amenities.

7. Key Observations

Unfunded Mandate: Service delivery in this portfolio was largely reactive and reliant on EPWP interventions, ward-based allocations, and emergency re-prioritisation of limited funds.

Deferred Maintenance: Lack of preventative maintenance has accelerated the deterioration of facilities, resulting in higher future rehabilitation costs.

Community Dissatisfaction: Growing negative sentiment due to declining access, safety concerns, and poor aesthetics of public spaces.

Missed LED Opportunities: Potential to stimulate local micro-economies through events, sports tourism, and facility rental remained untapped.

8. Strategic Alignment with the IDP

While the municipality has not been able to deliver fully on IDP Goal 1, efforts were made to keep facilities functional at a basic level. The unfunded nature of operations has highlighted the urgent need for:

Capital investment through national and provincial grants (MIG, DSAC, EPWP, Infrastructure Maintenance Fund).

Partnerships with private sector and civil society for facility management, security, and programming.

Community-based stewardship models to drive accountability and ownership at facility level.

The 2024/2025 financial year underscores the reality that without adequate funding, the sustainability and dignity of public amenities cannot be achieved. The state of parks, cemeteries, community halls, swimming pools, recreation facilities, and social amenities remains a significant service delivery risk, with direct implications for community wellness, social cohesion, and LED development opportunities.

The municipality requires urgent resource mobilisation, innovative partnerships, and strategic grant funding to shift from reactive maintenance to sustainable, proactive infrastructure management.

FACILITY AUDIT AND BASELINE INFRASTRUCTURE ASSESSMENT

The Sundays River Valley Local Municipality has undertaken a systematic facility audit and baseline infrastructure assessment to establish the current state, distribution, and functionality of parks, recreational facilities, and social amenities across all wards. This process was essential to identify gaps, prioritize interventions, and inform a sustainable infrastructure development plan.

The audit covered:

Community parks and public open spaces

Outdoor gyms and active living infrastructure

Sports fields and stadiums

Indoor recreational halls and multi-purpose centers

Associated utilities, amenities, and accessibility features

Each facility was assessed against key indicators including structural condition, accessibility, safety, usage levels, maintenance status, and potential for improvement or repurposing.

Key Findings

Parks and Outdoor Gyms:

Many parks, particularly in Nomathamsanqa, Bersheba, and Valencia, suffer from poor maintenance, vandalism, and inadequate equipment. Most outdoor gyms are either non-functional or underutilized due to missing components and lack of shade and safety features.

Sports Fields:

Critical facilities such as the Paterson, BERSIG, and Valencia sports fields require major upgrades. Infrastructure deficiencies include lack of irrigation, changing rooms, proper fencing, seating, and lighting. Steve Tshwete Stadium, although functional, needs targeted investment to meet competitive sports standards.

Indoor Recreation Facilities:

Facilities like Kuyasa, Masizakhe, and Valencia community halls are structurally sound but under-resourced. They lack basic equipment, programming, and staffing, which limits their potential as community development hubs.

Inactive or Derelict Halls:

Several community halls are either locked, abandoned, or being used for non-public purposes. This represents a lost opportunity for hosting social programmes, workshops, and economic activity.

Water-Based Recreation:

The absence of a swimming facility in Addo, despite community demand and climatic suitability, highlights a significant infrastructure gap, particularly for youth development and water safety education.

Strategic Baseline Observations

Spatial inequity persists, with remote and informal settlements having little or no access to functional amenities.

Infrastructure exists, but without operational support or maintenance budgets, much of it remains dormant.

Strong potential exists to optimize and cluster facilities using a nodal planning model.

Community partnerships and targeted programming can unlock value in underutilized spaces.

This assessment forms the baseline for all future infrastructure investment and supports the municipality’s vision of equitable, inclusive, and sustainable access to recreational and social amenities for all residents.

Indoor Recreational Facilities

There are currently four known indoor recreational facilities within the municipality, each with varying degrees of functionality and public accessibility:

Kirkwood Squash Courts

This facility is under private management, though the physical structure remains the property of the municipality. While operational, its management model limits broader public access and community programming. There is potential for greater community benefit if inclusive usage agreements or partnerships are explored.

Kuyasa Hall (Boxing Training Facility)

Historically used as a boxing training center, Kuyasa Hall has suffered from repeated vandalism, which has rendered the facility suboptimal and largely dysfunctional. Security concerns and a lack of consistent maintenance have contributed to its current state, diminishing its role in youth development and recreation.

Nomathamsanqa Community Hall

This hall is actively used for recreational and fitness activities, specifically Tybo (a form of aerobic exercise that blends taekwondo and boxing techniques). Despite its regular use, there may be limitations in capacity and equipment that restrict broader program offerings.

Valencia Community Hall

Similarly, Valencia Hall supports Karate sessions, offering a dedicated space for martial arts and youth engagement. While the facility is functional, enhancements in infrastructure, programming support, and safety would strengthen its role as a community asset.

Key Observations and Challenges

Infrastructure Vandalism and Security: Vandalism remains a key barrier to the sustainability of indoor facilities, especially in Kuyasa Hall. This reflects broader issues around facility security, community ownership, and municipal oversight.

Management and Access Issues: The mixed management structures—such as private operators managing municipal assets—introduce questions of equity, transparency, and service reach. Public-private management models require clearer guidelines and community-inclusive frameworks.

Uneven Distribution of Services: Recreational services are concentrated in certain areas, leaving other communities with limited or no access to structured recreational programs.

Resource Constraints: Many facilities lack the necessary equipment, staff, or budgetary support to operate at full capacity or to expand their program offerings.

Kirkwood Swimming Pool and Aquatic Facility Gaps

The Kirkwood Swimming Pool remains the sole dedicated municipal aquatic facility within the local municipality. Strategically located within the urban core of Kirkwood, the pool serves as a seasonal recreational space and has historically been used for school activities, community events, and informal swimming programs.

However, the facility faces several challenges:

Limited Operating Periods: The pool is not open year-round and is often closed for extended periods due to maintenance delays, water shortages, or lack of staffing.

Ageing Infrastructure: The facility requires upgrades to its filtration system, ablution blocks, and perimeter fencing to ensure safety, hygiene, and operational efficiency.

Underutilization: Due to intermittent closures and limited promotional activities, community usage has declined, particularly among youth and school groups.

Security Concerns: The absence of dedicated security personnel and proper lighting increases the risk of vandalism and discourages broader use.

While the Kirkwood pool remains a potentially valuable recreational asset, these limitations significantly reduce its impact and accessibility, particularly for residents living outside the immediate Kirkwood area.

Service Gap: Addo Area (Valencia, Nomathamsanqa, and Surrounding Farms)

There is currently no public swimming pool or aquatic facility in the Addo area, which includes the densely populated communities of Valencia and Nomathamsanqa, as well as several surrounding farm settlements. This constitutes a critical infrastructure gap, particularly considering the area's demographic profile, which includes a large youth population and numerous schools that could benefit from swimming as both a recreational and life-saving activity.

Key Implications of This Gap:

Exclusion from Water Safety Education: Children and youth in Addo do not have access to swimming lessons or water safety programs, posing risks in a region with farm dams and canals.

Recreational Inequality: The absence of swimming facilities contributes to spatial and social inequities in service delivery, with communities in Addo being disadvantaged compared to Kirkwood.

Unrealized Social and Health Benefits: Aquatic activities offer significant health and social benefits, including stress relief, low-impact exercise, and structured youth engagement. These benefits remain inaccessible to Addo’s residents.

Transport and Affordability Barriers: Traveling to Kirkwood for swimming is not a viable option for many households in Addo due to transport costs, time constraints, and limited public transport options.

Recommendations and Opportunities

Feasibility Study: Conduct a feasibility study for the development of a community swimming pool in the Addo area, possibly co-located with a school or community hall.

Public-Private Partnerships: Explore partnership models with local businesses, agricultural employers, or NGOs to co-fund a new aquatic facility in Addo.

Facility Upgrades: Prioritize refurbishment of the Kirkwood Swimming Pool to improve reliability, safety, and year-round accessibility.

Mobile Water Safety Programs: In the interim, implement mobile swimming and water safety education initiatives for Addo schools through inflatable pools or regional collaborations.

Outdoor Play Parks

The municipality has established four outdoor play parks in the following locations:

Bergsig

Emsengeni

Nomathamsanqa

Paterson

These parks provide essential play and recreational space for children and families. However, site assessments indicate varying levels of functionality and maintenance. Common challenges include:

Damaged or outdated play equipment

Lack of fencing and safety features

Insufficient lighting and supervision

Limited accessibility for children with disabilities

While the presence of these parks is commendable, there is a pressing need for consistent maintenance schedules, community stewardship programs, and inclusive upgrades to ensure they meet safety standards and serve a wider demographic.

Cross-Cutting Challenges

Maintenance and Vandalism: Many facilities face infrastructure degradation due to vandalism and lack of ongoing maintenance. This affects usability and public trust in facility safety.

Limited Community Programming: Even where facilities exist, the range of structured programming remains limited, affecting participation rates and the developmental potential of these spaces.

Equity and Access: Facilities are not evenly distributed across the municipality, creating access disparities—particularly in smaller or rural communities.

Governance and Partnerships: Some assets under private or informal management arrangements lack clear accountability frameworks, affecting transparency and strategic oversight.

Opportunities for Improvement

Development of a comprehensive maintenance and security plan for all public amenities

Formation of community partnerships to support programming and facility monitoring

Investment in inclusive infrastructure, particularly for children, the elderly, and persons with disabilities

Review of facility management models to ensure equitable public access and efficient resource utilization

Community Halls

Community halls serve as vital public assets that enable civic participation, cultural expression, recreational activities, and social service delivery. In the Sundays River Valley Local Municipality (SRVLM), community halls are central to hosting events, training sessions, public meetings, and recreational programs. Their accessibility, functionality, and condition significantly influence community cohesion and service outreach.

Currently, there are seven (7) community halls across various wards in the municipality. These facilities vary in terms of condition, usage status, and overall infrastructure integrity.

Current Status of Community Halls

| Facility Name | Location | Ward | Status | Condition | Comments |
| --- | --- | --- | --- | --- | --- |
| Bergsig Community Hall | Kirkwood | Ward 2 | In Use | Fair | Facility interior is controlled and functional. However, fencing is lacking, several windowpanes are broken, and electrical system is only fair. |
| Bersheba (Zinakile) Community Hall | Enon, Bersheba | Ward 8 | In Use | Fair | Internal access is well controlled; facility suffers from minor vandalism (broken windows) and requires fencing upgrades. |
| Enon Community Hall | Enon, Bersheba | Ward 8 | Not in Use | Not in Use | Currently inactive. No operational usage or maintenance. |
| Valencia Community Hall | Valencia | Ward 3 | In Use | Good | In generally good condition; fencing needs attention. Some windowpanes are broken, and electrical systems require moderate improvements. |
| Masizakhe (Nomathamsanqa) Community Hall | Nomathamsanqa, Langboos | Ward 5 & 6 | In Use | Good | Facility is in good working order with adequate fencing and security measures. Minor electrical issues persist. |
| Sinako (Paterson) Community Hall | Paterson | Ward 4 | In Use | Good | Well-maintained facility with secure access and fencing. Electrical system fair; minor repairs required. |
| Kuyasa Community Hall | Moses Mabhida | Ward 1 | Not in Use | Not in Use | Not operational; needs assessment for repair, repurposing, or decommissioning. |

Key Observations :

Operational Disparities: Out of seven community halls, five are in use while two (Enon and Kuyasa) are non-operational and require immediate evaluation for revitalisation or alternative use.

Physical Condition:

Good Condition: Masizakhe, Sinako, and Valencia Community Halls are structurally sound but require minor repairs.

Fair Condition: Bergsig and Bersheba halls are functional but lack critical external security features such as fencing and window protection.

Not in Use: Enon and Kuyasa halls are unused and pose a risk of further dilapidation if not addressed.

Common Maintenance Issues:

Fencing: Several facilities lack perimeter fencing, posing security and access control challenges.

Electrical Systems: Most halls have fair electrical systems that require upgrading for full safety and functionality.

Security Features: Doors with burglar bars are standard, but broken windows remain a recurring issue across facilities.

STRATEGIC CHALLENGES

Infrastructure Deterioration: Delayed maintenance contributes to rapid degradation, even in facilities still in use.

Underutilisation: Non-functional halls represent wasted infrastructure potential, especially in underserved areas.

Inequitable Access: Ward-level disparities in operational hall distribution limit uniform access to public indoor spaces.

Recommendations for Immediate and Long-Term Intervention

Immediate Maintenance and Repairs:

Replace broken windowpanes and upgrade outdated electrical systems in all functioning facilities.

Install or repair fencing to ensure secure and controlled access to premises.

Conduct minor renovations to address wear-and-tear issues in fair-rated facilities.

Reactivation of Non-Functional Halls:

Conduct structural assessments of Enon and Mzamomhle & Kuyasa halls.

Develop a costed plan for rehabilitation or repurposing to meet community needs.

Engage local stakeholders to identify viable programming for underused assets.

Preventive Maintenance Plans:

Implement a rotating maintenance schedule with ward-level oversight.

Allocate operational budgets to support basic upkeep and repairs.

Equity-Focused Investment:

Ensure that wards currently lacking fully operational halls receive priority in future infrastructure investments or hall upgrades.

Community halls in the Sundays River Valley Local Municipality remain critical for social cohesion, service delivery, and community empowerment. While most are in use and partially functional, targeted maintenance, improved security, and the revitalisation of dormant facilities are essential for maximizing their potential and ensuring equitable access across all wards.

INTRODUCTION TO LIBRARIES; ARCHIEVES; MUSEUMS; GALLERIES; COMMUNITY FACILITIES– LIBRARIES

SRVM Libraries form an important part of the services offered to the people of all communities including disadvantaged ones. The entire community has the right to free access to the library and information services. The reason for this is that it promotes a culture of reading, library use and learning that enriches the whole community and ensures that we accommodate people with disabilities (mini lib services for blind and partially sighted). Library Services ensures that this information is free, equitable and accessible to everyone.

Through our mobile library we assist underprivileged communities who cannot easily reach our libraries by providing free access. We also render our services to old age homes, pre-schools, local schools, and prisons by means of book loans.

COMMENT ON THE PERFORMANCE OF LIBRARIES; ARCHIVES; MUSEUMS; GALLERIES; COMMUNITY FACILITIES; OTHER (THEATRES, ZOOS, ETC) OVERALL:

Library week:  South African Library Week has been commemorated every year since 2001 and is always observed in mid-March.

The aim of Library Week is to celebrate the intellectual and literacy heritage of our nation. Library Week also seeks to contribute to the understanding of the key role that libraries play in a democratic society through advancing literacy, making the basic human right of freedom of access to information a reality, and promoting tolerance and respect among all South Africans.

Holiday program: SRVM Libraries offer a range of activities for children and young people at our libraries throughout the year. These activities are aimed at providing children with and promoting library services and providing a safe environment for children during the holidays. The activities are offered free of charge during library hours to both members and non-members of the libraries for recreational purposes and leisure.

International Literacy Day: Since 1967, International Literacy Day celebrations have taken place annually around the world to remind the public of the importance of literacy as a matter of dignity and human rights, and to advance the literacy agenda towards a more literate and sustainable society. SRVM libraries help to develop the lifelong love of books and reading for pleasure. They also promote Indigenous language publishing to foster South African literature.  We celebrated by inviting local schools to take part in in the following activities such as reading various Indigenous languages, Math is 24 and we added a recent activity called words within a word.

Career expo: On 09 May 2023, SRVM Libraries, in Partnership with SRVM and Government Departments conducted a successful career expo. Departments such as Department of Education, Department of Correctional Services, San Parks, Department of Health, SANRAL, Love Life, Independent Electoral Commission and SRCC, they all have information tables so that grade 12 learners can be taken through concerning career choices. All high Schools in SRVM were invited.

BUDGET: We receive a grant from DSRAC 1.2 million annually, the challenge is there is no budget allocated to the specific programs only staff salaries allocated. There are limited resources to conduct all the calendar of event activities.

### 3.13	CEMETERIES AND CREMATORIUMS

INTRODUCTION TO CEMETERIES & CREMATORIUMS

Our cemeteries have moved closer to reaching capacity, demographics have changed. There is extraordinarily minor change in the traditional norms and practices, traditional full burials are still the norm. When forecasting future capacity of using mortality rates, population forecasts, methods of disposition, market capture, and future interment needs. And critically analyzing the municipalities site inventory you find existing constraints and opportunities presented in many changing aspects of the municipality. Cemetery needs were combined with the inventory to create a high-level concept plan that can be used to develop the cemeteries for the next 20 to 30 years.

The Cemetery Needs Analysis established the need for additional space and a range of interment options to serve Municipal residents. To meet this need, the municipality has submitted an item to councils to seek approval that:

- Additional land be allocated and planned as soon as possible. And fast track the Establishment of new cemeteries for Ward 8 and Ward 4 on identified properties as proposed by the Spatial development Framework.

- That Council approves of the establishment of new cemeteries.

- That Councils to deliberate on submissions and make decisions on proceeding and approval for the establishment of new cemeteries.

|  | Sunday River Valley Municipality |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Town/Settlement/ | Name of Cemetery | Landowner | Status | Coordinates | Comments |
| Ward 7 | Glen Conor Cemetery | Sundays River Valley Municipality: Portion 25 of UITZICHT, 155/UITENHAGE RD | Presumption: +10 years taking into cognisance of locality population, but no scientific calculation done | 3323'31.0"S 25°09'21.8"E | The locality of Glen Connor currently utilises the cemetery of privately-owned property but is land that has been allocated for burial but not utilised. With the property being registered under the Sarah Baartman District Municipality. |
| Ward 7 | Westbank Cemetery | Sundays River Valley Municipality: Portion 108 of CLAAS KRAAL, 539/UITENHAGE RD | Presumption: +10 years taking into cognisance of locality population, but no scientific calculation done | 3327'17.6"S 25°29'32.9"E | The site is located on Westbank side of farm location and caters for the farm dwellers of around the location |
| Ward 2 | Bergsig/Kirkwood Cemetery | Sundays River Valley Municipality: ERF 459 and ERF 460 | Presumption: 1.5 years taking into cognizance of local population, but no scientific calculation done | 3323'13.5"S 25°27'24.2"E | Site recently expanded with new 1,2m high diamond mesh wire fence, with visible access gate. The cemetery has been well maintained in terms of vegetation overgrowth. There is no facility or proper infrastructure in place. The geotechnical soil conditions are favorable and close classification to sandy loam. The location is isolated from residential units |
| Ward 1 | Moses Mabhida Cemetery | Sundays River Valley Municipality: | Full capacity and closed and closed for new interment | 3323'32.6"S 25°28'46.4"E | The site has poorly designed or lack of proper access roads, fencing is in place but elevated risk of theft and vandalism. There is no facility or proper infrastructure in place. It has extremely poor geotechnical soil conditions with the soil been typified as rocky. The location of which is densely populated by surrounding informal settlement. |
| Ward 8 | Mis kraal Cemetery | Sundays River Valley Municipality: Farm 42of Portion 420 STRATHSOMERS ESTATE | the site is located on R336 on Mist kraal locality and caters for most farms that are transverse by R336 ending in Summerville | 3327'15.8"S 25°29'32.3"E | the site is located on R336 on Mist kraal locality and caters for most farms that are transverse by R336 ending in Summerville |
| Ward 8 | Enon Cemetery |  | Presumption: less than 1.5 years taking into cognisance of locality population, but no scientific calculation done | 3323'31.4"S 25°32'40.4"E | The location of these two sites is on a property that is said to belong to the Witrivier Communal Property Association. Currently the two locations for Enon and Beersheba respectively are set to reach full capacity soon. But one advantage is the availability of land to choose from the hydrogeological condition suffice. |
| Ward 8 | Bersheba Cemetery |  | Presumption: less than 1.5 years taking into cognisance of locality population, but no scientific calculation done | 3324'55.4"S 25°32'58.3"E | The location of these two sites is on a property that is said to belong to the Witrivier Communal Property Association. Currently the two locations for Enon and Beersheba respectively are set to reach full capacity soon. But one advantage is the availability of land to choose from the hydrogeological condition suffice. |
| Ward 6 | Sunland Cemetery | Sundays River Valley Municipality: FARM 639 | Presumption: +10 years taking into cognizance of local population, but no scientific calculation done | 3328'32.8"S 25°37'14.8"E | The site has a total approximate area of 19.7 Hectare and currently used as a landfill site and cemetery simultaneously. The cemetery is currently not maintained, and no burial activities monitored. Assistance is required to clear overgrown bushes and to demarcate/fence off the two sections in this property |
| Ward 3 | Valencia Cemetery | Sarah Baartman District Local Municipal Portion 306 of COMMANDO KRAAL ESTATE, 113 | Presumption: +10 years taking into cognisance of locality population, but no scientific calculation done | 3332'33.3"S 25°41'42.3"E | The site has poorly maintained or lack of proper access roads, there is no fencing in place or any structure demarcating the location. There are no facilities or proper infrastructure in place the geotechnical soil conditions are favorable and close classification to sandy loam. The location is isolated from residential units and caters for residence of Ward 3, 5 and 6. The total of land covers approx. 28 Hectares. The site and location present an opportunity to create what can be perceived as ideal design and enough cemetery that encapsulate all necessary amenities |
| Ward 5 | Nomathamsanqa Cemetery | Sundays River Valley Municipality: Erf 2071 in ADDO | Full capacity and closed for burials | 3331'39.9"S 25°42'35.5"E | site has been closed for burial; local narrative presumes that there are individual plots that have been reserved. The location of which is densely populated by surrounding informal settlement. |
| Ward 6 | Langboos Cemetery | Sundays River Valley Municipality: | Presumption: +5 years taking into cognizance of local population, but no scientific calculation done | 3330'06.7"S 25°41'41.0"E |  |
| Ward 4 | Paterson/Moreson Cemetery | Sundays River Valley Municipality: | Presumption: less than a year’s taking into cognisance of locality population but no scientific calculation done. Urgent action is needed | 3326'27.9"S 25°58'15.5"E | Site recently expanded with new 1,8m high diamond mesh wire fence-currently stolen, with visible access gate. The cemetery has been maintained in terms of vegetation overgrowth and litter. There is no facility or proper infrastructure in place. The geotechnical soil conditions are favorable and close classification to sandy. The location is located within the residential units with proximity to SAPS, but this has not deterred the theft of the fence. |

COMMENT ON THE PERFORMANCE OF CEMETERIES & CREMATORIUMS OVERALL:

| Strategic Objective | Project | Key Performance Indicator | Annual Target | Quarter 3 Target | Quarter 4 Target | Status | Reasons for Underperformance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Communities of SRVM with specific reference to youth have access to suitable and affordable recreational and sport facilities and public amenities. | Establishment of new cemeteries | Number of cemeteries established | 2X Cemeteries established | Initiate procurement processes for fencing and earthworks on the site | Establishment of 2 cemeteries | Submission to the council has been submitted for the last 2 consecutive financial period. But the council has not deliberated nor approved. Thus, this delays the office ability to facilitate the DEDEAT Application. Please refer to evidence submitted to POE file for 1st Quarter 2022/23 | Delay in council deliberation and approval |  |
| Strategic Objective | Project | Key Performance Indicator | Annual Target | Quarter 3 Target | Quarter 4 Target | Status |  | Reasons for Underperformance |  |
| Communities of SRVM with specific reference to youth have access to suitable and affordable recreational and sport facilities and public amenities. | Cemetery maintenance | Number of cemeteries maintained | 2X Cemeteries maintained | SCM & Procurement initiations | N/A | None where established |  | Delays in council submission of new regulations and adoption thereof |  |

### 3.14	CHILD CARE; AGED CARE; SOCIAL PROGRAMMES .

a) September 2024 NYDA Training

b) February 2025 All Art Festival in conjunction with Tsitsikama All ART

c) February 2025 District Games partnership with DSRAC

c) June 2025 Career Exhibition a partnership with Department of Labour

I Could not do other programs because of Financial constrains

## COMPONENT E: ENVIRONMENTAL PROTECTION

This component includes pollution control; biodiversity and landscape; and costal protection.

INTRODUCTION TO ENVIRONMENTAL PROTECTION

The municipality endeavors to provide services in a sustainable manner by ensuring that the environment is always protected. There has been one project that required EIA, which is the establishment of a Waste Transfer Station in Addo. The process has not taken off due to land unavailability.

### 3.15	POLLUTION CONTROL

INTRODUCTION TO POLLUTION CONTROL

Environmental Pollution Control is a function of the District Municipality under Municipal

Health Services. The district currently has two Environmental Health Practitioners rendering

Municipal Health Services utilizing the approved SBDM budget.

A collaborative relationship has been established between sister departments such as DWA

to monitor and ensure compliance with legislation in industrial areas.

COMMENT ON THE PERFORMANCE OF POLLUTION CONTROL OVERALL:

Currently the District Municipality does not have air pollution program or resolute personnel.

However, the Environmental Health Practitioners conduct inspections, investigations, and

assessments on operations that may have an impact on environmental pollution such as

monitoring compliance at landfill sites, sampling the final water being disposed into the

environment/rivers from the operations of wastewater treatment plants and oxidation ponds.

### 3.16	BIO-DIVERSITY; LANDSCAPE (INCL. OPEN SPACES); AND OTHER (EG. COASTAL PROTECTION)

While we understand the importance of biodiversity and ecosystem protection, currently the municipality is still in the process of developing a Climate Change Strategy and Air Quality Management Plan. In addition to this, SRVM is planning to establish its Tree canopy cover through remote sensing techniques and GIS. Neglecting these areas will result in deforestation, pollutions, (air, water, and land) as well as the modification of the ecosystems. SRVM is participating and has provided information towards having the 2 Strategies in place. Eradication of alien invasive species was started in 2022 and an ongoing project. Completion of the project will simplify estimates on air quality, and measurement of lifespan of the current ecosystem. The Department of Forestry, Fisheries and the Environment is supporting the municipality in some of these projects. The are 3 Priorities in the IDP, Development of Climate Change Strategy, Air Quality management Plan and provision of non-motorised facilities in town to encourage use of modes of transport that generate less fumes, thus reducing air pollution and its long-term effects. Ongoing community education is being done, basically awareness through various social media platforms and during community meetings.

In addition, SRVM is hard at work, eradication illegal dumping sites to preserve land and the environment in general. These are converted to gardens across the Valley encouraging communities to rethink open spaces. SRVM Participates in national and provincial competitions to obtain resources to advance the 10 million trees Programme which will also assist in the biodiversity and landscape management. Employment through EPWP and CWP and ensuring people work in their communities and are champions of change.

## COMPONENT F: HEALTH

This component includes clinics; ambulance services; and health inspections.

INTRODUCTION TO HEALTH

The Sunday’s River Valley is demarcated under Kouga Health Sub-District Authority together with Kouga Local Municipality and Kou-Kamma Local Municipality.  Primary Health Care Service Function has been provincialized since 01 January 2010, and this was to address duplication and fragmentation of services and to create and establish uniform norms and standards and ensure that the service is provided by the single authority (Eastern Department of Health) through District and Sub-district structures. The biggest challenge with Health Services is the poor provision of Emergency Medical Services (Ambulance Services), which require serious attention. The other challenge is the sizes of the Clinics, especially in Nomathamsanqa where the community has significantly grown and yet the facility is not extended. The other two townships that must be considered for new clinics are Emsengeni and Enon/Bersheba. These challenges will be pursued with the Eastern Cape Department of Health.

3.19	HEALTH INSPECTION; FOOD QUALITY MONITORING

Municipal Health Services (MHS) what was historically known as Environmental Health and

MHS is a function and a competency of Sarah Baartman District Municipality (SBDM).

Municipal Health services mainly focuses on:

- Water quality monitoring

- Food Control

- Waste Management

- Health surveillance of premises

- Vector Control

- Environmental pollution control

- Disposal of Dead.

- Chemical safety

- Surveillance and prevention of communicable diseases

- Water samples are submitted to the laboratory for bacteriological analysis in order to

ensure safety for human consumption. There has been isolated instance the non-

compliance of some water samples during 2024/2025 and on those instances “boil water” notices were issued for the affected communities.

- The call of the President of the country to formalize and register spaza shops has prompted the Municipality to hold several workshops with the spaza shop owners, where they were being sensitized on compliance issues. This has yielded positive results where several spaza shops have shown improvement in terms of hygiene practices and the structural conditions of the premises. A series of multisectoral blitz operations were held during this financial year to intensely monitor the quality of the food being provided to the public.

## COMPONENT G: SECURITY AND SAFETY

This component includes police; fire; disaster management, licensing and control of animals, and control of public nuisances, etc.

INTRODUCTION TO SECURITY & SAFETY

This component includes fire, disaster management, licensing, control of animals and control of nuisances.

The National Road Agency with Traffic services conducts meetings on a regular basis to discuss issues of road safety and community safety at large. Regular roadblocks are being conducted in major routes N10; N2; R366; R334; R75; R72; With respect to general safety the municipality still experiences challenges around:

- Medium accident rate

- Municipal by-law with respect to stray animals and hawkers trading areas were promulgated but the level of enforcing them is exceptionally low. Peace Officers will address these challenges.

- The municipality intends to solicit proposals from potential partners for the development of a pound.

- Crime decreases in all areas, but Paterson does not show any significant improvement.

### Traffic Services

SRVM is rendering a full traffic service to the communities within the district of the Municipality. The services rendered are as follows.

- Law enforcement,

- Traffic emergency services (accidents, incidents & disasters),

- Motor vehicle registration, licensing, and Roadworthy services.

- The driver’s licensing functions are partly operational (applications for renewal of drivers’ licenses; application for learners’ license; application for professional driving permits, application for driver’s license- our testing route is not compliant with National Standards, thus we can only test applicants for motor-cycle licenses). Regular maintenance needs to be done for the testing route to be compliant with national norms.

- We are registered as a grade “A” driver’s license testing and roadworthy testing center.

- We have a cashless policy at the Kirkwood Office which stamps out fraud and corruption.

- We have a WhatsApp line for driver’s license queries which assists the public with traffic department issues.

Number of traffic accidents: 157

Number of by-law infringements: 6

Number of traffic officers in the field: 6

Number of traffic officers on daily duty: 8

### Fire and Disaster Management Plan

The Directorate of community services is responsible for security of municipal assets (Halls, buildings and sports fields, wastewater treatment plants etc). The municipality has a Traffic department responsible for ensuring law and order is upheld in the SRV Municipal jurisdiction. Control of animals is management by Environmental Health Practitioners, a function of the Sarah Baartman District Municipality, with 2 officials based in SRVM. The district has an approved Municipal Health Bylaw within which is the Keeping of Animals bylaw, enforced in partnership with SRVM law enforcement officers. Fire and Disaster management services are provided by the LM through a Service Level Agreement with the District. Their role is to ensure compliance with Fire Bylaws, building regulations as they relate to safety measures, labour laws and property security.

### 3.20	POLICE

INTRODUCTION TO POLICE

Sundays River Valley Municipality has a Traffic department, rendering services to communities, in the form of learner’s licences, driver’s licenses, motor vehicle registration, roadworthy testing, traffic control, inspection and compliance. All these culminate to revenue collection. SRVM is in the process of renovating the Driver’s License testing ground to reopen the services. There is however at no budget currently. SRVM has experienced revenue losses due to closure of the Testing service by Department of Transport due to requirements not being met including the testing route owing to current road construction project. The top 3 priorities are Providing services to communities, ensuring safety of communities and municipal assets, Raising revenue for the municipality.

### 3.21	FIRE

The Disaster Management Act defines disaster management to mean a continuous and integrated multisectoral, multi-disciplinary process of planning and implementation of measures aimed at:

- Prevention or reducing the risk of disasters.

- Mitigating the severity of consequences of disasters

- Emergency preparedness

- A rapid and effective response to disasters

- Post-disaster recovery and rehabilitation

- All Local Authorities and the District Municipalities are required, in terms of legislation, to prepare disaster management plans as outlined in the Bill.

- Various District Municipalities have embarked on this process on a regional level, including the local municipalities.

The Disaster Management Plan was approved by Council and available.  The Disaster Management function has always resided with the District Municipality; the Enabling Act has allowed local municipalities to perform this function in conjunction with the district and as a result the following functions now apply.

- Disaster prevention/risk reduction Disaster mitigation priorities and the promotion of sustainable livelihoods

- Disaster preparedness

- Disaster response and relief

- Post disaster recovery, rehabilitation, and reconstruction.

- Establishment of effective management of the function

- Strategies to ensure the involvement of the community and volunteers.

- The Emergency Satellite Centre in Paterson and Addo is required.

The staff complement in the Fire & Disaster Unit is eight, inclusive of the Chief Fire Officer. However, the position of Chief Fire Officer is currently filled. The chief fire officer in the fire division and the section is headed by the Director of Community Services. Additionally, three fire fighters in the Unit are appointed through the funding from the SBDM in line with the Service Level Agreement entered between SRVM and SBDM.

There are plans in place to operationalize a Satellite Station in Addo and Paterson which will assist the response related to fires and disasters and this again is in line with SRVM Council resolution of decentralization and improvement of Emergency Services. The district has budgeted funds for the development of an emergency center in Paterson.

## COMPONENT H: SPORT AND RECREATION

This component includes community parks; sports fields; sports halls; stadiums; swimming pools; and camp sites.

INTRODUCTION TO SPORT AND RECREATION

In South Africa, sport has been defined as “any activity that requires a significant level of physical involvement in which the participants engage in either a structured or unstructured environment for the purposes of declaring a winner, though not solely so; or purely for relaxation, personal satisfaction, physical health, emotional health and development,” (Department of Sport and Recreation, 2009: 2). Recreation has been defined as, “a guided process of voluntary participation in any activity which contributes to the improvement of general health, well-being and the skills of both the individual and society,” (Department of Sport and Recreation, 2009: 2). Given that access to sport and recreation is seen as a global human right, stakeholders such as government, civil society and the private sector have an obligation to ensure equal opportunities of participation for everyone.

South African recreational behaviour cannot be understood in isolation from national political history, as important aspects of this behaviour are rooted in the spatial and political fragmentation of our society. The Reservation of Separate Amenities Act 1953 to use separate public amenities

in still a legacy that still manifest itself within certain sectors or field relating to the equitable distribution and accessibility to recreational facilities.

Access measures the extent to which an individual can avail himself of opportunities for self-fulfilment and betterment. It is a valuable yardstick of social well-being. Further that accessibility varies not only according to distance and direction but from individual to individual according to socio-economic status.

The rationale of refinement of delivery approach should be based on making qualitative changes in the lives of people and enhancing social, fiscal, and environmental sustainability well into the future.

It is hoped that this Recreation Plan will offer a rallying point for effective partnerships and assist stakeholders in identifying key areas for united action, thus changing public access to services for the better.

### 3.23	SPORT AND RECREATION

Sundays River Local Municipality Recreation and Sport Integrated Strategy has considered several public amenities. These amenities are used for various events and activities ranging from sport, music, meetings/ conference, and recreational activities. These include community parks; sports fields; sports halls; stadiums; swimming pool.

The objectives of Public Amenities Section under the directorate of Community Service are -but not limited.

- To render public amenities that are safe and healthy.

- To improve and maintain the standard of public amenities.

- To uplift the standard of living of residents, especially the vulnerable groups such as the youth

- Provide landscape and general maintenance for public amenities.

- Provide general maintenance and burial services on cemeteries.

Sundays River Local Municipality Recreation and Sport Integrated Strategy, has outlined this fundamental scope of desired achievement:

Vision

- A seamless, integrated, and mainstreamed youth development through recreation across public, private, and civil society sectors

Mission

- To facilitate, coordinate, lobby and monitor the implementation of youth development programmes and policies through recreation, as well as initiate and implement strategic projects.

Objectives

- To promote a uniform approach by all organs of state, the private sector and civil society organizations.

- To initiate strategic anchor projects to benefit youth from disadvantaged backgrounds (rural, disabled, and young women) and guide programming for other stakeholders including private and civic society sectors.

- To provide a framework and classification which will enable coordinated development programmes’ implementation in all sectors.

Critical to the success Recreation and Sport Integrated Strategy, a few success factors have been identified, such as the following:

- effective stakeholder management

- effective maintenance and management of facilities

- funding

- government department buy-in into the integrated service delivery.

- ongoing support within these facilities.

As local government we need to improve service delivery and further widen access services to underservice communities. Government needs to focus intensively on the development of suitable infrastructure that will cover the municipality and link all areas, particularly those that are most deprived, in a sustainable manner.

Other key areas of intensified concentration should include.

- Need for massive investment in rationale for a refinement of delivery approach, particularly in rural and disadvantaged communities.

- Strengthening the accessibility of different recreation codes such as boxing, karate, netball, and indoor recreation such as aerobics

- Promoting and expanding the scope of recreation accessibility architype

GOALS

- Provide a variety of high-quality programs that meet community needs and interests.

- Ensure services are accessible for those who are socio-economically disadvantaged.

- Provide adequate and appropriate public lands and facilities that are equitably distributed across the municipality to meet the needs of residents.

- Expand Park and recreation facility accessibility.

- Provide an equitable distribution of public indoor and outdoor recreation spaces.

- Maintain quality park and recreation lands and facilities for efficiency, safety, attractiveness, and long-term sustainability.

- Provide for the protection, security, and safety.

- Ensure long-term sustainability by focusing taxpayer funding on those services that produce the widest community benefit, using a cost recovery.

- Increase alternative funding sources.

The integrated approach to the project should ideally focus on the following elements for consideration and implementation, whereas they ultimately encompass the principles of the Project Scope of Work but determined by the nodal approach for each location.

- Improving Park Safety & Activation

- Enhancing Recreation Facilities & Programming

- Restoring & Improving Access to Open Space

- Restoring Parks & Facilities (Vandalism Response, Park Beautification & Viewpoint Maintenance)

- Increasing Access to Restrooms in a facility development

- Enhancing Life Safety & Regulatory Compliance (Aquatics Safety, Human Resources Safety Compliance and Training)

- Building Community Capacity

- Developing & Enhancing Park Assets (New Pool Park Development)

- be easily accessible, fenced and have clear signage for emergency and security purpose.

- Install irrigation for turf maintenance or water hose pipe connection.

SERVICE STATISTICS FOR SPORT AND RECREATION

SERVICE STATISTICS FOR SPORT AND RECREATION Existing Facilities

| Facility Name | Location | Nature of Use | State and Status of Use |
| --- | --- | --- | --- |
| Nomathamsanqa Sports Field | Ward 6 Langboos | Multi-Disciplinary | Under construction to be completed in 1st quarter of 2023 |
| Steve Tshwete Stadium | Ward 1 Moses Mabhida | Soccer Sports Field | Poor In Use Open space with no equipment, lack ablution facilities due to vandalism, insufficient sports facilities, No visible proper turf |
| Bergsig Sports Field | Ward 2 Bergisg | Rugby Sports Field and Soccer | Poor, lack of ablution facilities due to vandalism, Fair Turf with a need for upgrade, need increase security and irrigation services, insufficient sports facilities. |
| Valencia Sports Field | Ward 3 Valencia | Rugby Sports Field | Poor In Use- need to upgrade the irrigation system |
| Enon Bersheba Sports Field | Ward 8 Enon Bersheba | Rugby Sports Field | Poor In Use- need to upgrade the irrigation system |
| Paterson Sports Field | Ward 4 Paterson | Soccer Sports Field | Poor In Use- need to upgrade the irrigation system |

Existing Facilities

As local government we need to improve service delivery and further widen access services to underservice communities. Government needs to focus intensively on the development of suitable infrastructure that will cover the municipality and link all areas, particularly those that are most deprived, in a sustainable manner.

For the purposes of creating benefits for youth in the sector, the following opportunities need to be fully developed and exploited:

  - Sports goods and equipment

  - Sport sponsorship.

  - Event staging and management.

  - Capital expenditure, including refurbishment and construction of sports facilities.

Other key areas of intensified concentration should include.

  - Need for massive investment in school sports, particularly in rural and disadvantaged communities.

  - Strengthening variety of different sporting codes such as boxing, karate, netball, and indoor recreation such as aerobics

To ensure proper maintenance of recreation and sport facilities the following must be considered:

- That allocation for capital budget would not be made if there is no provision for a minimum 10-year facility operating and maintenance plan and budget. The operating and maintenance of facilities would be covered in the agreement to be assigned with the local municipalities.

- That the municipality should establish dedicated sport and recreation departments or units to manage programmes as well take responsibility for all operating and maintenance requirements of the facilities.

- To minimize maintenance costs, explore use of other minimal maintenance technologies such as artificial turfs based.  The comparative analysis between artificial and natural grass be undertaken.

- To improve on the maintenance of sport and recreation facilities introduce a skills development programmes targeted at sport and recreation facilities management and maintenance personnel. These include the Basic Sport and Recreation Facilities Management Training, Advanced Sport and Recreation Facilities Management Training and the Specialized Turf-grass Management Training. The programmes are designed to enable facilities management personnel to develop Operations and Maintenance Plans for their municipalities.

| Sport And Recreation Policy Objectives taken from IDP |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Service Objective | Outline Service Target | Year -1 |  |  | Year 0 |  |  | Year 1 | Year 3 |  |
|  |  |  |  | Target |  |  | Actual | Target |  |  |
|  |  |  |  | Previous Year |  | Current Year |  | Current Year | Current Year | Following Year |
| Communities of SRVM with specific reference to youth have access to suitable and affordable recreational and sport facilities as well as public amenities |  |  |  |  |  |  |  |  |  |  |

## COMPONENT I: CORPORATE POLICY OFFICES AND OTHER SERVICES

This component includes institutional policy, human resource services, ICT services, corporate services, labour relations, skills development, human resource management and Administration, Wellness, Council Support and Auxiliary Services.

### 3.24	EXECUTIVE AND COUNCIL

This component includes Executive office (mayor; councilors; and municipal manager).

INTRODUCTION TO EXECUTIVE AND COUNCIL

- Render administrative Support to the functioning of the Council (Agenda, Minutes

- Recording Tracking implementation of Council Resolutions

- Render administrative support to the EXCO meetings and Standing Committees.

- Render administrative Support to the MPAC and Audit & risk Committee.

### 3.26	HUMAN RESOURCE SERVICES

- Provide HR Management and Administration of Service Benefits to ALL staff members including Leave Management, comprehensive labour relation support,

- Monitor Training and Development Interventions to the institution and Monitoring Compliance with Labour Legislation

- Develop /Review a total of 9 institutional policies (in draft form) and 3 workshopped to the Councillors.

- Review and populate the approved organogram and currently standing at less 10% vacancy rate (recruitment processes underway for filling critical and funded vacancies).

- Conduct Training Interventions for Councillors, and other municipal officials (see Training Report for details)

- Monitor Leave Management and Leave Monthly Reports generated highlighting leave discrepancies and aligning with Attendance Registers per each department,

- Reduce the number of Grievances registered and attending thereto with urgency (Tally reduced from 36 to less than 20.

- Monitor implementation of Job Evaluation in the approved structure (129 in total Excl senior Managers) and ensure that all approved positions have written Job Descriptions. (Job Evaluation completed for 109 positions and JE Implementation is currently underway for payment of completed JE Outcomes)

### 3.27	INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

This component includes Information and Communication Technology (ICT) services.

INTRODUCTION TO INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

- Develop ICT Governance Framework for the institution and monitor its implementation,

- Develop a comprehensive on-off site Back up system for SRVM and monitor its functionality,

- Ensure functionality & continuity of the access to the email and telephone systems (backup)

- Ensure internet and intranet connectivity both Kirkwood and other satellite office (Network Access Points installed to ensure internet connectivity

- Develop and monitor functionality of the Website for improved access and communication with regards to important Council Documents

- Review and monitor implementation of approved ICT policies.

### INTRODUCTION TO LEGAL SERVICES

NB: Legal Services at Sundays River Valley Municipality are located at the Corporate Services Department and SRVM has developed a Litigation Management Policy approved by Council on the 8th of July 2022,

The Municipality also developed a Standard Operating Procedure to simplify attending to legal issues and litigation matters to reduce quantum and number of cases. The municipality is also a regular attendee in the Provincial Legal Advisors Forum to analyse trends in the litigation space.

COMPONENT K: ORGANISATIONAL PERFOMANCE SCORECAR

| Project Ref. | Project | Key performance indicator | 2023/24 Annual Target | 2023/24 Actual | 2024/25 Annual Target | 2024/25 Actual | Reasons for variance | Remedial Action | General Comment | Portfolio Of Evidence |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INFRASTRUCTURE PLANNING AND DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective: Ensure access and a continuous supply of good quality water and sanitation to each Household/User by 2026 |  |  |  |  |  |  |  |  |  |  |
| INFR 1 | Augmentation of the Water Reticulation Network in Noluthando | 300m of Bulk pipeline constructed | N/A | (50% of sewer pipeline and 20 manholes completed) | 300m of Bulk pipeline constructed | 300m of Bulk pipeline constructed | N/A | N/A | Target Achieved | - Minutes of site meetings - Progress Reports - Letter of approval for additional funding from DWS |
| INFR 2 | Water testing and Compliance blue drop | 12 IRIS water testing reports. | Number of new water connections meeting minimum standards | Project cancelled | 12 water testing reports | 12 Water Testing reports | N/A | N/A | Target Achieved | Monthly Water Testing Results from Scientific Services Certificate of analysis |
| INFR 3 | Testing sanitation and compliance with green drop. | 12 IRIS effluent/ Sanitation testing reports. | N/A | N/A | 12 IRIS effluent/ Sanitation testing reports. | 7 Effluent Testing Results from IRIS. (Quarter 2 Results need to be confirmed as it shows Septe-Decem 2024) | Paterson, Addo & Enon Ponds are non-functional due to theft & vandalism in WWTW Plant. | 1.Ensure Maintenance of Waste-Water Treatment Works 2. Provide Security measures for Waste-Water Treatment Works Plants. | Target not achieved | 7 monthly testing results from IRIS on effluent |
| INFR 4 | Refurbishment of Enon and Bersheba Water Borne Sanitation | 8 kms of sewer pipelines, lining of ponds and house connections Constructed | Percentage completion of the Enon and Bersheba Water Borne Sanitation Pump Station | (50% of sewer pipe line and 20 manholes completed ) | 8 kms of Construction of sewer pipelines, lining of ponds and 100 house connections | 8kms of construction of sewer pipelines 2. Lining of ponds not done. 3. 30 House Connections. | Community members were against signing for sewer house connections due to them requesting water provision | To ensure appropriate social facilitation and project governance to address any expectation gaps in projects | Target not achieved |  |
| Strategic Objective: SRVM Community has access to good quality roads built according to applicable standards. |  |  |  |  |  |  |  |  |  |  |
| INFR 5 | Upgrading of Roads &Stormwater in Enon and Beersheba – Phase 2 | 1kms of (paved) roads and stormwater Constructed | KMs of new municipal road network | Target not met | 1 KMs of Construction of roads and stormwater | 0 KMs of Construction of roads and stormwater | - Late commencement of work by the Contractor - Whilst this is deemed the root cause, the vacancies in the department contributed | To appoint a full-time Project Manager as the post remains vacant To review and consider an effective contract management system | Target Not Achieved Site clearance 95% Cut to fill 61% Road Prep 87% Sub-base 31% Kerbing 41% | Not achieved |
| INFR 6 | Emergency Flood Repairs at Vygie and Adams Street in Valencia | 1 km of storm water drainage Constructed | 1 km by March 2024 | Target not met | 1 km of Construction of storm water drainage | 1Km of construction of stormwater drainage | N/A | N/A | Target Achieved | Close out report. |
| Strategic Objective: Communities of SRVM with specific reference to youth have access to suitable and affordable recreational and sport facilities and public amenities. |  |  |  |  |  |  |  |  |  |  |
| INFR 7 | Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo (Budget Maintenance) | Percentage progress on Construction of Multi- Purpose Sports Recreational Facility | Nomathamsanqa Multi-Purpose Sports Recreational Facility completed | Target not met | 100% functional sport facility. | 100% functional sport facility. | N/A | N/A | Annual Target Achieved Functional Sports field: High Mast lights Ablution facilities Combi courts Kiosk Water tank irrigation Changerooms Grandstand Security Fencing Athletic Track Movable Grandstand | Progress Reports |
| Strategic Objective: To promote programmes of shared economic growth, land redistribution and general economic redress for the poor and disenfranchised |  |  |  |  |  |  |  |  |  |  |
| INFR 8 | EPWP Programme | 50 EPWP work opportunities created | EPWP: 316 | EPWP: 251 | 50 work opportunities created | 161 work opportunities created | This was due to poor planning. Whilst 50 work opportunities were planned for the year, the shorter period of 6 months or less didn’t take into account that each new opportunity increases the annual target | The Annual target for 2025/26 takes into account the number of intakes for EPWP participants | Annual Target Achieved | EPWP Contracts Listing for EPWP |
| INFR 9 | Land Audit | Number of land audit Conducted | N/A | N/A | land audit document done and completed | Land Audit document not done & completed. | Land Audit project was cancelled due to budget constraints. | Ensure budget is sufficient for land audit. Project has been rolled over into the 2025/2026 FY. | Target not achieved | Not achieved |
| Strategic Objective: Upgrade Electricity network for future development |  |  |  |  |  |  |  |  |  |  |
| INFR 10 | Retrovit of streetlights in Kirkwood | Number of power saving bulbs in Municipal offices, treatment works, and high mast lights provided | 2km of MV and LV line upgraded in Kirkwood town to provide connection to households. | 2km of MV and LV line upgraded in Kirkwood town to provide connection to 270 households. | Supplying 1000 power saving bulbs | 562 Power saving bulbs were supplied | SCM Delay appointing service provider Long lead times to wait for material | To implement effective procurement planning | Target not achieved | 1. Progress Reports 2. Purchase Order 3. Appointment letter of Supply and delivery of energy saving lights in SRVM. |
| Strategic Objective: Ensure access and a continuous supply of good quality water and sanitation to each user by 2026 |  |  |  |  |  |  |  |  |  |  |
| INFR 11 | Refurbishment of Addo and Kirkwood Wastewater Pump Station | Percentage progress on Refurbishment of Kirkwood wastewater pump stations | 100% completion of the refurbishment of the Kirkwood wastewater treatment works | 100% completion of the refurbishment of the Kirkwood wastewater treatment works | 100% Fully Functional wastewater pump station | 100% Fully Functional wastewater pump station | N/A | N/A | Target Achieved | Progress Reports |
| COMMUNITY AND PROTECTION SERVICES |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective: Communities have sufficient and affordable solid waste disposal options to encourage clean and healthy environment |  |  |  |  |  |  |  |  |  |  |
| COM 1 | Maintenance of Landfill sites | Number of landfill sites maintained | N/A | N/A | Two 2 Landfill sites maintained | 4 landfill sites maintained | N/A | N/A | Target Achieved (Kirkwood/Msengeni and Peterson) | Pictures for before and after of maintenance |
| COM 2 | Licensing of Landfill sites | Number of valid waste licenses issued to SRVM | N/A | N/A | 2 valid waste licenses | 0 valid waste licenses | Due to lengthy processes involved, the process had to be rolled over to the next financial year | The process to be rolled over to the next financial year | Target not achieved 1.Submission of communique to DEDEA and follow up 2. Appointment of service provider to conduct EIA for the application of land fill sites licenses | 1. Report of communique to DEDEA 2.Appointment letter of service provider |
| COM 3 | Integrated Waste Management Plan | Council adopted IWMP | N/A | N/A | 1 valid Council adopted IWMP | 1 valid Council adopted IWMP | N/A | N/A | Target Achieved Council adopted Integrated Waste Management Plan (IWMP) | Council resolution Final IWMP (available in soft copy due to size) |
| COM 4 | Eradication of illegal dumping sites | Number of illegal dumping sites eradicated | 8 illegal dumping sites eradicated | 8 illegal dumping sites eradicated | eight (8) illegal dumping site eradicated | Eleven (11) illegal dumping site eradicated | N/A | N/A | Target Achieved (Aqua Park, Msengeni area, Moses Mabhida Taxi Rank, Valencia, Addo Nomathamsanqa and Bersig | Pictures for before and after of maintenance |
| Strategic Objective: Community of SRVM with specific reference to youth have access to sustainable and affordable recreational and sport facilities as well as public amenities |  |  |  |  |  |  |  |  |  |  |
| COM 5 | Facilities Maintain | Number of Municipal buildings facilities maintained | N/A | N/A | Three (3) Municipal buildings Maintained | No municipal buildings maintained | Poor planning, unclear targets about the work to be done and lack of coordination of facilities maintenance | Develop clear and achievable targets and improve monitoring of work implementation | Target not achieved |  |
| COM 6 | Public amenities Sustainability plan | Council approved public amenities Bylaw, Public amenities policy, public amenities Masterplan | N/A | N/A | Gazetted Public amenities Bylaw and Council adopted Public Amenities Policy & Masterplan | Council adopted public amenities bylaw policy Public amenities By Law not gazetted | There was no funding from Sarah Baartman | Council to budget for the gazetting of Public Amenities By-Law | Target not achieved | 1. Council resolution 2. Facility Provision and Management Policy |
| COM 7 | Planting of trees | No. of trees planted | N/A | N/A | 180 Target on Trees planted | 60 out 180 trees planted | Budget constraints | Council budget for planting of trees | Target not achieved | Tree planting attendance register |
| COM 8 | Libraries Outreach programmes | Number of outreach programmes conducted | N/A | N/A | Twelve (12) outreach programmes conducted | Thirteen (13) outreach programmes conducted | N/A | N/A | Target Achieved | 1. Progress Reports 2. Pictures 3. Attendance registers |
| Strategic Objective: To ensure monitoring of water quality and food control |  |  |  |  |  |  |  |  |  |  |
| COM 9 | Environmental Health Inspections | Increased compliance post inspections | N/A | N/A | 100 targets for Inspections | 144 inspections conducted | There was a Wildfees festival during June 2025 with many stalls selling foodstuffs and that resulted to more inspections conducted | The Wildsfees is a private event that happens annually, whilst we can plan for its occurrence, it is beyond the control of the municipality to adopt a remedial action for this over-achievement | Target Achieved | Inspection forms |
| COM 10 |  | Creating community awareness | N/A | N/A | Ad hoc awareness campaigns | 4 Awareness campaigns conducted | N/A | N/A | Target Achieved | Attendance registers |
| Strategic Objective: To ensure provision of traffic services including improved revenue. |  |  |  |  |  |  |  |  |  |  |
| COM 11 | Development and review of by-laws | No. of Traffic by-laws reviewed | N/A | N/A | 6 By-Laws reviewed | 8 By-Laws reviewed | N/A | N/A | Target Achieved | - List of by-laws - Council resolution - By-Laws |
| COM 12 | Revenue enhancement (RR) | Admin | N/A | N/A | 872 135 | 1711 71 | N/A | N/A | Target Achieved 1711 Disc License issued, and 71 Road worthy issued | Transaction summary reports on disc and road worthy issued |
| Strategic Objective: To ensure safety and compliance to Fire safety requirement, disaster management plan and bylaw |  |  |  |  |  |  |  |  |  |  |
| COM 13 | Improved compliance by businesses | Number of inspections conducted, and compliance certificates issued | Average time taken to finalise business license applications | Business license application forms approved within 10 days | 100 | 164 | N/A | N/A | Target Achieved 101 inspections conducted and 63 compliant certificates issued | Inspection forms Compliant certificates |
| GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective: Annual review and development of IDP/ Budget |  |  |  |  |  |  |  |  |  |  |
| GG 1 | Development of IDP | Effective IDP Process for the period under review | N/A | N/A | Final IDP adopted by Council on May 2025 | Final IDP adopted by Council in June 2025 | Whilst the IDP was brought to Council in May for adoption, there were delays in the adoption of the IDP which resulted in the IDP being adopted in June 2025 | Development, implementation and strict monitoring of the IDP Process plan | Target not achieved Albeit adopting later than the envisaged date | Council resolution. Adopted IDP for 2025/26 |
| Strategic Objective: Annual review and development of Annual Report |  |  |  |  |  |  |  |  |  |  |
| GG 2 | Development of Annual Report | Timely submission of Annual Report | N/A | N/A | Submission of Oversight Report on Annual report to Council by Mar-25 | Oversight Report on Annual report submitted to Council | N/A | N/A | Target achieved | Council resolution. |
| Strategic Objective: To establish and strengthen service delivery partnerships between the municipality, district, sector departments, communities and civile society |  |  |  |  |  |  |  |  |  |  |
| GG 3.1 | Youth empowerment | Annual career expo | N/A | N/A | Annual career expo | Annual Career Expo | N/A | N/A | Target achieved | Attendance Register |
| GG 3.2 | Strengthening of IGR | Number of IGR meetings held | N/A | N/A | Four (4) IGR meetings per year | Three (3) IGR meeting held for the year. | One of the IGR meetings was postponed and was not reconvened to reach the targeted number of meetings | Scheduling of IGR meeting well on time in the quarter to cater for any unforeseen postponements | Target not achieved | 1.Minutes of the IGR 2.Agenda and Attendance register. 3. Invitation. |
| GG 4 | Functionality of Audit com | Number of Audit meetings held | N/A | N/A | 4 Audit committee meetings per year | Seven (7) Audit Committee meeting held for the year. | Due to the number of issues that had to be dealt with and the need to address the Disclaimer Audit opinion status, more Special meetings were convened that envisaged | Audit Committee meetings to be scheduled to the number required to achieve the committee mandate | Target achieved | 1.Minutes of Audit Committee meetings |
| GG 5 | Functionality of MPAC | Number of MPAC meetings held | N/A | N/A | Four (4) MPAC meetings held per year | Six (6) MPAC meetings were held for the year. | More MPAC meetings had to be convened to deal with pressing matters | Develop MPAC Workplan for 2025/26 to guide number of meetings to be held | Target achieved | 1.Minutes of MPAC meetings |
| Strategic Objective: To enhance council oversight and to improve audit outcomes |  |  |  |  |  |  |  |  |  |  |
| GG 6 | Development and Implementation of audit action plan | Number of AGSA findings addressed by Management | N/A | N/A | Four (4) quarterly report to AC and Council | Four (4) quarterly reports to AC and Council | N/A | N/A | Target Achieved | 1.Report on Audit Action Plan 2.Implemetation of Audit Action plan status. |
| GG 7 |  |  | 62 repeat audit findings (resolved) | 62 repeat audit findings (resolved) | Number of findings addressed | 54 out of 100 findings achieved as at 30 June 2025 | Despite many Audit Steering Committee sittings to address the findings, many of the issues were attended to beyond 30 June 2025 | - Submit all information required for audit - Develop action plans to address findings - Set realistic and SMART targets | Target Not Achieved | Minutes of Audit Steering Committee meetings |
| Strategic Objective: To Strengthen implementation of internal control |  |  |  |  |  |  |  |  |  |  |
| GG 8 | To developed Fraud Prevention Policy | Number of fraud prevention plan/ policy developed | N/A | N/A | Developed, Reviewed, and adoption of fraud prevention policy | Developed, Reviewed, and adopted fraud prevention policy | N/A | N/A | Target Achieved | Council resolution. Fraud Prevention Policy |
| Strategic Objective: Establish policy framework for LED related policies |  |  |  |  |  |  |  |  |  |  |
| GG 9 | Development of LED Policy | Develop, Review and Approval of LED Strategy | N/A | N/A | Develop, Review and Approval of LED Strategy | Developed, Reviewed and Unapproved LED Strategy | Non-availability of Stakeholders | LED strategy will be Approved in the 2025/26 financial year, upon consulting all relevant stakeholders | Target Not Achieved |  |
| Strategic Objective: To establish LED forum for the implementation of LED Strategy |  |  |  |  |  |  |  |  |  |  |
| GG 10 | Establishment of LED Forum | Functionality of LED Forum | N/A | N/A | LED Forum | LED Forum not established | LED strategy its not yet Approved by Council | LED Forum will be established after the Approval of LED Strategy in this financial year 2025-2026 | Target Not Achieved |  |
| Strategic Objective: To ensure fully functional Performance Management system |  |  |  |  |  |  |  |  |  |  |
| GG 11 | Performance reviews | Four (4) Quarterly performance reviews | N/A | N/A | Four (4) Annual performance reviews conducted | Four(4) Performance review reports conducted | N/A | N/A | Target Achieved |  |
| Strategic Objective: Mainstreaming of all venerable groups . |  |  |  |  |  |  |  |  |  |  |
| GG 12 | Development of Programmes targeting venerable | Four programmes targeting one Venerable group per quarter | N/A | N/A | Four programmes targeting Vulnerable groups | Two Programmes targeting vulnerable groups | Lack of capacity and managerial supervision in implementing programmes | Strategic Manager appointed to oversee implementation of Special Programs | Target Not Achieved |  |
| Strategic Objective: To provide an appropriate environment for the establishment and promotion of self-sustainable SMMEs which participate meaningfully in both the first second economy of the Municipality |  |  |  |  |  |  |  |  |  |  |
| GG 13 | Development and Review of SMME Policy and Strategy | One SMME Policy and Strategy Developed | N/A | N/A | Approved SMME Policy and Strategy | SMME Policy and Strategy not approved | Unavailability of stakeholders. | Strategic Manager appointed to oversee implementation of Special Programs SMME Policy will be sent to Council for approval in the third quarter | Target Not Achieved |  |
| GG 14 | Development of Informal Trading Policy and Establishment of Committee | Development of Informal Trading Policy | N/A | N/A | Informal Trading policy approved | Informal Trading policy not approved. | Lack of capacity and managerial supervision in implementing programmes | Strategic Manager appointed to oversee implementation of Special Programs | Target Not Achieved |  |
| GG 15 | Skills Development and Training of SMMEs | 60 SMMEs trained | N/A | N/A | 60 SMMEs trained | 150 SMME's trained | N/A | N/A | Annual target achieved | 1.Terms of reference 2. Attendance register |
| GG 16 | Establishment of SMME Forum | One SMME Forum established | N/A | N/A | SMME Forum | SMME Forum is not established | There were issues regarding the governance of SMMEs and the distribution of work opportunities for SMMEs, which led to delays in consultations with the SMMEs | SMMEs to be consulted during the 2025/26 financial year, also with the development of the LED Strategy the forum will be established | Target Not Achieved | 1.Terms of reference 2. Attendance register |
| GG 17 | Outreach Workshop programmes | At least 4 outreach workshops |  |  | 4 Outreach workshops | 6 outreach workshops | N/A | N/A | Target Achieved | 1. Attendance register 2. Invitation |
| FINANCIAL MANAGEMENT AND VIABILITY |  |  |  |  |  |  |  |  |  |  |
| INSTITUTIONAL TRANSFORMATION AND DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective: To ensure the Municipality approves the organogram and fills vacancies to support the implementation of IDP |  |  |  |  |  |  |  |  |  |  |
| ID 1 | Development and review of institutional structure | Reviewed Organizational structure populated (less than 10% vacancy rate) | N/A | N/A | Development and review of organizational structure for 24/25 and 25/26 | Organizational structure for 24/25 and 25/26 developed and reviewed | N/A | N/A | Target Achieved | Council resolution. |
| Strategic Objective: capacity building and empowerment programmes to ensure skills enhancement of staff |  |  |  |  |  |  |  |  |  |  |
| ID 2 | Skill development programmes | Number of Training interventions and capacity building for staff members | N/A | N/A | MFMP = 20 OD Training = 5 Advanced MS Excel = 15. Project Management = 4 Advanced Strategic Management = 4 Coaching and Mentoring Programme=10 | 1. MFMP = 20 2. OD Training = 20 3. 10 Employees were trained on project management. 4. Advance strategic management training not done | Target was not SMART | To set SMART targets for training in the 2025/26 financial year | Target Not Achieved | Attendance registers |
| Strategic Objective: To ensure effective public participation of ward committees |  |  |  |  |  |  |  |  |  |  |
| ID 3 | Ward Committees participation | Involvement of All eight (8) ward committees in public engagements | 100% ward committees with 6 or more ward committee members (excluding the ward councillor) | 100% ward committees with 6 or more ward committee members (excluding the ward councillor) | 32 Ward Committees meetings facilitated per year | 23 Ward meetings held out of 32 meetings | Non-availability of Committee members and Ward Councillors not calling meetings as per schedule | Meeting to be arranged with Office of Speaker to address the matter Council to consider referring matters of non-sitting to Ethics Committee | Target Not Achieved | 1.Attendance Registers 2.Minutes of the Meeting |
| Strategic Objective: To optimize the information and communication technology (ICT) function to support organizational performance |  |  |  |  |  |  |  |  |  |  |
| ID 4 | AD configuration and installation of Proxy Server | Installation of Proxy Server | N/A | N/A | Installation and configuration of A.D and proxy Server | Installation and configuration of A.D and proxy Server completed | N/A | N/A | Target Achieved | Report on the installation and configuration of A.D and Proxy server |
| ID 5 | Installation of UPS(Uninterrupted Power Supply) | Installation of UPS | N/A | N/A | Installation of UPS in the server room | Installation of UPS in the server room completed | N/A | N/A | Target Achieved | Purchase order of UPS Pictures of UPS |
| ID 6 | Installation of Wireless Access points (Wi-fi) | Installation of Wireless Access Points | N/A | N/A | Installation of 3 (three) Wi-Fi points | Three Wi-Fi access points not installed | Budget constraints | Budgeted for in 2025/2026 FY | Target Not Achieved |  |
| Strategic Objective: To enhance employee wellness through prevention and provision of therapeutic programmes and physical fitness |  |  |  |  |  |  |  |  |  |  |
| ID 7 | Improve Employee Wellness through conducting a number of wellness programmes | Conduct a number of Employee Wellness prevention, therapeutic and physical fitness programmes in the 2024/25FY | N/A | N/A | 4 Employee Wellness programmes | 5 wellness programs conducted | N/A | N/A | Target Achieved | Attendance registers |
| ID 8 | Implementation of the Occupational Health and Safety Act and COIDA | Conduct regular meetings with the OHS Committee and inspections | N/A | N/A | 4OHS Committee Meetings and inspection Conduct 1 OHS Training to Committee members | 1 OHS Committee Meeting and 1 inspection conducted | Lack of budget due to cash flow challenges | To advocate for more budget resources and look at other creative ways to fund OHS activities | Target Not Achieved | Notice of inspection |
| ID 9 | Implementation of the HIV/AIDS prevention plan | Ensure the establishment of LAC to develop HIV/Aids prevention plan | N/A | N/A | Conduct 4 HIV/AIDS prevention / awareness programmes and other Communicable diseases. Attending (4) scheduled LAC meeting . | 3 out of 4 HIV/AIDS prevention / awareness programmes and other Communicable diseases held | Lack of budget, due to cash flow challenges | Lack of budget, due to cash flow challenges | Target Not Achieved | Attendance registers |
| ID 10 | Implementation of the Workplace Skills Plan Regulations and EE Act | Ensure the submission of an approved Workplace skills plan | N/A | N/A | Development of an Annual Training Plan (ATP) | Annual Training Plan (ATP) Developed | N/A | N/A | Target Achieved | The letter of Department of Labour |
| ID 11 |  | Development of EE Plan and submission of EE report | N/A | N/A | Submission of the approved EE Report and compliance with EE Act and other prescripts | Submission of the approved EE Report and compliance with EE Act and other prescripts completed | N/A | N/A | Target Achieved | The letter of department of Labour |
| ID 12 | Improvement of working employee relations and labour peace as per the BCEA and LRA | Improve the functionality of the LLF Committee | N/A | N/A | 4 LLF meetings and rollout of the Code of Conduct for 120 officials | 1 LLF meeting Rollout of the Code of Conduct for 112 officials | Non availability of stakeholders and non-submission of items for the agenda | To develop an LLF workplan/action plan with all matters raised in previous sittings and ensure close monitoring of sittings and that issues are included in the agenda | Target Not Achieved | 1.Attendance register of LLF, 2.Agenda of LLF 3. Attendance register of code of conduct session. |
| Strategic Objective: To ensure effective and efficient records management |  |  |  |  |  |  |  |  |  |  |
| ID 13 | Review and Development of policies | Review and development of HR policies in line with Legislative Requirements | N/A | N/A | 10 HR Policies Reviewed / Developed | 12 HR Policies were developed, reviewed and adopted by council | N/A | N/A | Target Achieved | Council resolution |
| ID 13 | Develop and review Records Management Policy | Develop Records Management Policy and SOP | N/A | N/A | Review Records Management Policy and develop SOP | Reviewed Records Management Policy and SOP developed | N/A | N/A | Target Achieved | 1.Report on the state of records management 2. Attendance register of records management and ICT seminar |

- COLOR CODES:

The following colour codes have been used in the Annual Performance Report.

|  | Previous financial year actuals |
| --- | --- |
|  | Current financial year annua targets and actuals |
|  | Achieved targets – CY Also, Strategic Objectives CY |
|  | Targets not achieved – CY |
|  | Department name |

# CHAPTER 4 – ORGANISATIONAL DEVELOPMENT PERFORMANCE

# (PERFORMANCE REPORT PART II)

# COMPONENT A:  INTRODUCTION TO MUNICIPAL PERSONNEL

## Employee Total, Vacancies and Turnover

Table: Staff Compliment

| Directorate |  | Positions on structure | Filled positions | Vacant positions |
| --- | --- | --- | --- | --- |
| Office of the mayor |  | 4 | 4 | 0 |
| Municipal manager |  | 16 | 14 | 2 |
| Corporate services |  | 36 | 34 | 2 |
| Financial services |  | 44 | 42 | 2 |
| Community services |  | 113 | 99 | 14 |
| Technical Services |  | 95 | 84 | 11 |
| Total |  | 308 | 282 | 31 |

Table: Vacancy rate

### 4.2	POLICIES

A total of 12 policies is being reviewed and new ones developed and still in draft form. Namely:

- Recruitment and Selection Policy

- End user Car Scheme Policy,

- Induction and Orientation Policy,

- Acting Policy,

- SMME Policy,

- Termination and Exit Management Policy,

- Promotion and Transfer Policy,

- Counselling Policy,

- Dress Code

- Fraud Prevention Policy

- Danger Allowance Policy

- Risk Management Framework/ Policy

## COMPONENT C: CAPACITATING THE MUNICIPAL WORKFORCE

## 4.2	 Workforce Profile

The total number of employees (including employees with disabilities) in each of the following.

Occupational levels: Note: A=Africans, C=Colored, I=Indians and W=Whites

| Occupational Levels | MALE |  |  |  | FEMALE |  |  |  | FOREIGN NATIONALS |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | A | C | I | W | A | C | I | W | MALE | FEMALE |  |
| Top management | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4 |
| Senior management | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 |
| Professionally qualified and experienced specialists and mid- management | 5 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 | 0 | 17 |
| Skilled technical and academically qualified workers, junior management, supervisors, supervisors, and superintendents | 27 | 8 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 48 |
| Semi- skilled and discretionary decision making | 21 | 6 | 0 | 0 | 47 | 10 | 0 | 2 | 0 | 0 | 86 |
| Unskilled and defined decision making | 66 | 22 | 0 | 1 | 24 | 5 | 0 | 1 | 0 | 0 | 119 |
| TOTAL PERMANENT | 124 | 36 | 0 | 2 | 96 | 15 | 0 | 5 | 0 | 0 | 278 |
| Temporary employees | 22 | 6 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 30 |
| GRAND TOTAL | 146 | 42 | 0 | 2 | 97 | 16 | 0 | 5 | 0 | 0 | 308 |

### People with Disabilities

The total number of employees with disabilities only in each of the following occupational levels: Note: A=Africans, C=Colored, I=Indians and W=Whites

| Occupational Levels | MALE |  |  |  | FEMALE |  |  |  | FOREIGN NATIONALS |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | A | C | I | W | A | C | I | W | MALE | FEMALE |  |
| Top management |  |  |  |  |  |  |  |  |  |  |  |
| Senior management |  |  |  |  |  |  |  |  |  |  |  |
| Professionally qualified and experienced specialists and mid- management |  |  |  |  |  |  |  |  |  |  |  |
| Skilled technical and academically qualified workers, junior management, supervisors, supervisors, and superintendents |  |  |  |  |  |  |  |  |  |  |  |
| Semi- skilled and discretionary decision making | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 |
| Unskilled and defined decision making | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |
| TOTAL PERMANENT |  |  |  |  |  |  |  |  |  |  |  |
| Temporary employees |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL | 3 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 |

Table: 6

### Recruitment

The total number of new recruits, including people with disabilities, are reflected below. Note: A=Africans, C=Colored, I=Indians and W=Whites

Table to be updated.

### Skills Matrix

| Management Level | Gender | Number of employees identified for training at the start of the year. | Number of Employees that received training. |
| --- | --- | --- | --- |
| MM and S57 | Female | 0 | 0 |
|  | Male | 0 | 0 |
| Legislators, senior officials, and managers | Female | 1 | 1 |
|  | Male | 5 | 5 |
| Associate professionals and Technicians | Female | 4 | 4 |
|  | Male | 3 | 3 |
| Professional | Female | 4 | 4 |
|  | Male | 2 | 2 |
| Clerks | Female | 32 | 32 |
|  | Male | 5 | 5 |
| Plant and machine operators and assemblers | Female | 0 | 0 |
|  | Male | 0 | 0 |
| Elementary occupations | Female | 0 | 0 |
|  | Male | 12 | 12 |
| Sub total | Female |  |  |
|  | Male |  |  |
| Total |  | 68 | 68 |

### 4.6	EMPLOYEE EXPENDITURE

The municipality is still within the personnel cost threshold set by National Treasury between 25% - 40% (SRVM currently standing at 36% of the total operating budget.

COMMENT ON WORKFORCE EXPENDITURE:

- Job Evaluation processes have started in earnest and costing implications have been made for payments to be affected in the new fiscal year with effect from 01 July 2023.

- A total of 136 approved positions in the reviewed organogram have written Job Descriptions, except newly created positions namely HR Manager and Legal Services Practitioner at Corporate Services, Finance Manager at BTO and Building Inspector at Technical Services,

- Some employees have been placed in vacant positions due to their reviewed and approved organogram on 8th July 2022.

- The personnel costs have marginally increased but are still within the National Treasury Norms and Standards, currently standing at 36% of the Total Operating Budget.

DISCLOSURES OF FINANCIAL INTERESTS

NB: Disclosures have been made by ALL Senior Managers, not aware of the other categories of employee.

# CHAPTER 5 – FINANCIAL PERFORMANCE

INTRODUCTION

Chapter 5 contains information regarding financial performance and highlights specific accomplishments. The chapter comprises of three components:

- Component A: Statement of Financial Performance

- Component B: Spending Against Capital Budget

- Component C: Other Financial Matters

## COMPONENT A: STATEMENTS OF FINANCIAL PERFORMANCE

The 2024/2025 Medium Term Revenue and Expenditure Framework (MTREF) was prepared in terms of the approved Integrated Development Plan and Budget process plan approved by the Council.

ACCOUNTING AND REPORTING

The municipality has the necessary financial-related policies approved by Council and these policies are reviewed annually. The implementation of policies assists in ensuring compliance with the Standard of Generally Recognized Accounting Practices (GRAP).

The annual financial statements are prepared internally in terms of GRAP. The unaudited annual financial statements have been prepared on the going-concern basis and were approved by the Accounting Officer on the 31 August 2025.

### 5.1	STATEMENTS OF FINANCIAL PERFORMANCE

### 5.2	GRANTS

### ASSET MANAGEMENT

| TREATMENT OF THE THREE LARGEST ASSETS ACQUIRED YEAR 0 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Asset 1 |  |  |  |  |
| Name | Water and Sanitation |  |  |  |
| Description | KIRWOOD WWTW - GREEN DROP REPRIORTISATION PROJECT |  |  |  |
| Asset Type | Work- in-progress (Infrastructure Asset) |  |  |  |
| Key Staff Involved | Technical Service |  |  |  |
| Staff Responsibilities | Director Technical Services |  |  |  |
| Asset Value | Year -3 | Year -2 | Year -1 | Year 0 |
|  |  |  |  | 19 247 011 |
| Capital Implications | Acquired through grant funding |  |  |  |
| Future Purpose of Asset | Service Delivery |  |  |  |
| Describe Key Issues | Ensure service backlogs are addressed in the community |  |  |  |
| Policies in Place to Manage Asset | Yes |  |  |  |
| Asset 2 |  |  |  |  |
| Name | Sports and Recreational Facilities |  |  |  |
| Description | CONSTRUCTION OF A NEW MULTI-PURPOSE SPORT RECREATIONAL FACILITY AT NOMATHAMSANQA |  |  |  |
| Asset Type | Work- in-progress (Infrastructure Asset) |  |  |  |
| Key Staff Involved | Technical Service |  |  |  |
| Staff Responsibilities | Director Technical Services |  |  |  |
| Asset Value | Year -3 | Year -2 | Year -1 | Year 0 |
|  |  |  | 1 617 571,87 | 15 827 854,20 |
| Capital Implications | Acquired through grant funding |  |  |  |
| Future Purpose of Asset | Service Delivery |  |  |  |
| Describe Key Issues | Promote safety and recreational activities |  |  |  |
| Policies in Place to Manage Asset | Yes |  |  |  |
| Asset 3 |  |  |  |  |
| Name | Community Assets |  |  |  |
| Description | CONSTRUCTION OF MOSES MABIDA MULTIPURPOSE SPORTS HALL |  |  |  |
| Asset Type | Work- in-progress (Infrastructure Asset) |  |  |  |
| Key Staff Involved | All |  |  |  |
| Staff Responsibilities | All |  |  |  |
| Asset Value | Year -3 | Year -2 | Year -1 | Year 0 |
|  |  |  | 4 272 105,35 | 10 460 581,53 |
| Capital Implications | Acquired through grant funding |  |  |  |
| Future Purpose of Asset | Service Delivery |  |  |  |
| Describe Key Issues | Promote safety and recreational activities |  |  |  |
| Policies in Place to Manage Asset | Yes |  |  |  |
|  |  |  |  | T 5.3.2 |

### FINANCIAL RATIOS BASED ON KEY PERFORMANCE INDICATORS

### 5.5	CAPITAL EXPENDITURE

### 5.6	SOURCES OF FINANCE

Please see: Appendices

### CAPITAL SPENDING ON 5 LARGEST PROJECTS

| Project Name | Contractor Name | Consultant Name | Funder | Budgeted In 2023/24 | Status Quo |
| --- | --- | --- | --- | --- | --- |
| Upgrading of Roads &Stormwater in Enon and Bersheba – Phase 2 | N/A | LA Consultant Engineers | MIG | R 5 069 402.00 | Construction phase |
| Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo | Matela Civil and Construction | Melokuhle Management | MIG | R 3 625 496.00 | Project is in construction phase. |
| Construction of a New Community Hall in Moses Mabhida | ZKS Projects | Buchule Engineers | MIG | R 4 030 119.00 | Completed |
| Refurbishment of Enon and Bersheba Water Borne Sanitation- Phase 1 | ZKS Projects | Black Mountain Engineers | MIG | R 6 032 129.00 | Construction phase |
| Emergency flood works in Vygie and Adam Street | N/A | LA Consultant | MIG | R5 500 000 | . Construction in progress. |
| Zinyoka Electrification | N/A | Vokon | INEP | R 6 512 000 | Project completed. |
| 15 km Zinyoka MV Line | N/A | Vokon | INEP | R 4 000 0000 | Completed |
| Electrification of Aqua Park Household | N/A | Vokon | INEP | R 7 036 000 | Completed |
| Kirkwood WWTW - Green Drop Reprioritization | N/A | Lech Consultants | WSIG | R 14 785 446.00 | Completed. |
| Nomathamsanqa: Completion of Water Backlogs | N/A | Bosch Projects | WSIG | R 2 96 619,80 | Completed |
| Refurbishment of Kirkwood & Addo Wastewater Pumps | N/A | Lech Consultants | WSIG | R 9 538 000.00 | Completed |
| Repairing of Roads & Stormwater cleaning in SRVM | N/A | N/A | EPWP | R 980 000.00 | Complete |

### BASIC SERVICE AND INFRASTRUCTURE BACKLOGS – OVERVIEW.

The following are priority problems that need to be addressed as a matter of urgency.

Old, dilapidated, and Irreparable infrastructure (Roads & Stormwater, Water and Sewer Pipelines, Water & Sewer Treatment Works)

Poorly planned, poorly designed infrastructure (with inherent challenges)

Neglected infrastructure (due to poor or no maintenance and insufficient finances to eradicate the backlog.)

Services provided at a loss resulting in loss of revenue due to water losses and illegal electricity connections.

Vandalism to all Infrastructure assets (Water & Waste Treatment Works Plants, theft of high mast lights cables, Copper from overhead lines)

Rapid illegal growth of informal settlements due to population growth that Is not catered for.

No Land audit to identify pockets of land for development.

## COMPONENT C: CASH FLOW MANAGEMENT AND INVESTMENTS

### 5.9 CASH FLOW

5.10	BORROWING AND INVESTMENTS

### PUBLIC PRIVATE PARTNERSHIPS

| Public Private Partnerships Entered into during Year |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | R' 000 |
| Name and Description of Project | Name of Partner(s) | Initiation Date | Expiry date | Project manager | Value |
| The Municipality does not have Public Private Partnerships as all projects belong to the Municipality and appoints service providers to do all projects |  |  |  |  |  |

## COMPONENT D: OTHER FINANCIAL MATTERS

### 5.12	SUPPLY CHAIN MANAGEMENT

The municipality has a Supply Chain Management Policy, and it incorporates the recent amendment of B-BEE Regulations which came into effect on the 1st of April 2017. The internal control environment is not so strong, and it needs some improvements.

All the bid committees are in place and sufficient warm bodies are employed to ensure adherence to procurement regulations. Training has been provided for SCM unit to capacitate officials ensuring improved service delivery.

### 5.13	GRAP COMPLIANCE

GRAP is the acronym for Generally Recognized Accounting Practice, and it provides the rules by which municipalities are required to maintain their financial accounts. Successful GRAP compliance will ensure that municipal accounts are comparable and more informative for the municipality. It will also ensure that the municipality is more accountable to its citizens and other stakeholders. Information on GRAP compliance is needed to enable the National Treasury to assess the pace of progress and consider the implications.

# CHAPTER 6 – AUDITOR GENERAL AUDIT FINDINGS

INTRODUCTION

Note: Constitution S188 (1) (b) states that the functions of the Auditor-General include the auditing and reporting on the accounts, financial statements, and fiscal management of all municipalities. MSA section 45 states that the results of performance measurement… must be audited annually by the Auditor-General.

Refer to the Annual Financial Statements set out in    Volume II and the timescale for the audit of these accounts and the audit of performance and the production of reports on these matters by the Auditor General as set out in this Chapter. If this is the version of the annual report presented to Council in September, then the Auditor-Generals statements on this year’s submissions will not be available for inclusion in this Chapter and this should be explained.

## COMPONENT A: AUDITOR-GENERAL OPINION OF FINANCIAL STATEMENTS Year -1

### 6.1 AUDITOR GENERAL REPORTS Year -1 (Previous year) SRVM AUDIT REPORT - 30 June 2024

## COMPONENT B: AUDITOR-GENERAL OPINION YEAR 0 (CURRENT YEAR)

### 6.2 AUDITOR GENERAL REPORT YEAR 0

AUDITOR GENERAL REPORT ON THE FINANCIAL STATEMENTS: YEAR 0

COMMENTS ON AUDITOR-GENERAL’S OPINION

An audit outcome like the 2024/2025 outcome was expected under the following circumstances.

- Lack of stability and continuing management is essential for any organization to function effectively.

- Lack of consequence management.

SRVM must take this opportunity to build on this undesired audit opinion, and it can only improve in the future.

COMMENTS ON MFMA SECTION 71 RESPONSIBILITIES

The returns on financial performance data are returned to the National Treasury on a quarterly basis within 10th day after the end of the quarter. The data strings are returned to the municipality where there are differences in calculations, and the municipality rectifies those issues. The Municipal Manager and the CFO sign the verifications for submissions.

Signed (Chief Financial Officer) …………………………

COMMENTS ON AUDITOR-GENERAL’S OPINION YEAR 0:

T 6.2.4

COMMENTS ON MFMA SECTION 71 RESPONSIBILITIES:

Section 71 of the MFMA requires municipalities to return a series of financial performance data to the National Treasury at specified intervals throughout the year. The Chief Financial Officer states that these data sets have been returned according to the reporting requirements.

Signed (Chief Financial Officer) ……………………………………………………….... Dated

T 6.2.5

# GLOSSARY

| Accessibility indicators | Explore whether the intended beneficiaries can access services or outputs. |
| --- | --- |
| Accountability documents | Documents used by executive authorities to give “full and regular” reports on the matters under their control to Parliament and provincial legislatures as prescribed by the Constitution. This includes plans, budgets, in-year, and Annual Reports. |
| Activities | The processes or actions that use a range of inputs to produce the desired outputs and outcomes. Activities describe "what we do". |
| Adequacy indicators | The quantity of input or output is relative to the need or demand. |
| Annual Report | A report to be prepared and submitted annually based on the regulations set out in Section 121 of the Municipal Finance Management Act. Such a report must include annual financial statements as submitted to and approved by the Auditor-General. |
| Approved Budget | The annual financial statements of a municipality as audited by the Auditor General and approved by the council or a provincial or national executive. |
| Baseline | Current level of performance that a municipality aims to improve when setting performance targets. The baseline relates to the level of performance recorded in a year prior to the planning period. |
| Basic municipal service | A municipal service that is necessary to ensure an acceptable and reasonable quality of life to citizens within that area. If not provided it may endanger public health and safety or the environment. |
| Budget year | The fiscal year for which an annual budget is to be approved – means a year ending on 30 June. |
| Cost indicators | The overall cost or expenditure of producing a specified quantity of outputs. |
| Distribution indicators | The distribution of capacity to deliver services. |
| Financial Statements | Includes at least a statement of financial position, statement of financial performance, cash-flow statement, notes to these statements and any other statements that may be prescribed. |
| General Key performance indicators | After consultation with MECs for local government, the Minister may prescribe general key performance indicators that are appropriate and applicable to local government. |
| Impact | The results of achieving specific outcomes, such as reducing poverty and creating jobs. |
| Inputs | All the resources that contribute to the production and delivery of outputs. Inputs are "what we use to do the work". They include finances, personnel, equipment, and buildings. |
| Integrated Development Plan (IDP) | Set out municipal goals and development plans. |
| National Key performance areas | - Service delivery & infrastructure. - Economic development - Municipal transformation and institutional development - Financial viability and management - Good governance and community participation |
| Outcomes | The medium-term results for specific beneficiaries are the consequence of achieving specific outputs. Outcomes should relate clearly to an institution's strategic goals and objectives set out in its plans. Outcomes are "what we wish to achieve". |
| Outputs | The final products, or goods and services produced for delivery. Outputs may be defined as "what we produce or deliver". An output is a concrete achievement (i.e., a product such as a passport, an action such as a presentation or immunization, or a service such as processing an application) that contributes to the achievement of a Key Result Area. |
| Performance Indicator | Indicators should be specified to measure performance in relation to input, activities, outputs, outcomes, and impacts. An indicator is a type of information used to gauge the extent to which an output has been achieved (policy developed, presentation delivered, service rendered) |
| Performance Information | Generic terms for non-financial information about municipal services and activities. It can also be used interchangeably with performance measures. |
| Performance Standards: | The minimum acceptable level of performance or the level of performance that is accepted. Standards are informed by legislative requirements and service-level agreements. Performance standards are mutually agreed criteria to describe how well work must be done in terms of quantity and/or quality and timeliness, to clarify the outputs and related activities of a job by describing what the required result should be. In this EPMDS performance standards are divided into indicators and the time factor. |
| Performance Targets: | The level of performance that municipalities and their employees strive to achieve. Performance Targets relate to current baselines and express a specific level of performance that a municipality aims to achieve within a given time. |
| Service Delivery Budget Implementation Plan | Detailed plan approved by the mayor for implementing the municipality’s delivery of services; including projections of the revenue collected and operational and capital expenditure by vote for each month. Service delivery targets and performance indicators must also be included. |
| Vote: | One of the main segments into which a budget of a municipality is divided for appropriation of money for the different departments or functional areas of the municipality. The Vote specifies the total amount that is appropriate for the purpose of a specific department or functional area. Section 1 of the MFMA defines a “vote” as: one of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriate for the purposes of the department or functional area concerned |

APPENDICES

## APPENDIX A – COUNCILLORS; COMMITTEE ALLOCATION AND COUNCIL ATTENDANCE

| Councilors | 31/07/24 | 30/08/24 |  | 27/09/24 |  | 01/10/24 |  | 11/10/25 |  | 23/10/24 |  | 30/10/24 |  | 31/10/24 |  | 11/12/24 |  | 31/01/25 |  |  | 10/02/25 |  | 17/02/25 |  | 28/02/25 | 07/03/25 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cllr L E Baka | ü | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr N R Baxana | ü | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr H Bayini | apology | ü |  | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  |  |  |  |  |  | apology |  | ü | ü |
| Cllr M Bosman | ü | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr A Dyantyi | ü | ü |  | ü |  | ü |  | ü |  | ü |  |  |  | apology |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr S Hendricks | ü | ü |  | ü |  | ü |  | apology |  | ü |  | apology |  | ü |  | ü |  | ü |  |  | ü |  |  |  |  | apology |
| Cllr H Jagers | ü | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | apology |  | ü |  | ü |  |  | ü |  | ü |  | ü | apology |
| Cllr X J Jonas | ü | ü |  | apology |  | apology |  | apology |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü |  |
| Cllr N Langbooi | ü | ü |  | ü |  | apology |  | ü |  | apology |  | ü |  | ü |  | ü |  | apology |  |  | ü |  | apology |  | ü | apology |
| Cllr S Lucas | ü | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr N P Ncambele | ü | ü |  | apology |  | apology |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr A Ndawo | ü | ü |  | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü |  |  | apology |  | apology |  | apology | apology |
| Cllr S Nodonti | ü | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr M C Payi | ü | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr Z Qusheka | ü | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Cllr K Smith | ü | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  | ü |  | ü |  | ü | ü |
| Councilor |  |  | 31/03/25 |  | 03/04/25 |  | 17/04/25 |  | 23/04/25 |  | 09/05/25 |  | 30/05/25 |  | 06/06/25 |  | 13/06/25 |  | 20/06/25 | 27/06/25 |  | 02/07/25 |  |
| Cllr L E Baka |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  |  |  |
| Cllr N R Baxana |  |  | ü |  | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü |  |  |  |  |
| Cllr H Bayini |  |  | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü |  | ü |  |  |  |  |
| Cllr M Bosman |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  |  |  |  |
| Cllr A Dyantyi |  |  | ü |  | ü |  | ü |  | ü |  | apology |  | apology |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr S Hendricks |  |  | apology |  | apology |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr N Jagers |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr X J Jonas |  |  | ü |  | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr N Langbooi |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr S Lucas |  |  | ü |  | ü |  | apology |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr N P Ncambele |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr A Ndawo |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr S Nodonti |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr M Payi |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü | apology |  | ü |  |
| Cllr Z Qusheka |  |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |
| Cllr K Smith |  |  | ü |  | ü |  | ü |  | ü |  | apology |  | ü |  | ü |  | ü |  | ü | ü |  | ü |  |

| Councilors, Committees Allocated and Council Attendance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Council Members | Full Time / Part Time | Committees Allocated | *Ward and/ or Party Represented | Percentage of Council Meetings Attendance | Percentage Apologies for non-Attendance |
|  | FT/PT |  |  | % | % |
| Baka L E | PT | MPAC Chair | Ward 4 | 96 | 4 |
| Baxana N | PT | Finance, Admin & IDP/LED Infrastructure | Ward 6 | 96 | 4 |
| Bosman M | PT | Finance & Admin Infrastructure MPAC | PR | 100 | 0 |
| Bayini H | PT | Finance, Admin & IDP/LED | PR | 84 | 16 |
| Dyantyi S | PT | Infrastructure MPAC | PR | 88 | 12 |
| Hendricks | PT | Community Services | PR | 80 | 20 |
| Jagers | PT | Finance, Admin & IDP/LED Community Services | PR | 96 | 4 |
| Jonas X | PT | Finance, Admin & IDP/LED MPAC | Ward 3 | 88 | 12 |
| Langbooi N | PT | Finance, Admin & IDP/LED Community Services MPAC District Council | Ward 2 | 76 | 16 |
| Ncambele N | PT | Community Services Infrastructure | Ward 8 | 92 | 8 |
| Ndawo A | PT |  | Ward 7 | 88 | 12 |
|  |  | Community Services |  |  |  |
|  |  | MPAC |  |  |  |
| Nodonti S | FT | Speaker | PR | 100 | 0 |
| Payi M | FT | Infrastructure Chair | Ward 1 | 96 | 4 |
| Qusheka Z | PT | Infrastructure Community Services | Ward 5 | 92 | 8 |
| Lucas S | FT | Finance, Admin & IDP/LED EXCO Chair | PR | 92 | 8 |
| Smith K | FT | Community Services Chair | PR | 96 | 4 |

## APPENDIX B – COMMITTEES AND COMMITTEE PURPOSES

| Committees (other than Mayoral / Executive Committee) and Purposes of Committees |  |
| --- | --- |
| Municipal Committees | Purpose of Committee |
| Finance, Administration & LED Committee | Investigate and make recommendations to the executive committee on all matters within its functional area. |
| Infrastructure Services Committee | Investigate and make recommendations to the executive committee on all matters within its functional area. |
| Community Services Committee | Investigate and make recommendations to the executive committee on all matters within its functional area. |

## APPENDIX C –THIRD TIER ADMINISTRATIVE STRUCTURE

| Third Tier Structure |  |
| --- | --- |
| Directorate | Director/Manager (State title and name) |
| MM’s Office | Strategic Services Manager (vacant) |
|  | Mr. S Nkuntayi (CAE) |
| Corporate Services | Mrs. S. Fourie (Manager Administration) |
|  | Mr. S. Ntongana (Senior ICT Administrator) |
| Community Services | Mr. N.G Kandile (Chief Traffic Officer) |
|  | Mrs. E. Fourie (Acting Principal Librarian) Mr. J. Mokweni (Chief Fire Officer) |
| Engineering Services | Mr. R Herholdt (Manager Technical Services) Ms. N. Ntlantsana (PMU) |
|  | Mr. V Mata (Superintendent) |
|  | Mr. X Louw (Superintendent) |
| Finance Department | Mrs. O Tyhali (Senior Accountant) |
|  | Ms. T Vetsheza (Senior Accountant) |
|  | Ms. Joko (Senior Accountant) Ms. A. Mtshikwana (Senior Accountant) |

## APPENDIX D – FUNCTIONS OF MUNICIPALITY / ENTITY

| Municipal / Entity Functions |  |  |
| --- | --- | --- |
| MUNICIPAL FUNCTIONS | Function Applicable to Municipality (Yes / No) * | Function Applicable to Entity (Yes / No) |
| Constitution Schedule 4, Part B functions: |  |  |
| Air pollution | Yes |  |
| Building regulations | Yes |  |
| Childcare facilities | No |  |
| Electricity and gas reticulation | Yes | Eskom |
| Firefighting services | Yes |  |
| Local tourism | No | LTO |
| Municipal airports | No |  |
| Municipal planning | Yes |  |
| Municipal health services | No |  |
| Municipal public transport | No |  |
| Municipal public works only in respect of the needs of municipalities in the discharge of their responsibilities to administer functions specifically assigned to them under this Constitution or any other law | Yes |  |
| Pontoons, ferries, jetties, piers, and harbors, excluding the regulation of international and national shipping and matters related thereto | No |  |
| Storm-water management systems in built-up areas | Yes |  |
| Trading regulations | Yes |  |
| Water and sanitation services limited to potable water supply systems and domestic wastewater and sewage disposal systems | Yes |  |
| Beaches and amusement facilities | No |  |
| Billboards and the display of advertisements in public places | Yes |  |
| Cemeteries, funeral parlours, and crematoria | Yes |  |
| Cleansing | Yes |  |
| Control of public nuisances | Yes |  |
| Control of undertakings that sell liquor to the public | No |  |
| Facilities for the accommodation, care, and burial of animals | No |  |
| Fencing and fences | No |  |
| Licensing of dogs | No |  |
| Licensing and control of undertakings that sell food to the public | Yes |  |
| Local amenities | Yes |  |
| Local sport facilities | Yes |  |
| Markets | Yes |  |
| Municipal abattoirs | No |  |
| Municipal parks and recreation | Yes |  |
| Municipal roads | Yes |  |
| Noise pollution | Yes |  |
| Pounds | Yes |  |
| Public places | Yes |  |
| Refuse removal, refuse dumps and solid waste disposal | Yes |  |
| Street trading | Yes |  |
| Street lighting | Yes |  |
| Traffic and Parking | Yes |  |

## APPENDIX E – WARD REPORTING

| Functionality of Ward Committees |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Ward Name (Number) | Name of Ward Councilor and elected Ward committee members | Committee established (Yes / No) | Number of monthly Committee meetings held during the year | Number of monthly reports submitted to Speakers’ Office on time | Number of quarterly public ward meetings held during year |
| Ward 1 | Cllr Payi | Yes | 9 | 0 | 3 |
|  | Tiyo NG. Same-Madikane PC. Jonas S T. Makana S G. Mni X C. Screetch M. Matyu S T. Nyanisile. Mboya N. Kebe N. |  |  |  |  |
| Ward 2 | Cllr Langbooi | Yes | 2 | 0 | 0 |
|  | Jack P Jinikwe NP Marotya B Nyati A Plaatjies M Swartbooi N |  |  |  |  |
| Ward 3 | Cllr Jonas | Yes | 4 | 0 | 0 |
|  | Dolph H Gatyeni N Gebuza N Jacobs L Kimberly Z Matwa M Mto N Pullen C Tyali L Peteni S. |  |  |  |  |
| Ward 4 | Cllr Baka | Yes | 2 | 0 | 4 |
|  | Jantjies N. Manene S. Mbola N. Mfeketho N. Nkewana N. Nofemele TP. Pukwana P. Sajini M C. Sokupa M A. Syce D W. |  |  |  |  |
| Ward 5 | Cllr Qusheka | Yes | 4 | 0 | 1 |
|  | Apolisi Z. MithiyoT. Somya F. Macezu M. Ngogela V. Twana A. July Z. Matthews F. Williams M. Somya S. |  |  |  |  |
| Ward 6 | Cllr Baxana | Yes | 3 | 0 | 0 |
|  | Kuboni N. Mkokeli B. Mlatho N. Ndzengu N. Ngindana L. Nopote Z. Scritsh A. Stemele A. Tiervlei B. |  |  |  |  |
| Ward 7 | Cllr Ndawo | Yes | 2 | 0 | 0 |
|  | Plaatjie P. Uithaler J. Nyiki N. Andries S. Takane N. Smith CC. Dobo Y. Dixie P. Langbooi F. Pezisa R. |  |  |  |  |
| Ward 8 | Cllr Ncambele | Yes | 2 | 0 | 0 |
|  | Hopo M. Jackson N. Kleinbooi S. Mangala S. MangcakaX. Matomela N. Mboniswa M Rooi I. |  |  |  |  |

## APPENDIX F – WARD INFORMATION

| Ward Title: Ward Name (Number) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Capital Projects: Seven Largest in Year 0 |  |  |  |  |
| No | Project Name and Detail | Start Date | End Date | Total Value |
| 2 | Upgrading of Emsengeni Taxi Loop - Phase 2 | August 2021 | September 2022 | R 16 026 139.51 |
| 5 | Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo | April 2022 | February 2024 | R 24 337 418,58 |
| 1 | Construction of a New Community Hall in Moses Mabhida | January 2022 | October 2023 | R 23 105 195.89 |
| 7,5,4 | Refurbishment and Maintenance all Municipal Buildings | July 2022 | May 2023 | R 506 000.00 |
| 7 | Installation of Bulk and Domestic Water Meters in Kirkwood and surrounding areas | July 2022 | June 2023 | R 700 000.00 |
| 1 | Refurbishment of Kirkwood Wastewater Treatment Works | November 2022 | October 2023 | R 17 039 380,20 |
| 5 | Nomathamsanqa: Completion of Water Backlogs | November 2022 | June 2023 | R 2 960 619,80 |
| 4 | Zinyoka Electrification | June 2022 | August 2023 | R10 512 000 |

## APPENDIX G – RECOMMENDATIONS OF THE MUNICIPAL AUDIT COMMITTEE

## YEAR 0

| NO | ITEM | DISCUSSION | RESPONSIBLE PERSON |
| --- | --- | --- | --- |
|  | Opening and Welcome | - The meeting was officially opened by the Chairperson of the APRC,who welcomed everyone present. | Chairperson |
|  | Attendance and apologies | - SRVM Senior Management was in attendance except for the Director: Technical Services and Infrastructure, Mr. X Mntonintshi. | All |
|  | Confirmation of Agenda | - The chairperson suggested that the 9.1 report will be done as an in-committee item. Note that 10.5 is part of 8.1. - Michelle confirmed the agenda. - Tania commented that after 10.2, there is a space, and no report was received after the Internal audit planning. - The chairperson suggested it be attended during the meeting of 23 August when reviewing AFS and Annual Performance Report. - CAE confirmed Tania ’s comment, saying the report was included in the pack and the planning has been done for 2024/25 FY; however, there was a mistake of not including the report with the other reports. Suggested that the report be a third item in the special audit committee meeting that is to be held on the 23rd of August 2024. RESOLUTION - The agenda was confirmed and adopted. | All |
|  | Declaration of Interest & Fraud Incidence forms | - Nothing to declare from all members. | All |
|  | Confirmation of the Minutes of the previous meeting and signature by the Chairperson & updated Resolution Register 5.1 Confirmation of Minutes and Signature by the Chairperson | - The Chairperson said he could not go through the minutes, as he received them late. - However, he asked members who were able to review the minutes to kindly adopt them. - Michelle said there were changes she needed to check; she did not get the chance to. - Tania said she did not receive the updated minutes in her emails. - It was suggested the resolution register should be flighted and the minutes be reviewed for the following meeting. Resolutions - The Audit Committee suggested that the minutes be done separately for the in-committee meeting. | CAE |
|  | 5.2 Updated resolution register | a) “Have all prior meeting resolutions been resolved? Resolutions coming to ARC should indicate all previous meetings’ resolutions that have not yet been resolved. - CAE said all resolutions have been taken into account, this one only focuses on the previous meeting, dated 23 April 2024, and there are no matters arising. The register was submitted for adoption. - Ms. Tania Knoetze requested that a specific date should be stated where “next audit committee” is referenced for clarity purposes. CAE took note and accepted the advice. - CAE responded that the resolution register for in-committee meeting held on the 23rd of April 2024 is not included. - CAE said the MM will respond and elaborate more on the Audit Controller issue. - The director for Corporate Services confirmed that the ICT Governance framework had been drafted with SALGA assisting the Municipality. He said there was a follow-up meeting, one held virtually and the next meeting was physical and issued a draft report on parts that need improvement. - CAE said the Risk appetite policy needs to be presented to the management and reviewed, then submitted to the Council for approval. - CAE suggested that a paragraph of the Risk Appetite Policy should be included in the Risk Methodology rather than having another separate policy. - Tania and Michelle seconded the suggestion. b) - MIs were forwarded to the audit committee; MM elaborated: - Consultant’s feedback on performance has not been submitted yet; the CFO will divulge on the matter. - The matter is to be resolved on the e meeting held on 13 May 2024.The Audit Action plan was developed, but CAE is not sure how far the implementations are. The CFO will answer this matter. - Treasury reported that according to their web-enabled Audit Action Plan system, 62.6% are in progress, and 37.4% have not yet started. - CAE responded by saying that the Municipality has been using the system, and he can confirm that 122 COAFS were uploaded to the system. - Treasury responded by saying that everything uploaded on the system by the municipality is pulling through. They have spoken with employees who are using the system, and they are not facing any challenges. However, the office has availed itself to assist when there are challenges and provide training. - Updated figures were presented live from Treasury’s system on what the Municipality has used as Implementation Audit Action Plan: 55,7% Not yet started. 43,4% - in progress. 0,8% Completed. - Upon answering the Chairperson's questions, the Municipal Manager confirmed that there are only 4 Material Irregularities, the 5th one hasn’t come out yet. - “The debtors’ balance is not creditable: CFO to get assistance from SBDM.” The CFO responded by saying that no assistance was rendered whatsoever. - The Chairperson wanted clarity on the information that was incorrectly recorded in the Section 52 report. - The CFO said he will check on those errors however, he believes that the AFS and Section 52 issues are being resolved. - The chairperson wanted to know whether there’s been an update on the system for the final budget for 2024/25 free of errors. - CFO said yes, the update has taken place. - Issues with the VAT are being finalised and reconciled for the whole year. On the next version of the AFS, this will be included: - Interest in Bulk water is disclosed as fruitless and wasteful expenditure. - The chairperson requested the MPAC chair to take note of this. - The revenue recognition for grants that were being performed on an actual basis and not on payment due to system glitches has been corrected, said the CFO. - MM said he had a session with all members of the bid committees and the evaluation committee, and he added that there has been improvement, as the meetings have been sitting, and he is monitoring them. However, there have been challenges with the evaluation and BAC, the Municipal Manager said he asked the CFO to attend to challenges with SCM staff. - MM to resolve the issues between the Internal auditors and the Finance department. The Municipal Manager said he would intervene and report on the “no submission of reports”. - Mr. Tambo lost connection and couldn’t respond to the question on whether he was getting POEs on time, the CAE said they were received on time. Information for the Performance Management Unit is flowing smoothly. - MM confirmed that the draft adjusted budget was looked at and signed. Chairperson requested Director Kondile to submit quarterly performance reports. - The CFO confirmed that the Municipality’s tabled Annual budget for FY 2024/2025 was resolved. - Issues relating to the assessment of the segments for MSCOA were addressed. - CAE said he is satisfied with calculations at Payroll, he requested the payroll officer to be present in the meeting in case further follow-up questions arise regarding the accuracy of payroll calculations in terms of Job Evaluation. - The chairperson asked if “Remote access of the ICT Manager to the system due to R-data being in control of the institutions' financial system, has been resolved”. - Director Kondile said the issue had been managed, and ICT has access to the system, and they will be able to generate reports. He concluded that the unit has been trained by R-data. Resolution - The chairperson said that there are a lot of outstanding items, however the resolutions register 23 April 2024 have been noted. |  |
| 6. | Update by the Accounting Officer on the municipal overview quarter 4 | - The chairperson said he saw no mention of security concerns in the report, and he then asked the Municipal Manager for clarity. - Chairperson said Section 52d was tabled at the end of July and asked the Performance Management Policy to be sent to AC, saying they had the 1st Quarter review of FY 2023/24 and there were issues on the Performance Policy. - Michelle requested a full list of the register about fruitless and wasteful. - AC asked what the status of the prior outstanding performance reviews is, and from which year the reviews will be done. - The Municipal Manager said the security issue continues to be a challenge. - The Municipality has three types of security, e.g. Personal assets, Access security and personal security guards. - The MM said both security areas have been advertised in the hopes of cutting costs on irregular expenditure, and the current security services and gain cost-effective security services. He added by saying that he hopes the bidding committee processes will be up and running by October 2024. - The Municipal Manager said he should be able to report back to the next meeting about the outstanding matters regarding securities in the involvement of the Hawks. - SRVM Performance Management was reviewed, including the MM Performance, by his supervisor, the Mayor, however, there wasn’t enough time to evaluate everyone, - What is outstanding is to agree on a day with the chairperson to conclude the matter. - With regard to wasteful expenditure, MPAC has been re-energised and a support team for MPAC has been established. - Work has been concluded for 2021/22/23/24. They are scheduled for Monday. These recommendations are to be presented to the council. - Michelle questioned if progress was made in dealing with investigations to be brought about. - Tania questioned if the municipality requested SBDM for assistance. - MM said the municipality will engage with SBDM and manage the support. - The CFO also responded that the municipality is looking at approaching SBDM. - Michelle commented on the outstanding review and wanted to know why it dated back to 2014. is it even legal to do so? - MM said this process is legal, and the municipality will follow an approach of inviting the former management for reviews and see if they still have records - The Chairperson advised it to be closed if the former management is not available. He said the municipality has more pressing issues for now. - Treasury was asked by the chairperson to confirm whether the Financial Management Capability Maturity Modules were all completed. - MM responded by saying that the CFO is the audit controller, and the CAE is also included to assist. He concluded by saying that he prefers one audit controller to mitigate confusion. - The draft AFS was available the day before the meeting, and it was sent to AG and Treasury. IA mentioned that APR is also available since the day of the meeting, 16 August 2024. - Treasury confirmed that the municipality completed the FMCMM. They are waiting for National Treasury to do the final review and then confirm that the municipality is compliant for FY 2023/2024. Resolutions - The institutional overview report was noted. | MM |
| 7. | Finance Reports: 7.1 Report in terms of Section 52(d) Quarter 4 | - The CFO informed the meeting that the questions were not sent to him on time for preparation. - “Have the YTD actuals considered all accounts and all accruals at year-end? How different do the figures look compared to the AFS?” - “Please explain why capital expenditure was overspent by R6.3 million? What was this spent on, and how was it funded?” - The CFO said there will be changes towards the finalisation of AFS. “Indicates cash flow challenges” - Security services cost seems to be the biggest challenge the municipality has now. “What plans are being put in place to be able to meet all financial obligations? (especially regarding collecting the huge debtors’ amounts)” - The CFO said the Department is trying its best to manage the institutions' finances. “The Cash flow - Is this uncommitted?” - Yes, the capital cash flow is reflected. Why debtors for National and Provincial so high – what steps are put in place for collecting these? Residents and industry - what steps are put in place for collecting these? No incentive plan for residents? Councillors and staff - what steps are put in place for collecting these?” - Still needs to be addressed to the forum, post offices are not functioning for collection anymore. The municipality is utilising the sheriff for collection. - “What is the budgeted collection?”. - The CFO said the budget collection rate is 65%. The proposed amount with the collected amount is corresponding. - “Has the job Evaluation been completed?” - Mr Kondile responded by saying that there are 129 positions in the organogram, a total of 109 were submitted and evaluated, and upgrading positions have been implemented, so 85% is completed. “Overtime R611,190 – 17% over budget - why?” - The CFO said this is initiated by the services delivery departments, he deals with payments only. - Chairperson said 17% is a lot of money, and he asked if IA should convene and investigate this. - Mr Kondile said that it is unfortunate that from the HR point of view, they cannot give out the accurate/exact details on the matter since the payroll officer who was dealing with these payments is still on suspension. However, the task has been transferred to BTO. “Goods for sale – negative - why? Fines, penalties – 95% below budget – why? Licences and permits – 46% below budget – why? “ - Finance said these items will be finalised and reflected correctly in the AFS. There was a bit of a challenge in the Traffic Department. - PT wanted clarity on the Capital gain of Disposal Assets in the report. - Finance said they do not recall any disposal of Assets in this quarter; however, this will be looked into. “Why is the Traffic Department testing ground not operational? Is the salary cost under-stated? And if so by how much? What is the integrity of the S52d provided?” - CFO said if he recalls well, the Traffic Department had challenges with their testing grounds as well as the routes (streets). Challenges were looked into by the Department, and they have ensured that the testing ground is in good condition, they will soon be fully functional. - Salaries will also be corrected in the AFS. “Who is responsible for recording all manual fines? Please explain the process of doing this and how often it gets done.” - Fines are recorded on the system on an annual basis, and manual fines are captured on a quarterly basis. - AC requested SCM report, as they were not included in the report. - As a result of the adjustment proposed to the remuneration of councilors, AC commented that this doesn’t make sense in Q4 and when this is going to become functional. - CFO responded to the Chairperson regarding the negatives under Grant Utilisation. He said the negatives are savings from other projects. - An amount of + - R15 million was received from WSIG and was not captured in the report because the amount came in late. “There is a 94% over expenditure on Technical, and are these incorrect votes or what?” - CFO- This has been noted as a system error, and it will be corrected. “Are there no rollovers to confirm that you applied to National Treasury?” - The additional funds will result in the rollovers. “Can you tell how much it will be?”. - CFO – unfortunately, we cannot tell how much it will be. “AC some of the projects have no budget, where does the money come from? Grant expenditures are not recorded, who is responsible for the process of recording? Can this be corrected, what is the real issue - do you have sufficient capacity to manage these processes?” - CFO – they are all deposits. Issues of capturing are a combination of system error and staff shortage however; we always ensure that everything is properly recorded and corrected. - AC suggested that the management should have the system error issue looked into as it is time-consuming and costly. “Are you happy with the system, don’t you think it should be changed when it’s giving you problems continuously?” - The CFO said the system cannot be changed now; it will take quite a process to change it, and it may cause financial administration problems. “Is this ageing correct - R240 mill in current, correct? Interest- Nil?” - The CFO said the numbers can’t be correct. The total is correct, but the ageing is not. - AC questioned creditors - is the R50 mill included on the above-mentioned table? What is the status of the Department of Water and Sanitation? - CFO, yes, it is included. There is a scheduled meeting with the department to discuss this. “S&T own Transport noted - was additional level required during a period that was not planned for. Why is the excessive amount in actual? Why has the March journal not been included in the report? What is the status of overtime? If the journal is considered, which department has incurred the most overtime?” - The CFO agreed that it is concerning, and the MM has made a lot of effort to ensure that costs are reduced. He said he would ensure that the following report has records of departments’ overtime. Supply Chain outstanding. “Why is the CSD not functional?” At the time there was a system error due to network connection and this CSD system is the Treasury system the Municipality does not have full control over it. Resolution - Submit the final AFS draft before the following meeting (20th August 2024) - Provide details on overtime of departments in next report - AC noted the section 52d report with concerns. | CFO |
| 7.2 | Prior year issues, including material irregularity reporting, etc. | - CFO stated that 3 COAFS are progressing, 68 are completed, and 12 are not completed - The AG started to Finalise planning working papers that were not finalised in April and also issued RFI’s for SCM, they also started with the audit of SCM. - So far, they have received information that was recently issued in August except for RFI 26 which is related to HR. Management formally requested an extension, and it was granted until the 20th of August 2024. No further COAFs were issued except for the four (4) that have been issued. - Planning reviews are underway, and deficiencies that will be noted during the planning stage will be communicated. - The Municipal Manager mentioned 4 MIs that were issued, 2 were for the landfill sites. AG has assessed the accounting officer’s response in taking appropriate actions. They will then follow up on actions. 2 MIs that are related to lack of records for Financial and Performance information have been escalated. The assessment information was that appropriate actions were not taken to fully resolve the MIs. - AC wanted clarification on the Utilisation of the fleet at landfill sites. - Director Mbongwe reported that they have advertised for service providers, but local SMMEs said the municipality cannot give out jobs of this magnitude to outside SMMEs. The Department submitted applications for assistance to the Department of Economics and Environment specifically, but they didn’t receive funding. - AC asked about the amount of costs spent on machinery and requested that the municipality rather focus on buying their own TLB for cost containment. - Director Kondile to report on records management developments. He said that key projects to improve records management have been identified by SALGA and they are working on it. RESOLUTIONS - Look at ways to cut costs in terms of infrastructure assets. - Develop an Implementation plan with a timeline and budget so that we can track costs accordingly. - Community Services to report on a quarterly basis on their fleet expenditure. - To wait on SALGA to report on their progress with records management. |  |
| 8. | Institutional Performance Report Quarter 4 | “MM was not assessed?” - All SRVM Senior managers were assessed, the scores have been documented. We couldn’t get a hold of the accounting officer due to a bereavement. The comment needs to change to not yet completed. - CAE said there’s no portfolio of evidence for 2023/24, so we cannot say it was achieved hence we reduced the numbers. - Mr. Tambo lost connection, further clarifications are to be reported by him. - The Performance Officer, monitored by the accounting officer, is responsible for making sure that all performance agreements are signed, they were indeed signed. RESOLUTION - CAE needs to go back and look at the smartness of the Targets. - Performance management framework/policy must be updated and specify who constitutes the panels of each section 56 managers. - CAE to find out whether AAP and material irregularities are included in the performance agreement for the current financial year 2024/2025. - . | CAE presented on behalf of the PMS Officer |
| 9. | Corporate Services Reports 9.1 Litigation register | The litigation register will be looked at in the in-committee meeting. The litigation register report was noted. | Director Corporate Services |
| 10. | Reports by Internal Audit 10.1 Report on Audit Action Plan | “This is as of the 30th of June - what is the status now?” - The municipality has 122 audit findings that were fully populated in the system, the action plans the municipality is using lacking detailed information. - The updated audit action plan will be submitted in the following meeting. This report is not an updated one. - AC proposed to wait for a proper report. RESOLUTIONS - Identify what is affecting the Audit report and focus on high-risk matters. |  |
| 10.2 | 10.2 Risk Assessment Results 2024/2025 10.2.2 Internal Audit Planning 2024/2025 | “Only done Strategic Risks” - Due to the time when Treasury assisted in facilitation, there haven’t been discussions about the conclusion of quarter 4 of this year. RECOMMENDATIONS - The plan needs to include other sections. - AC recommended that CAE add the comments that are on the report in the following meeting as matters arising. Specifically on the cover page. | CAE |
| 10.3 | Report on Revenue Management 2023/24 | - Formalised all the issues CAE has with certain departments and have them resolved outside the meeting. |  |
| 10.4 | Report on SCM management 2023/24 | - AC awaiting SCM Comments. |  |
| 10.5 | IA report on PMS Quarter 4 | This will be reported in the Special meeting. |  |
| 10.6 | Report on IA plan | - The payroll case is still ongoing; there is only 1 employee that has not been interviewed. The final report will be submitted once the case is closed. - ICT audit is delayed by the procurement processes, and the adjudication committee has not yet sat to appoint. - AC suggested IA wait for the report from SALGA and look at it and put the new service provider on hold until later in the year. |  |
| 11. | General | RESOLUTIONS - AC suggested that there be a Special AC meeting. - The following meeting date was communicated and agreed upon. |  |
| 12. | Date of Next meeting | - Special Audit, Performance and Risk Committee meeting to be held on the 23rd of August 2024. |  |
| 13. | Closure | The meeting was adjourned at 14:39 |  |
| NO | ITEM | DISCUSSION | RESPONSIBLE PERSON |
|  | Opening and Welcome | The meeting was officially opened by the Chairperson who welcomed attendees to the first meeting of the 2024-2025 Audit Performance and Risk Committee. | Chairperson |
|  | Attendance and apologies | The presence of key members was confirmed, noting only one apology received from Ms Magadaza from AGSA. The CFO joined the meeting shortly after confirmation of attendance. | All |
|  | Confirmation of Agenda | The agenda was established focusing on audit outcomes and recent fraud incidents, including a conviction related to corruption and ongoing investigations into past fraudulent payments. The agenda was then confirmed by the APRC members. | All |
|  | Declaration of Interest & Fraud Incidence forms | There were no interests declared in the meeting and no fraud incidents were noted. Councillor Smith highlighted a recent court ruling against a municipal official for corruption, prompting a discussion on the matter. The Municipal Manager provided context, explaining that the fraud incident involved the sale of licenses and that the convicted employee would be suspended. He also mentioned ongoing investigations into another fraudulent payment related to a service provider. During the meeting, the Mayor expressed frustration over the municipality's ongoing issues with disclaimers of opinion, questioning the skills and effectiveness of the Audit Committee. He emphasized the need for a physical meeting to address ongoing issues, particularly the repeated disclaimer of opinion. The Chairperson and other members acknowledged the mayor's concerns, highlighting the importance of addressing root causes such as skill shortages and management collaboration to improve audit outcomes. The discussion also touched on the challenges faced by the municipality, including the failure of West Rand Consulting to meet performance expectations, which has contributed to ongoing financial difficulties. The Audit Committee Members responded to the question of effectiveness of the Audit Committee as follows: - Mrs. Wait clarified the role of the Committee which is doing oversight and recommendations to Council. She emphasised the importance of management's implementation of audit recommendations. - Mrs. Knoetze highlighted the need to identify the root causes of non-implementation. - The Chairperson also responded that all inputs of members at the AFS and AC meetings were communicated in writing and emailed to the CAE and copied to MM and CFO. The AFS submissions were also reviewed by stakeholders such as the Provincial Treasury. All reviews relating to the face of the AFS could not be confirmed by IA during the last review of the AFS by the AC. The AC reported as such to the Council. The Municipal Manager reported on ongoing investigations by the Hawks and SIU regarding irregular appointments and a fraudulent payment of R1.3 million related to WRCON, highlighting the need for improved implementation of the audit action plan to address repetitive findings and consequence management failures. He emphasised the urgency of filling critical vacant positions to prevent service delivery issues and mentioned the appointment of an independent consulting company to assist with audit outcomes, while also addressing the need for comprehensive reporting from previous consultants. The Municipal Manager has committed to the following Action Items: - To meet with the Director of Corporate Services and the Director of Community Services to discuss the implementation of actions regarding the convicted employee. - To implement the suspension of the convicted employee today. | All |
|  | Minutes of previous Meeting & updated Resolution Register. - Confirmation of the Minutes and signature by the Chairperson | - Minutes and Resolutions from the meeting of 16 August 2024 will be discussed in an ordinary Audit, Performance and Risk Committee meeting. | CAE |
| 5. | Update by Accounting Officer on the Municipal Overview Quarter 2 | The Municipal Manager tabled his overview report stating or highlighting the following: The purpose of the report is to provide an overview of the state of governance and service delivery at Sunday’s River Valley Municipality. It also seeks to highlight various challenges in the SRVM Administration and how those challenges impact the ability of the municipality to discharge its statutory and constitutional responsibilities. The SRVM has once again received a Disclaimer Audit Opinion from the AGSA. This against the backdrop of Westrand Consulting who were appointed on a three (3) year contract with the sole purpose of turning around the municipality to improve its audit outcomes. This also against drastic cost escalations and the Irregular Expenditure this transaction has brought to bear the municipality’s financial challenges the municipality is facing today. Westrand Consulting has failed in all the performance scorecards it was meant to achieve when they were appointed and these are i.e. development of credible Annual Financial Statements (AFS) and an Asset Register (AR ) and thus improving audit outcomes , the second failed performance score card is Transfer of Skills. The contract between the municipality and the WRCON came to an end on 30 November 2024. They have indicated verbally that they want to work “ free of charge “ this year but the MM was yet to receive a formal correspondence and the legal basis in this regard. It would be interesting to understand their thinking in this regard after a three-year dismal performance. But I must hasten to say taking into account their dismal failure I am not interested to their “free lunch”. Theirs at the moment is a ‘crime scene‘ as both Hawks and SIU are currently busy investigating and conducting interviews on their irregular appointment including escalating costs. Also under investigation is the 2021 alleged fraudulent payment of R1.3 million to WRCON which was later partially re-paid to the municipal account and the rest was not yet accounted. The Audit Committee Resolved that: - Audit Committee noted the overview report for Quarter 2. - The investigation into the contract of Consultants should be expedited, and the results of the investigation be tabled in the next APRC meeting. | MM |
| 6. | 6.1 Finance Reports: Report in terms of Section 52(d): Q1 Quarter 2 REPORT ON SCM: Quarter 1 Quarter 2 | The CFO presented the S52(d) Q1 report to the meeting Comments and queries of the Audit Committee members: Debt (R289,3m in Q1) Staff and Councilor debts are being managed internally. There is a challenge that the municipality does not have punitive measures to assist with debt collection (e.g. electricity cutting). The Audit Committee wants a comprehensive debt collection plan with priorities and timelines as these funds could be better utilised, for example payments to creditors (R80m) and avoiding interest payments to creditors. Interest of debtors is indicated as nil with no explanation; The CFO has committed to correct this. The current funded budget is based on a collection rate of 75%. The CFO tabled the S52(d) Q1 report to the meeting and the report was noted by the Audit Committee. OVERTIME: The Committee is not happy with a monthly advance in pre-authorisation of overtime. Overtime needs to be divided into “stand by” and “overtime”. The Community Services Councilor stated that overtime in their department was reduced from three days (3) to one day. Questions were raised regarding the productivity of staff and the Director of Technical Services stated that they may review work schedules. Generally, the credibility of the S52d (Q2) was questioned as figures did not agree, for example, cash flows, debtors and the surplus reflected in the reports. Cash flow is reflected as a negative in the Q2 report. Capital projects are doing well, although there is a delay in some projects. Electricity had a negative (R67 000) for December 2024, which the CFO stated would be corrected in January 2025. Debtors increased from R289,3m (in Q1) to R295m, hence the recommendation of a comprehensive debt collection plan with priorities and timelines of Q1 is still valid. Negative values in the debtor’s age analysis are a concern for the Committee. Fines and penalties are 97% below the target. The Audit Committee resolved that: - Overtime be divided into “standby” allowances and overtime, which should only be authorised when required. - The Committee supports an adjustment budget requested by management. - Management should engage with the Department of Water & Sanitation (the highest creditor) to find common ground. The Chief Financial Officer tabled the report for Q2 at the AC meeting. This is the first time the CFO has tabled an SCM report to the Committee. Deviations for Q1 amount to R1.66m; the main contributor was chemical purchases. The SCM process is underway to correctly source a service provider. Irregular Expenditure for Q1 amounts to R13.2m (the main contributor is security costs). The Chief Financial Officer was requested to distinguish between legacy (old Irregular Expenditure and new Irregular Expenditure) in reports going forward. Fruitless and Wasteful expenditure for Q1 amounts to R6.5m. The Chief Financial Officer tabled the SCM report for Q2 at the AC meeting. The Chief Financial Officer has cited challenges with regard to bid specifications that would affect the evaluations of tenders. Also, achieving a quorum was cited as a challenge. Deviations for Q2 amount to R2.1m (Q1 - R1.66m), with the main contributor being chemical purchases. The SCM process is underway to correctly source a service provider. Irregular Expenditure for Q2 amounts to R12.4m (Q1 -R13.2m) (the main contributor is security costs). The CFO was requested to distinguish between legacy (old Irregular Expenditure and new Irregular Expenditure) in reports going forward. Unauthorised Expenditure for amounts to R17 236.58. Fruitless and Wasteful expenditure for Q2 amounts to R367 271.47 (Q1 - R6.5m). The Committee noted a disagreement in the amount disclosed for Q2 as R1.1m was disclosed of interest to creditors. The Chief Financial Officer indicated that Unauthorised expenditure will be regularised through an adjustment budget. He further advised that a contract management clerk was appointed which will improve the contract management and register. The process of installing a bulk electricity meter to take own readings on Eskom consumption has started. The Audit Committee Resolved that: - The SCM report for Q1 & Q2 2024/2025 be noted. - The Municipal Manager intervenes regarding the procurement challenges and human resource challenges. - MPAC to investigate the Irregular Expenditure and Fruitless and Wasteful expenditure. | CFO |
| 6.2 | Draft Audit Action Plan 2024/2025 and an update on the material irregularity MATERIAL IRREGULARITY (MI) | The Chief Audit Executive presented the Draft Audit Action Plan and mentioned that: The municipality received 122 COAFs in the previous FY 2022/2023 that were fully populated in the automated system and the current year 2023/2024 received 102 COAFs. The challenges identified in the current automated system were escalated to Provincial Treasury for intervention. Mr. Galada from Cogta discussed the dual reporting on the Audit Action Plan, highlighting the need for Municipal Public Accounts Committees to oversee the process effectively and report to Council. The Chairperson informed the meeting that the incomplete document was submitted very late to the Committee members thus they could not review it. The Municipal Manager committed to the following Action Item: - To present the draft audit action plan for 2025 in the next meeting. Mrs. Gillian Hammond from Treasury committed to ensuring the municipality incorporates the web-enabled audit action plan into their action plan for Equitable Share compliance. The Mayor raised concerns about the lack of a report from consultants whose contracts had ended, stressing the importance of documentation for future reference. The Meeting confirmed that all documentation regarding the work done by West Rand Consulting was submitted to the municipality and a final report was done. The Audit Committee Resolved that: The Draft Audit Action Plan was noted as an incomplete document by the Audit and Risk Committee. The meeting concluded with discussions on the importance of dual reporting on the audit action plan and ensuring that the council receives adequate oversight and accountability. Four (4) Material Irregularities were issued: Two (2) for the landfill sites. Director Community Services reported that they have advertised for service providers for the landfill sites, but local SMMEs said the municipality cannot give a job of this magnitude to outside SMMEs. Funding was a challenge: Amounts mentioned verbally were Fencing (R700 000), Weighbridge (R560 000), a Service Provider (R2.5m), Security (R1.5m) and the cost of the internal road could not be determined at this stage. The Committee required clarification on the Utilisation of the fleet at landfill sites. Also questioned the amount of costs spent on machinery and requested that the municipality rather focus on buying its own TLB for cost containment. The Audit and Risk Committee noted that there has been no movement regarding the MIs since the AG issued its Audit Report. The Municipal Manager proposed a budget alignment within the adjustments budget and the fast-tracking of the appointment of the Strategic Manager. The other two (2) Material Irregularities relate to a lack of records for Financial and Performance information. The Chairperson highlighted difficulties in the audit process, particularly regarding record keeping and the verification of data. He pointed out specific issues, such as the lack of independent measurement for bulk utilities and concerns about a ghost employee. The discussion also included the need for a physical meeting to address these challenges and ensure accountability moving forward. The Municipal Manager has committed to the following Action Items: - To ensure that a full 100% employee verification is undertaken and concluded by not later than April 2025. To appoint an independent human resource consulting company to undertake the employee verification exercise and report to Council | CFO |
| 7 | Performance Management | IDP/PMS |  |
| 7.1 | Institutional Performance Information Quarter 1, 2 and Midterm reports | The Audit Committee Resolved that: Directors are to submit evidence stipulated in the SDBIP and report the actual performance/implementation. Directors are to provide reasons for deviation and corrective action for non-performance with timelines. Directors are requested to review submitted evidence for Q1 and Q2 and submit it in lieu of year-end targets. | MM |
| 7.2 | Draft Annual Report 2023/24 FY (for noting by AC, IA will report in Feb 2025) | The Chairperson highlighted that a high-level review was done by the Audit Committee on the Draft Annual Report. Auditor General Report not included. The Committee highlighted the following: - Internal Audit has not yet reviewed the annual report. Awaiting Internal Audit's detailed review of the February 2025 AC meeting. - Does not seem complete – Management should indicate to various individuals what is outstanding and what the deadlines are. - In appendix G: address each specific item separately and no management response is reported. - Submit a copy to AG to review as part of public participation and implement their inputs. The Audit Committee Resolved that: - Internal Audit reviews the draft annual report during the public participation phase and report to MPAC. - Submit a copy to AG to review as part of public participation and implement their inputs. | CAE/ CFO |
| 8 | Internal Audit reports |  |  |
| 8.1 | IA report on institutional performance quarter 1 and 2 2024/25 | The Chief Audit Executive in his brief report mentioned the following: The audited institutional performance for Q1 is 47% and Q2 is 37% The audited institutional performance for the mid-year period is 42%. The reasons for the underperformance are inadequate supporting evidence submitted to support the reported targets. The annual report was submitted to the Committee without being reviewed by Internal Audit. The reasons for non-reviewal: No information was submitted to the internal audit for review; and Late submission of information to the performance management unit by departments. The Audit Committee Resolved that: Directors are to submit evidence stipulated in the SDBIP and report on the actual performance/ implementation Directors are to provide reasons for deviation and corrective action for non-performance with timelines. Directors are requested to review submitted evidence for Q1 and Q2 and submit it in lieu of year end targets. |  |
|  | Corporate Services Reports | No reports submitted |  |
| 9 | General | The Audit Committee has asked the municipality to consider using a Microsoft programme called “SharePoint” where multiple users review documents simultaneously. This will enhance efficiencies in reviewing audit committee packs. Management will then also be able to capture their responses to the documents where relevant. It should not have any additional costs to the municipality as this is part of the Microsoft package, but the municipality should confirm the cost. |  |
| 10 | Date of Next meeting | 17 February 2025 |  |
| 11 | Closure | The meeting adjourned. |  |
| NO | ITEM | DISCUSSION | RESPONSIBLE PERSON |
|  | Opening and Welcome | - Meeting was officially opened by the Ms. Wait; she welcomed everyone present. | Chairperson |
|  | Attendance and apologies | - All SRVM Senior Management are in attendance except for The Hon. Mayor Cllr Lucas. - MM said there is no apology from AG, nonetheless he had a hand over meeting with AG, it was confirmed that there will be a rotation, a new manager will be assigned to the Valley for audits, and a new SM will be introduced to us in due course. - Miss Knoetze asked if a consistent person will be assigned to a manager’s level. - MM said there will be a consistency, however the senior manager that has been assigned for the Municipality is being represented. - The meeting welcomed a new service provider named Abacwaningi Business Solutions they were appointed by SALGA to assist the municipality in turning around the audit outcomes. - The team told the committee about their services, which includes improvement of internal controls, assets management, and the resolution of UFW expenditure. | All |
|  | Confirmation of Agenda | RESOLUTION - The agenda was confirmed | All |
|  | Declaration of Interest & Fraud Incidence forms | - Nothing to declare from all members. - Cllr Smith draw attention to the fraud incident that happened at the Traffic department, saying she was unsure if administration sent a report regarding the outcomes or not. - The chairperson responded by saying that the matter was discussed at the previous meeting the committee had, and the report should be documented in the previous minutes. - It was then concluded that the were no new fraudulent incidents. - The chairperson recommended a solution for internal audits to reduce the number of reports they send; last week’s emails contained different attachments and versions. He suggested the municipality to obtain a license for SharePoint. | All |
|  | Confirmation of the Minutes of previous meeting and signature by the Chairperson & updated Resolution Register 4.1 Confirmation Minutes held on 16 August 2024 and signature by the Chairperson 4.2 Confirmation Minutes held on 20 January 2025 and signature by the Chairperson 4.3 Updated resolution registers | - The chairperson said that minutes of the meeting held on the 16 of August 2024 do not have page numbers, the formatting is not right. - Contradiction was spotted on page 2. - Ms. Knoetze read through page 2, on the 5th point of Confirmation of Agenda, she requested we change the wording to “The CAE said the report was included in the pack, and planning has been done for 2024/2025, however there was a mistake of not including the report on the email, when the agenda was sent.” - On page 3, point 4 was confirmed that the previous minutes mentioned are of the meeting that was held on the 23rd of April 2024. - The chairperson mentioned that he never reviewed those minutes, he only reviewed the resolutions register. - He also added that the meeting had mentioned risk appetite to CIA, and it was suggested that it should be in one policy, rather than having different policies and it has gone to council for approval. - The chairperson felt like the members questions on page 12 were copied and pasted. - In conclusion the chairperson said the minutes are technically correct, but it doesn’t have a completed scenario. - Mr. Nkuntayi responded by saying that he assigned the IA to assist with minutes because SRVM committee clerks may not understand the terminology that is being used in the meeting. - The chairperson mention that on page 13, the 70% over budget with regards to overtime should be investigated by Internal Audit, not AG. Recommendation - It was recommended by the Chairperson that the minutes be reviewed and re submitted, Ms. Wait supported the proposal, seconded by Ms. Knoetze. - CAE committed to have the minutes send by the second week of March. - It was suggested that there should be an indication as to where a person comes from on the list of attendees, e.g. Abacwaningi Business Solutions. And there is information/ detail missing on the list (which was not discussed). - On page 3 Ms. Knoetze said the scenario was completed. However, information was added in purple writing. Recommendation - The minutes for the 20th of January 2025 were confirmed, MS Knoetze supported, seconded by MS Wait. - Asked for the resolution register dated 23rd April, because some of them are in complete. - MS Knoetze asked if resolutions from all meetings were resolved. - CIA replied by saying that according to his knowledge, minutes of the 16th of August and those of the 20th of January were not resolved. - CIA mention that there are resolutions from April that have not yet been resolved e.g. WRCON is still under investigation, he said that there was also an issue with payroll, the chairperson from disciplinary board has not yet attended council meeting. - The Chairperson suggested a list that’ll stipulate actions from those that had already been done, and what is left. he also mentioned that points 6, 6.2 and 7.1 be taken from the register. - MS Knoetze and Ms. Wait suggested that the register should be edited whenever there is progress on the register. - CIA supported the proposal. - The chairperson suggested again that we keep 6.2 and then perhaps ask SBDM if they can’t assist. - 7.1 should be listed as completed. - MS Knoetze complained that 7.4 in the prior issues has been unresolved for a while now, which is a concern. - 10.2 is outstanding, CIA said is these items still need to go to council for adoption - MS Wait mentioned that on 10.5 the date should be changed from June 2023 to June 2024 - CIA replied by saying that 2023 is correct. - Reference to the minutes of the 16 of August 2024. MS Wait wanted clarity about the incomplete comment on AC special meeting notes, CIA said he would have to go back to the reports to answer the question as he couldn’t recall. RESOLUTIONS - It was resolved the documented information should be shared on Excell spreadsheet, included changes that were made during the meeting. - Combine the resolution register and send it through for review so that it can be approved as an up-to-date register with the changes. - After the meeting concluded on the resolution register Cllr Smith suggested to the committee that the next audit committee try to meet in person. This comes after experiencing signal issues. The Hon. Mayor, Cllr Lucas also raised this suggestion on the previous audit committee meeting. - The Chairperson agreed. |  |
| 5. | Finance Reports: 5.1 Draft report on Adjustment budget | - The CIA flighted an email that was sent by the CFO to the Municipal Manager explaining why the department failed to work on a complete adjustment budget. The email contained details such as the struggle with the Internet, a severe storm that took place in the valley which affected all financial systems Rdata. - The Chairperson requested the CFO to raise his issues in terms of the adjustment budget he reported not to be ready yet. - The Chief Financial Officer said they are experiencing challenges with schedules that must accompany the adjustment budget e.g. the cash flow. He said his personnel and the service provider are working on it. - He said they are working on distributing it to council on Monday, he added that this issue was also raised by the Audit committee on the C schedules with the section 52 in the previous meeting and he didn’t want to submit schedules that are not 100%. - Ms. Knoetze asked when can the adjusted budget be expected. Ms. Wait wanted to know who will be checking the changes made in the adjusted budget. - The CFO replied by saying that the correct Adjustment budget document should be expected by council on Monday Morning. He added that they are also ensuring that it is in line with the SDBIP. Resolution - The report was not submitted | CFO |
| 6. | Final report on Audit Action Plan 2024/25 | - The chairperson asked the CIA to clarify about the incomplete scenario in 5.2 on the ordered action plan where two departments didn’t submit for full on details. - The CIA replied by saying that they have competed to develop the motivation plan, and the action plan was uploaded on the Treasury system for implementation. - He then suggested that Mr. Thomas from Abacwaningi to briefly give them to the progress of the report. - Councilor Smith raised her hand, she wanted to know why this document was not submitted, she addressed her frustration with the lack of information and failure to submit the necessary documents to the committee, she added by saying that the meeting was postponed due to late submissions. She also mentioned that the Audit Committee is there to assess the oversight and advice, she suggested the meeting should move on to the next item. She concluded by saying that someone needs to be held accountable for not submitting to the committee. - The chairperson asked if will they get feedback from the management as to what transpire, why they didn’t get submissions? - Mr. Nkuntayi, the Chief InternalAuditor,r said he didn’t want to speak on behalf of the management. However, he did say that the plan is completed and uploaded onto the system, implementation is needed. - Ms. Knoetze confirmed that this is a repetition, it also happened with AG where they don’t get needed information. She added by saying that if this continues it will be hard for the municipality to get out of a dark hole, this matter needs to be escalated to council. - The MM explained that the audit action plan was approved 3 weeks ago, he mentioned that corporate services were not included in the plan because the director joined the municipality late, they commenced in January the other departments commenced in February (Finance). - He added that the reporting of the audit outcomes of the audit action plan will now go through the steering committee. The Council was updated; the first steering committee was set for the 21st of February 2025. Aligning the dates is needed. - The chairperson wanted to know how they’ll be able to give oversight, do they wait on the steering committee’s input or? - The MM said the minutes of the steering committee will be available in council. - The Audit committee is concerned that they will not be able to perform their oversight - The CIA said the progress report of the action plan will be submitted to the committee after it’s adopted by the council PT - Ms. Budaza flighted the assessment for 2024/2025, she reported that 10 modules should have been assessed in the 2024/25 fy, only capacity building, internal audit and risk management were assessed, and they have been audited by internal auditors, IA should be able to submit by now. - In the report she opened the second time, she reported on the two modules that have been assessed between July 2024 and February 2025 she added that bank investment and compensation are outstanding. - She reported that the first three bank compensation and capacity building on page 2 should have been assessed in July, and in August. There should’ve been a reassessment of the Annual Financial Statement in September and December. - She also included that National Treasury is enforcing municipalities to use these systems to assist the implementation of FM, CMM. - Ms. Budaza also explained how the system works, saying the system asks you questions that require a yes, no, partial or not applicable. For all the nose and not applicable there is an action plan that the system generates. - The MM agreed that this system was discussed with the management last year. - The CFO said that within 2 weeks, BTO will ensure that everything is up to date. - He also mentions that the only reason why the implementation is delayed is that FMC has a lot of work, however E monitoring has been covered. - Director reported that ICT completed only one module out of several modules, he committed to monitor the completion of these modules. - CIA asked that the FMCM modules must not be assessed at the last moment, they should be given time to verify RESOLUTIONS - The committee took of the reports | PT |
| 7 | Performance Management 7.1 Draft Adjustment SDBIP 2024/25 7.1.1 Adjusted revised or amended information on SDBIP 2024-2025 | - Mr. Tambo reported that he faced a challenge with Annual report, he couldn’t answer some of the questions based on outstanding information from the MPAC committee. - The chairperson had a few questions to ask, which were answered by Ms. Budaza: She said not all questions need to be answered in one go. However, you answered the questions asked then you submit supporting documentation. - One can answer and save them, then go back again. - Ms. Budaza said they request to be given a slot to present on the status of their web. - Ms. Knoetze suggested internal auditors to be given time to review. Resolutions - The meeting noted the report. - Personnel to manage their time by completing their work, if it is 15 minutes, take time to finish it. - Ms. Wait, Ms. Knoetze and the chairperson, read out their comments. - The MM said he’ll comment on the overall framework of amendments to the SDBIP, he explained that when there have been changes in the environment whether it’s a result of regulatory or any other reason or any other reason you take into account mid-year , so that is the framework within which amendments are, at every time. During the course of implementation there are adverse findings, either by interna audit or by the Audit committee or by AG. If there was an anticipation of no funding, but there is a service delivery budget and implementation plan, but if there is no budget then it is removed. He added that these are considerations the management takes into consideration so there could be an internal audit finding that would be done to prove alignment. He also mentioned that one cannot change their indicators during midterm. - Director Mntonintshi reported that the reservoir is situated far away from the informal settlements, and they calculated according to distance when they did the business plan. However, when the construction started, they identified pipelines that are not far away from Moly Blackburn. - The director said they reiterated the resources of that one-kilometer pipeline into the household’s connection in terms of the sewer in Nomathamsanqa in Noluthando where they identified that they would connect to 15 households with the Park. He then clarified that the pipeline is 300 meters closer to the informal settlements. - He also added that they don’t have a budget for the project. EPWP is also based on the target of work opportunities that might be created, but it’ll depend on the amount of resources they have, - The chairperson asked how much the project is willing to change the 50 job opportunities - The director replied by saying that they are only allowed to employ 50 EPWP employees by the end of the financial year. - Mr. Tambo asked the meeting to look at the column regarding EPWP, he said changes were made based on findings of internal audit reviews. Key performance indicator is not aligned with the annual target in terms of the report. - Cllr Smith asked why the KPIs target and the Annual target adjusted, the was a R700 000 rent plus minus for EPWPs for the financial year, she said if the municipality does well there is a possibility that it would go up to R1.4 million. - Ms. Wait said she would like to confirm if the changes are in line with the SDBIP. She then said she thinks that there is another column missing that shows the adjustment budget, the needs ghto be a cash flow because, she concluded that if the department reduce the 1.3 kilometer to 300 meters, then the municipality will have a huge saving. Recommendation It was recommended that this document includes the two budgets, one with the previous, then the other one with changes. IA to go and revise the document | IDP/ PMS |
|  | 7.2 Final Draft on Annual Report 2023/2024/ | - The CIA flighted a check list with previous comments made by the Chairperson and Auditor General when they were overviewing the annual report. - The check list is a simplified method of correcting previous mistakes and a to do list on outstanding information. CIA said the final version of the annual report will be submitted to council with all the necessary annexures. Dates were also corrected. - What is outstanding at this point? Asked the chairperson - Mr. Tambo said the annual report was advertised for public comments and it is on the municipal website. MPAC is to do their oversight, thereafter it will go to council for adoption. - It was also confirmed that deliveries of the report to libraries were made. RESOLUTION - . - The audit committee would like to have a look at the AC recommendations that were included in the Annual Report . - The meeting also noted the Final draft report if is in the completion stages or it has gone to the public for review? |  |
| 8. | Internal Audits Report 8.1 Update on risk management Quarter 1 and 2 | - The chairperson complained about the risk management document; he said the document doesn’t show that work has been done. - The CIA said the municipality is regressing in terms of the risk management because they are only done at the beginning of the financial year, there is no implementation. He suggested that a different approach be used. - He added that instead of receiving POEs he’ll only get comments. He mentioned that there are four internal audit interns that are coming to SRVM, and he will assign them specifically to deal with risk management component in the municipality, he concluded that he cannot wait for the support plan from COGTA. - Ms. Boya from COGTA shared her sentiments on the risk management aspect, that there’s an inverse relationship between risk management and performance, if the municipality is able to handle the risk management well, the performance will be optimal, she also mentioned that it is a municipal culture where all risk management is treated as a compliance issue rather than a governance priority. She concluded by saying that someone must cater for risk Management, however it needs someone who has the previous circuit and requirements to withhold the office’s stuff. - The Municipal Manager said that he is in full agreement with the CIA and COGTA. He also mentioned that the Strat Manager post has been advertised, and the closing date is the 3rd/4th of March 2025. - It was clarified to Ms. Boyer that risk management function reports to the MM. RESOLUTION - The meeting took note of the report | IA |
|  | 8.2 Report ICT audit 2023/2024/2025 | - The chairperson asked the MM if it’s possible to cover everything that needs to be covered knowing that he has a backlog of other things to cover. - The MM said the chairperson should also take into consideration the resource constrain environment they are working on; however, they are committed to ensuring that they are fully effective in some areas. - The chairperson said the findings on ICT report are very concerning, and it covers a period of 3 years, there are a lot of question marks. He mentioned that some of the management comments are thin, and the implementation doesn’t seem to cover all the risks in terms of the review. - He also asked if the timelines were realistic, are they planned actions viable? - What is your current capacity within the ICT department, do you have the manpower hands on deck to unable the implementation, asked Ms. Wait. - Ms. Knoetze said she is glad the report was finally done, but the audit raises concerns, she asked the management how much of the ICT function is done in house and how much is much is being outsourced by service providers like Rdata can the management access these systems and how long is the service providers contract period? Can the management provide the meeting with a matrix of all IT-related services. - CIA replied and said he does have a team to assist with internal audit, the director for Corporate Services will answer in terms of staffing, service providers have access to Rdata, and the CFO was requested to invite them, he said on contract level, he has no idea. - Chairperson asked the service provider if they believe that the action plans would deal with the root causes - Ms. Wait requested for the author’s detail to be documented in the report compiled by the service provider. - Ms. Mbandla from Lunika said they do believe that action plans were correctly identified, because there is a system on Active Directory, that system is outdated and managed. She said they planned on sending a memo SCM to update the system and have compliance with the recent policies that are in place as well as the updated infrastructure. And the outdated Active Directory system, policies were reviewed and identified. She concluded by saying that workshops will be done 25 of March – 31st of March 2025 - Director Kondile replied in terms of the SharePoint issue, he said that it is a feature in our Microsoft 365 package. The challenges are that some employees are not familiar with the system, so they can’t utilize it, employees will be schooled. - He also mentioned that the department doesn’t have enough staff, they have a systems administrator and 3 technicians , they don’t have a help desk officer who will deal with ICT relation queries. - Most of the ICT projects have been identified but they are not executed, so they are packed and stored to be attended later and there is no position available in the organogram for ICT. - Director Kondile said that the service providers that are giving ICT related support, the issue of the access by the staff at ICT continues to be a problem and the biggest challenge because they cannot generate and monitor the system. If they don't have access. They’re also not able to generate reports to see if the ICT system is working optimally without having that access. - The director said he’s happy about the internal audit assessment that has been done by Luniko. - He also thanked the CIA for saying that they managed to get some of the information that they have made findings against them. - He mentioned that the department does have external service providers that are assisting them. For example, ICT choice is giving them services with the backup system, the cloud backup systems, the have an SLA in place and that contract is active, they also have a telephone management system which is also rendered by a different service provider. - On the issue of policies. He said they can’t tackle all services if they don't have a policy governance framework. They have a total of 12 ICT policies developed on a register; they need to be reviewed. - They are approved and ready for implementation and lastly on the ICT. They have also solicited the assistance technical assistance from SALGA through the mass programme where SALGA conducted the proof, level assessment tool. - They have given the department a draft report that pinpointed some challenges in terms of the maturity level as a municipality. - He concluded by saying that he is happy because the department has a committee that was enhanced by the inclusion of the directors. At the last meeting they had 100% attendance 100% by all the directors. And it will assist in terms of enhancing the capacity and the decision making in terms of the ICT. - Ms. Wait mentioned again that reports should have its author listed. - The chairperson wanted to know if someone wants to completely wipe out all the municipal data. Will it be like burning down this municipality again. And does the municipality have the ability to recover from this - He asked if money is going to be an issue, then, or later? - He asked the External auditors that have done this evaluation what would be the next step in terms of the evaluation. - Ms. Knoetze told the meeting that it needs to look ahead and take action now to prevent such a risk from occurring, where data loss might take place. - Ms. Mabandla replied to the comments and said they would like findings to be presented in an issue tracker. So, an internal audit action plan where the findings will be listed as well as the target dates, and a follow-up will be made. - She said the targeted dates end around 31st of March. Internal auditors will come back after the 31st of March, and they will request the issue tracker to track the work I order to resolve each finding where it will have a column that will see that the management has addressed this finding. - The MM commented in terms of the vulnerability of the systems, he said an action plan would have to be drafted and developed. he said the action plan must also have timelines, so that at each point they will be able to report on the progress made. he concluded by saying that the municipality has the capacity of staffing. - Ms. Wait made a suggestion that recommendation be made to council. - On ICT governance, the chairperson said they are going to look at the implementation of disaster management and disaster recovery. - He said the next report on ICT should be about how they are implementing these particular scenarios. It must include the challenges that they're having within the ICT structure, the budget scenarios and what is required to do things better. - Director Kondile replied by saying that if the Municipality burns, yes data will be lost, however this is a standing item in the steering committee. In terms of backup the ICT unit has a service provider that is based in East London that has an offsite backing, in case everything is destroyed. - Ms. Wait wanted to confirm with the director that there are 4 warm bodies, and are they able to handle the findings of the majority highest risk? She asked if the unit is understaffed or is there an issue of capability within the staff - Director Kondile said the capacity is not enough. SRVM has three towns and that needs the assistance of ICT. - It's not enough to deal with all the challenges they have, especially the issue of the help desk officer that can answer all satellite offices and deal with ICT related issues because people complain about the Internet that is down, which takes time for their complaints to be attended on time. - Ms. Wait suggested the Director for corporate services submits their shortcomings in the staffing so that the meeting can put forward a recommendation. And if the position is available on the ORGANOGRAM, but they unfunded or not basically, something in writing would assist in order to give a proper recommendation to Council. - MM said the municipality must first do a skills audit before more positions are created. RESOLUTIONS - The Audit Committee is not intending to make a recommendation to change the organogram. - The meeting requested director for corporate Services to furnish the current structure, needed qualifications for visibility of weaknesses. |  |
|  | 8.3 Review report on Annual report 2023/24 | - The meeting didn’t go through this report, however resolutions were made. RESOLUTIONS - The chairperson said they have done the scenarios on their side. Mr. Nkuntayi needs to complete processes on his side and summaries for both the audit committee and internal audit. However, the MM needs to do his reviews. - CIA was requested to furnish the next committee meeting with the final evaluations so that they can go to Council also. |  |
|  | 8.4 Progress report on the IA Implementation Plan | - The CIA reported that there were no findings due to lack of comments and from the management and non-submission of comments in IA engagements. - Findings that were raised in the previous financial year are being dealt with, the CIA assigned IA to do a follow-up with developer tracking documents to track the findings, to see if recommendations were implemented. - There was also no response to COAFs - Projects that were supposed to start in Quarter 2 couldn’t because they were busy with AG, they tried to execute. - The Chairperson said the Tracking documents have to be submitted at the next meeting with the implementation plan. - The CFO did confirm that they were busy with AG and outstanding information was provided before the new audit started. - Ms. Wait suggested the meeting take into consideration the timing of AG audits and schedules and make sure audits will not have issues of not sitting because of AG. - The chairperson suggested to the CIA to approach the management or vice versa when there is a backlog to stay safe and to ensure that reports are indeed submitted according, he should communicate. - He asked if it’s possible to have a tracking document for the next meeting. - Ms. Wait recommended that there should be amendments coming through into the charters because the new standard is effective now. - CIA committed to completing the data before 14 March 2025 RESOLUTIONS - The meeting took note of the report |  |
| 9. | General |  |  |
| 10. | Date of Next meeting | The CIA will inform the Chairperson of the next date of the meeting, |  |
| 11. | Closure | The meeting was adjourned at 16:27 |  |

## APPENDIX H – LONG TERM CONTRACTS AND PUBLIC PRIVATE PARTNERSHIPS

| Long Term Contracts (20 Largest Contracts Entered into during Year 2020/21) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| - R' 000 |  |  |  |  |  |
| Name of Service Provider (Entity or Municipal Department) | Description of Services Rendered by the Service Provider | Start Date of Contract | Expiry date of Contract | Project manager | Contract Value |
| Ibhabhathane Civil & Construction | Upgrading Of Roads and Stormwater in Enon Bersheba – Phase 2 | 13 Nov 2023 | 31 March 2026 | PMU | R 24 354 663,94 |
| ZKS | Refurbishment of Enon and Bersheba Water Borne Sanitation- Phase 1 | 09 May 2023 | 30 January 2026 | PMU | R 19 479 346 |
| ZKS Projects | Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo | April 2022 | February 2024 | PMU Manager | R 24 337 418,58 |
| Matela Civils | Construction of a New Community Hall in Moses Mabhida | January 2022 | October 2023 | PMU Manager | R 23 105 195.89 |
| R-Data (Pty) Ltd | Integrated MSCOA Financial Management Systems with internal control functions for SVRLM for a Period of 3 years | 2021/06/11 | 31 May 2024 | PMU Manager | R 4 451 040.50 |
| Xerox Eastern Cape (Pty) Ltd | Leasing Printers for a period of 3 years | 2021/06/14 | 31 May 2024 | PMU Manager | R 596 549.88 |

## PPENDIX J – DISCLOSURES OF FINANCIAL INTERESTS

| Disclosures of Financial Interests |  |  |
| --- | --- | --- |
| Period 1 July 2023 to 30 June 2024 |  |  |
| Position | Name | Description of Financial interests* (Nil / Or details) |
| Mayor | Cllr S Lucas | Nil |
| Member of Exco | Cllr S Lucas | Nil |
|  | Cllr K Smith | Properties in Kirkwood and Port Elizabeth |
|  | Cllr M C Payi | Nil |
| Councilor | Cllr L E Baka | Nil |
|  | Cllr N R Baxana | Shack in Molly Blackburn |
|  | Cllr H Bayini | Nil |
|  | Cllr M Bosman | Employed at A & R Attorneys |
|  | Cllr A Dyantyi | Black Youth corporate Pty LTD |
|  | Cllr S Hendricks | Nil |
|  | Cllr N Jagers | Nil |
|  | Cllr N Langbooi | Nil |
|  | Cllr N P Ncambele | Witrivier Communal Land Ezamabamba Construction |
|  | Cllr A Ndawo | Lusapho Citrus |
|  | Cllr S Nodonti | Nil |
|  | Clle XJ Jonas | Shares of Mbuyiselo and Luthando Citrus Farms |
|  | Cllr M Payi | Nomzamo Trust |
|  | Cllr Z Qusheka | Nil |
|  | Cllr K Smith | Properties in Kirkwood and Port Elizabeth |
| Municipal Manager | T Klaas | MEO at IEC, Property in Port Elizabeth |
| Chief Financial Officer | H Krapoh | Property in Upington |
| Directors | NA Mbongwe | Properties in East London Bold compass Performance Group |
|  | X W Mntonintshi | Property in East London |
|  | A P Kondile | Property in King Williamstown |

## APPENDIX K:  REVENUE COLLECTION PERFORMANCE BY VOTE AND BY SOURCE

## APPENDIX K (I): REVENUE COLLECTION PERFORMANCE BY VOTE

## APPENDIX K (ii): REVENUE COLLECTION PERFORMANCE BY SOURCE

## APPENDIX L:  CONDITIONAL GRANTS RECEIVED: EXCLUDING MIG

## APPENDIX M:  CAPITAL EXPENDITURE – NEW & UPGRADE/RENEWAL PROGRAMMES

## APPENDIX M (I): CAPITAL EXPENDITURE - NEW ASSETS PROGRAMME

## APPENDIX M (ii): CAPITAL EXPENDITURE – UPGRADE/RENEWAL PROGRAMME

## APPENDIX N – CAPITAL PROGRAMME BY PROJECT 2024/2025

The Infrastructure Planning and Development had the below Capital Projects in 2024/2025 as part of the MIG. WSIG,INEP & EPWP grants

| Project Name | Contractor Name | Consultant Name | Funder | Budgeted In 2024/2025 | Status Quo |
| --- | --- | --- | --- | --- | --- |
| Upgrading of Roads &Stormwater in Enon and Bersheba – Phase 2 | N/A | LA Consultant Engineers | MIG | R 11 069 402 | Construction phase |
| Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo | Matela Civil and Construction | Melokuhle Management | MIG | R 3 112 900 | Project is in construction phase. |
| Construction of Multi- Purpose Sports Recreational Facility in Nomathamsanqa in Addo | N/A | LA Consultant Engineers | MIG | R 10 000 000 | Complete |
| Construction of a New Community Hall in Moses Mabhida | ZKS Projects | Buchule Engineers | MIG | R 4 030 119.00 | Completed |
| Refurbishment of Enon and Bersheba Water Borne Sanitation- Phase 1 | ZKS Projects | Black Mountain Engineers | MIG | R 4 990 690 | Construction phase |
| Emergency flood works in Vygie and Adam Street | N/A | LA Consultant | MIG | R2 446 218 | Completed |
| Zinyoka Electrification | N/A | Vokon | INEP | R 6 512 000 | Project completed. |
| 15 km Zinyoka MV Line | N/A | Vokon | INEP | R 4 000 0000 | Completed |
| Electrification of Aqua Park Household | N/A | Vokon | INEP | R 7 036 000 | Completed |
| Kirkwood WWTW - Green Drop Reprioritization | N/A | Lech Consultants | WSIG | R 14 785 446.00 | Completed. |
| Nomathamsanqa: Completion of Water Backlogs | N/A | Bosch Projects | WSIG | R 2 96 619,80 | Completed |
| Refurbishment of Kirkwood & Addo Wastewater Pumps | N/A | Lech Consultants | WSIG | R 9 538 000.00 | Completed |
| Repairing of Roads & Stormwater cleaning in SRVM | N/A | N/A | EPWP | R 980 000.00 | Complete |

| Infrastructure Asset Management | N/A | LA Consultant | MIG | R 752 500 | Completed |
| --- | --- | --- | --- | --- | --- |
| Electrification of Bergsig Household | N/A | Inyusa Group Holdings | INEP | R 2 495 000 | Completed |
| Refurbishment of Kirkwood & Addo Wastewater Pumps (Kirkwood) | N/A | Lech Consultants | WSIG | R 9 095 796,00 | Completed |
| Provision of Water and Sanitation services of Nomathamsanqa and Molly Blackburn | N/A | Bosch Consultants | WSIG | R 6 507 689,29 | Complete |
| Refurbishment of Addo Sewer Treatment Works and Moses Mabhida Sewer Reticulation | N/A | Lech Consultants | WSIG | R 5 072 514.71 | Construction Phase |
| Installation of Energy saving Lights | N/A | Inyusa Group Holdings | EEDSM | R 4 000 000 | Complete |
| Upgrading of Kirkwood internal Roads | N/A | N/A | EPWP | R 949 000 | Complete |

## APPENDIX O – CAPITAL PROGRAMME BY PROJECT BY WARD 2024/2025

| WARDS | NATIONAL REGISTRATION NUMBER | PROJECT TITLE | REGISTER ED MIG FUNDS | TOTAL PLANNED EXPENDITU RE ON MIG FOR 2023/24 | TOTAL PLANNED EXPENDITU RE ON MIG FOR 2024/25 |
| --- | --- | --- | --- | --- | --- |
|  | R/EC/15300/18/20 | Upgrading of | 24 354 663,94 | ____________ | 8 069402 |
| Ward 8 |  | roads |  |  |  |
|  |  | &stormwater |  |  |  |
|  |  | in Enon and |  |  |  |
|  |  | Bersheba- |  |  |  |
|  |  | phase 2 |  |  |  |
| Ward 5&6 | CS/EC/2020/21/1 | Construction | 24 337 | 8 000 000 | 3 168327 |
|  | 1/67 | of multi- | 418,58 |  |  |
|  |  | Purpose sport |  |  |  |
|  |  | recreational |  |  |  |
|  |  | facility in |  |  |  |
|  |  | Nomathamsanqa |  |  |  |
|  |  | in Addo |  |  |  |
| Ward 1 | CS/EC/2020/21/6 | Construction | 14 411377,89 | 4 056 432 | 2 348 070 |
|  | 8 | of a new |  |  |  |
|  |  | Community |  |  |  |

| WARDS | NATIONAL REGISTRATION NUMBER | PROJECT TITLE | REGISTER ED MIG FUNDS | TOTAL PLANNED EXPENDITU RE ON MIG FOR 2022/23 | TOTAL PLANNED EXPENDITU RE ON MIG FOR 2024/25 |
| --- | --- | --- | --- | --- | --- |
|  |  | Hall in Moses Mabida |  |  |  |
| Ward 8 | EC/2021/22//12/1 47 | Refurbishment of Enon and Bersheba water Borne sanitation | 13 948 110,39 | ____________ | 6 032 129 |
| Ward 4 | NYR | Augmentation of the waste reticulation network Paterson | 16 572 000.00 | ____________ | 1 467 804 |
| Ward 6 | NYR | Construction of Molly bulk water reticulation | 20 994 000,00 | ____________ | 2 000 000 |
| Ward 3 | NYR | Refurbishment of sewer line in Vygie street (emergency works) | 2 500 000,00 | ____________ | 2 446 217 |

## APPENDIX Q – SERVICE BACKLOGS EXPERIENCED BY THE COMMUNITY WHERE ANOTHER SPHERE OF GOVERNMENT IS RESPONSIBLE FOR

## SERVICE PROVISION

| Service Backlogs Experienced by the Community where another Sphere of Government is the Service Provider (where the municipality whether act on an agency basis) |  |  |
| --- | --- | --- |
| Services and Locations | Scale of backlogs | Impact of backlogs |
| Clinics: |  |  |
| Enon-Bersheba | Needs new building infrastructure | The entire word is served by mobile, and many people do not have access to health care |
| Housing: |  |  |
| All wards | No developments have occurred, and all wards have informal settlements | Informal settlements mushroom daily at an alarming rate. Risks of protest actions highly likely |
| Licensing and Testing Centre: | N/A | N/A |
| Schools (Primary and High): | N/A | N/A |
| Sports Fields: |  |  |
| Bersheba Sport field |  |  |
| Moses Mabida Stadium Nomathamsanqa Stadium Glen Connor and Zuney Sport fields | Development of new sport fields some needs total upgrades | Youth engagement in alternative means of social interaction like drug and alcohol abuse. |

## APPENDIX R – DECLARATION OF LOANS AND GRANTS MADE BY THE MUNICIPALITY

| Declaration of Loans and Grants made by the municipality: Year 0 |  |  |  |  |
| --- | --- | --- | --- | --- |
| All Organisation or Person in receipt of Loans */Grants* provided by the municipality | Nature of project | Conditions attached to funding | Value Year 0 R' 000 | Total Amount committed over previous and future years |
| Dept of Public Works (EPWP) | Infrastructure | EPWP projects must comply with the project selection criteria determined in the EPWP grant manual, the EPWP guidelines set by the Department of Public Works and Infrastructure (DPWI), the latest EPWP. Ministerial Determination, the EPWP Recruitment Guidelines and the National Minimum Wage Act of 2018 including applicable gazettes | 1 206 |  |
| Dept of Cooperative Governance and Traditional Affairs (MIG) | Infrastructure | Municipal allocations must be fully committed to registered projects prior to the year of implementation and be informed by the Integrated Development Plans (IDPs) and three-year capital plans which are aligned to. the relevant One Plan of districts areas developed under the District Development Model | 28 785 |  |
| Department of Water and Sanitation (WSIG) | Infrastructure | Municipalities must submit business plans signed off by their Accounting Officer in line with their Water. Services Development Plans (WSDPs) and Integrated Development Plans (IDPs) | 20 000 |  |
| Department of Energy (INEP) | Infrastructure | Municipalities must register electrification business plans for bulk infrastructure with INEP and abide by the advice or guidance of the Department of Mineral Resources and Energy (DMRE) regarding the central planning and co-ordination for such bulk infrastructure | 10 512 |  |

## APPENDIX S – NATIONAL AND PROVINCIAL OUTCOMES FOR LOCAL GOVERNMENT

| National and Provincial Outcomes for Local Government |  |  |
| --- | --- | --- |
| Outcome/Output | Progress to date | Number or Percentage Achieved |
| Output: Improving access to basic services | All our formal households have access to water, sanitation and refuse removal services. Electricity sits at 75%. | Access to water 100% |
|  |  | Sanitation |
| Output: Implementation of the Community Work Programme | The municipality participates in CWP with an implementing agent |  |
| Output: Deepen democracy through a refined Ward Committee model | All wards have established ward committees. War rooms and ward committees are not functioning effectively | 8 wards – 100% |
| Output: Administrative and financial capability | We depend mostly on grants for capital projects |  |